## NEO
NEO BLDG. 7 BRICK LEFT TO FABRICATE FOR FRAMING
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
7.01A |  | 60 |  | COMPLETE IN MILLING | 1850 | 1850 | 0 |  | 100%
7.01B |  | 60 |  | COMPLETE IN MILLING | 1878 | 1878 | 0 |  | 100%
7.02A |  | 32 |  | COMPLETE IN MILLING | 998 | 998 | 0 |  | 100%
7.02B |  | 3 |  | COMPLETE IN MILLING | 106 | 106 | 0 |  | 100%
7.03A |  | 55 |  | COMPLETE IN MILLING | 1619 | 1619 | 0 |  | 100%
7.03B |  | 50 |  | COMPLETE IN MILLING | 1450 | 1450 | 0 |  | 100%
7.04A |  |  |  | N/A |  |  |  |  | N/A
7.04B |  | 36 |  | COMPLETE IN MILLING | 1183 | 1183 | 0 |  | 100%
7.05A |  | 4 |  | COMPLETE IN MILLING | 111 | 111 | 0 |  | 100%
7.05B |  |  |  | N/A |  |  |  |  | N/A
7.05C |  | 10 |  | COMPLETE IN MILLING | 318 | 318 | 0 |  | 100%
11 |  | 310 |  |  | 9513 | 9513 | 0 |  | 100%
NEO BLDG. 7 CW LEFT TO FABRICATE FOR 707
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
7.01A |  | 56 |  | COMPLETE IN MILLING | 3186 | 3186 | 0 |  | 100%
7.01B |  | 52 |  | COMPLETE IN MILLING | 5541 | 5541 | 0 |  | 100%
7.02A |  | 58 |  | COMPLETE IN MILLING | 2392 | 2392 | 0 |  | 100%
7.02B |  | 44 |  | COMPLETE IN MILLING | 1437 | 1437 | 0 |  | 100%
7.03A |  | 59 |  | COMPLETE IN MILLING | 2488 | 2488 | 0 |  | 100%
7.03B |  | 44 |  | COMPLETE IN MILLING | 2211 | 2211 | 0 |  | 100%
7.04A |  | 52 |  | COMPLETE IN MILLING | 1771 | 1771 | 0 |  | 100%
7.04B |  | 32 |  | COMPLETE IN MILLING | 1737 | 1737 | 0 |  | 100%
7.05A |  | 5 |  | COMPLETE IN MILLING | 266 | 266 | 0 |  | 100%
7.05B |  | 17 |  | COMPLETE IN MILLING | 425 | 425 | 0 |  | 100%
7.05C |  | 8 |  | COMPLETE IN MILLING | 408 | 408 | 0 |  | 100%
11 |  | 427 |  |  | 21862 | 21862 | 0 |  | 100%
NEO BLDG. 1 BRICK LEFT TO FABRICATE FOR FRAMING
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
1.05C |  | 13 |  | COMPLETE IN MILLING | 336 | 336 | 0 |  | 100%
1.01B |  | 48 |  | COMPLETE IN MILLING | 1340 | 1340 | 0 |  | 100%
1.01A |  | 74 |  | COMPLETE IN MILLING | 1974 | 1974 | 0 |  | 100%
1.04B |  | 43 |  | COMPLETE IN MILLING | 1310 | 1310 | 0 |  | 100%
1.04A |  | 35 |  | COMPLETE IN MILLING | 989 | 989 | 0 |  | 100%
1.03B |  | 49 |  | COMPLETE IN MILLING | 1285 | 1285 | 0 |  | 100%
1.03A |  | 31 |  | COMPLETE IN MILLING | 802 | 802 | 0 |  | 100%
1.02A |  | 41 |  | COMPLETE IN MILLING | 1165 | 1165 | 0 |  | 100%
1.02B |  | 55 |  | COMPLETE IN MILLING | 1520 | 1520 | 0 |  | 100%
1.05A |  | N/A |  | N/A |  |  | 0 |  | N/A
1.05B |  | N/A |  | N/A |  |  | 0 |  | N/A
11 |  | 389 |  |  | 10721 | 10721 | 0 |  | 100%
NEO BLDG. 1 CW LEFT TO FABRICATE FOR 707
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
1.05C | REC'D ALL INFO 3/15/23 | 8 |  | COMPLETE IN MILLING | 835 | 835 | 0 |  | 100%
1.01B | REC'D ALL INFO 3/9/23 | 44 |  | COMPLETE IN MILLING | 4463 | 4463 | 0 |  | 100%
1.01A | REC'D ALL INFO 3/14/23 | 60 |  | COMPLETE IN MILLING | 6114 | 6114 | 0 |  | 100%
1.04B | REC'D ALL INFO 3/16/23 | 36 |  | COMPLETE IN MILLING | 3755 | 3755 | 0 |  | 100%
1.04A | REC'D ALL INFO 3/16/23 | 44 |  | COMPLETE IN MILLING | 4165 | 4165 | 0 |  | 100%
1.03B | REC'D ALL INFO 3/14/23 | 49 |  | COMPLETE IN MILLING | 5117 | 5117 | 0 |  | 100%
1.03A | REC'D ALL INFO 3/16/23 | 45 |  | COMPLETE IN MILLING | 4318 | 4318 | 0 |  | 100%
1.02A | REC'D ALL INFO 3/9/23 | 42 |  | COMPLETE IN MILLING | 3787 | 3787 | 0 |  | 100%
1.02B | REC'D ALL INFO 3/16/23 | 62 |  | COMPLETE IN MILLING | 5421 | 5421 | 0 |  | 100%
1.05A | REC'D ALL INFO 3/15/23 | 15 |  | COMPLETE IN MILLING | 696 | 696 | 0 |  | 100%
1.05B | REC'D ALL INFO 3/15/23 | 45 |  | COMPLETE IN MILLING | 2001 | 2001 | 0 |  | 100%
ASSY BRACKETS | 2023-06-29 | BRACKETS |  | COMPLETE IN MILLING | 1443 | 1443 | 0 |  | 100% |  | SITE
12 |  | 450 |  |  | 42115 | 42115 | 0 |  | 100%
NEO BLDG. 3 BRICK LEFT TO FABRICATE FOR FRAMING
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
3.03B | 2023-04-04 | 46 |  | COMPLETE IN MILLING | 1450 | 1450 | 0 |  | 100%
3.03A | 2023-04-04 | 44 |  | COMPLETE IN MILLING | 1187 | 1187 | 0 |  | 100%
3.02B | 2023-04-04 | 41 |  | COMPLETE IN MILLING | 1095 | 1095 | 0 |  | 100%
3.02A | 2023-04-04 | 67 |  | COMPLETE IN MILLING | 1878 | 1878 | 0 |  | 100%
3.01B | 2023-04-04 | 60 |  | COMPLETE IN MILLING | 1677 | 1677 | 0 |  | 100%
3.01A | 2023-04-04 | 39 |  | COMPLETE IN MILLING | 1091 | 1091 | 0 |  | 100%
3.05C | 2023-04-04 | 6 |  | COMPLETE IN MILLING | 125 | 125 | 0 |  | 100%
3.04B | 2023-04-04 | 55 |  | COMPLETE IN MILLING | 1597 | 1597 | 0 |  | 100%
3.04A | 2023-04-04 | 50 |  | COMPLETE IN MILLING | 1347 | 1347 | 0 |  | 100%
3.05A | N/A | N/A |  | N/A |  |  |  |  | N/A
3.05B | N/A | N/A |  | N/A |  |  |  |  | N/A
3.01A B2 | 2023-04-25 | 20 |  | COMPLETE IN MILLING | 627 | 627 | 0 |  | 100%
3.02B B2 | 2023-04-26 | 3 |  | COMPLETE IN MILLING | 88 | 88 | 0 |  | 100%
3.03A B2 | 2023-04-26 | 14 |  | COMPLETE IN MILLING | 388 | 388 | 0 |  | 100%
3.03B B2 | 2023-04-26 | 26 |  | COMPLETE IN MILLING | 727 | 727 | 0 |  | 100%
3.01B B2 | 2023-05-09 | 22 |  | COMPLETE IN MILLING | 625 | 625 | 0 |  | 100%
3.04A B2 | 2023-05-09 | 3 |  | COMPLETE IN MILLING | 90 | 90 | 0 |  | 100%
3.04B B2 | 2023-05-09 | 13 |  | COMPLETE IN MILLING | 331 | 331 | 0 |  | 100%
3.05C B2 | 2023-05-17 | 4 |  | COMPLETE IN MILLING | 101 | 101 | 0 |  | 100%
19 |  | 513 |  |  | 14424 | 14424 | 0 |  | 100%
NEO BLDG. 3 CW LEFT TO FABRICATE FOR 707
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
3.01A | 2023-06-06 | 88 |  | COMPLETE IN MILLING | 9999 | 9999 | 0 |  | 100% |  | MISSING 387 [1] FROM KM
3.01B | 2023-06-05 | 66 |  | COMPLETE IN MILLING | 7681 | 7681 | 0 |  | 100%
3.02A | 2023-05-24 | 68 |  | COMPLETE IN MILLING | 7344 | 7344 | 0 |  | 100%
3.02B | 2023-05-23 | 48 |  | COMPLETE IN MILLING | 5564 | 5564 | 0 |  | 100% |  | MISSING 387 [1] FROM KM
3.03A | 2023-06-06 | 69 |  | COMPLETE IN MILLING | 7495 | 7495 | 0 |  | 100% | 2023-09-22 | MISSING 387 [4] FROM KM
3.03B | 2023-06-07 | 69 |  | COMPLETE IN MILLING | 7147 | 7147 | 0 |  | 100% | 2023-09-22
3.04A | 2023-05-25 | 48 |  | COMPLETE IN MILLING | 5840 | 5840 | 0 |  | 100% | 2023-12-11 | MISSING 437 [45] FROM KM
3.04B | 2023-05-31 | 64 |  | COMPLETE IN MILLING | 7612 | 7612 | 0 |  | 100% |  | MISSING 384 [14] FROM KM
3.05A | 2023-06-12 | 18 |  | COMPLETE IN MILLING | 1006 | 1006 | 0 |  | 100% | 2023-10-13 | MISSING 396 [15] FROM KM/11/28
3.05B | 2023-06-07 | 10 |  | COMPLETE IN MILLING | 853 | 853 | 0 |  | 100% | 2023-10-13 | MISSING 433 [12] FROM KM/11/28
3.05C | 2023-06-06 | 8 |  | COMPLETE IN MILLING | 999 | 999 | 0 |  | 100% |  | MISSING 434 [20] FROM KM
ASSY BRACKETS | 2023-07-20 | BRACKETS |  | COMPLETE IN MILLING | 1802 | 1802 | 0 |  | 100% | 2023-09-26 | SITE
FINS LVL 1-5 | 2023-09-26 | FINS |  | COMPLETE IN MILLING | 392 | 392 | 0 |  | 100% | 2023-10-06 | SITE
13 |  | 556 | 0 |  | 63734 | 63734 | 0 |  | 100%
NEO BLDG. 12 BRICK LEFT TO FABRICATE FOR FRAMING
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
12.01A | N/A | N/A |  | N/A | N/A | N/A | N/A |  | N/A
12.01B | 2023-04-24 | 36 |  | COMPLETE IN MILLING | 983 | 983 | 0 |  | 100%
12.02A | 2023-04-24 | 60 |  | COMPLETE IN MILLING | 1522 | 1522 | 0 |  | 100%
12.02B | 2023-04-25 | 64 |  | COMPLETE IN MILLING | 1686 | 1686 | 0 |  | 100%
12.03A | 2023-04-25 | 32 |  | COMPLETE IN MILLING | 848 | 848 | 0 |  | 100%
12.03B | 2023-04-25 | 3 |  | COMPLETE IN MILLING | 88 | 88 | 0 |  | 100%
12.05C | 2023-04-25 | 7 |  | COMPLETE IN MILLING | 170 | 170 | 0 |  | 100%
12.04A | 2023-04-25 | 44 |  | COMPLETE IN MILLING | 1091 | 1091 | 0 |  | 100%
12.04B | 2023-04-25 | 64 |  | COMPLETE IN MILLING | 1643 | 1643 | 0 |  | 100%
12.05A | N/A | N/A |  | N/A |  |  |  |  | N/A
12.05B | N/A | N/A |  | N/A |  |  |  |  | N/A
11 |  | 310 |  |  | 8031 | 8031 | 0 |  | 100%
NEO BLDG. 12 CW LEFT TO FABRICATE FOR 707
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
12.01A | 2023-04-17 | 36 |  | COMPLETE IN MILLING | 2123 | 2123 | 0 |  | 100% | 2023-10-23
12.01B | 2023-06-28 | 44 |  | COMPLETE IN MILLING | 4762 | 4762 | 0 |  | 100% | 2023-10-30
12.02A | 2023-05-01 | 52 |  | COMPLETE IN MILLING | 5489 | 5489 | 0 |  | 100% | 2023-11-06 | 2023-11-10
12.02B | 2023-05-01 | 59 |  | COMPLETE IN MILLING | 6350 | 6350 | 0 |  | 100% | 2023-11-20 | 2023-11-24
12.03A | 2023-07-12 | 58 |  | COMPLETE IN MILLING | 5555 | 5555 | 0 |  | 100% | 2023-12-01 | 2023-12-11
12.03B | 2023-07-14 | 44 |  | COMPLETE IN MILLING | 4828 | 4828 | 0 |  | 100% | 2023-12-08 | 2023-12-19
12.04A | 2023-07-21 | 44 |  | COMPLETE IN MILLING | 4195 | 4195 | 0 |  | 100% | 2023-12-22 | 2023-12-20
12.04B | 2023-07-24 | 63 |  | COMPLETE IN MILLING | 6136 | 6136 | 0 |  | 100% | 2023-12-29 | MISSING 1164 [64] FROM KM
12.05A | 2023-07-24 | 17 |  | COMPLETE IN MILLING | 667 | 667 | 0 |  | 100% | 2024-01-05 | 2024-01-09
12.05B | 2023-07-24 | 2 |  | COMPLETE IN MILLING | 132 | 132 | 0 |  | 100% | 2024-01-05 | 2024-01-09
12.05C | 2023-07-24 | 8 |  | COMPLETE IN MILLING | 783 | 783 | 0 |  | 100% | 2024-01-05 | MISSING 1164 [7] FROM KM
REL-NEO-OF12 STL BRACKETS | 2023-11-08 |  |  | COMPLETE IN MILLING | 1287 | 1287 | 0 |  | 100% | 11/17, 11/24, 12/8 | SITE
12 |  | 427 | 0 |  | 42307 | 42307 | 0 |  | 100%
NEO BLDG. 11 BRICK LEFT TO FABRICATE FOR FRAMING
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
11.01A | 2023-10-18 | 55 |  | COMPLETE IN MILLING | 1474 | 1474 | 0 |  | 100% | 2023-11-13 | 2023-11-14
11.01B | 2023-10-12 | 19 |  | COMPLETE IN MILLING | 503 | 503 | 0 |  | 100% | 2023-11-13 | 2023-11-14
11.01C | 2023-10-18 | 27 |  | COMPLETE IN MILLING | 655 | 655 | 0 |  | 100% | 2023-11-13 | 2023-11-14
11.02A | 2023-08-01 | 58 |  | COMPLETE IN MILLING | 1474 | 1474 | 0 |  | 100% | 2023-09-22
11.02B | 2023-09-13 | 46 |  | COMPLETE IN MILLING | 1258 | 1258 | 0 |  | 100% | 2023-10-02
11.03A | 2023-09-18 | 32 |  | COMPLETE IN MILLING | 852 | 852 | 0 |  | 100% | 2023-10-09
11.03B | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A
11.04A | 2023-09-13 | 46 |  | COMPLETE IN MILLING | 1180 | 1180 | 0 |  | 100% | 2023-10-16
11.04B | 2023-09-13 | 48 |  | COMPLETE IN MILLING | 1274 | 1274 | 0 |  | 100% | 2023-10-23
11.04C | 2023-09-13 | 42 |  | COMPLETE IN MILLING | 1210 | 1210 | 0 |  | 100% | 2023-10-30 | 2023-11-14
11.05A | 2023-10-05 | 5 |  | COMPLETE IN MILLING | 154 | 154 | 0 |  | 100% | 2023-11-20
11.05B | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A
11.05C | 2023-10-05 | 4 |  | COMPLETE IN MILLING | 118 | 118 | 0 |  | 100% | 2023-11-20
13 |  | 382 | 0 |  | 10152 | 10152 | 0 |  | 100%
NEO BLDG. 11 CW LEFT TO FABRICATE FOR 707
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
11.02A | 2023-08-01 | 66 |  | COMPLETE IN MILLING | 6840 | 6840 | 0 |  | 100% | 2023-01-12
11.02B | 2023-09-19 | 40 |  | COMPLETE IN MILLING | 4491 | 4491 | 0 |  | 100% | 2024-02-02
11.03A | 2023-10-10 | 66 |  | COMPLETE IN MILLING | 5055 | 5055 | 0 |  | 100% | 2024-02-09
11.03B | 2023-09-18 | 28 |  | COMPLETE IN MILLING | 2202 | 2202 | 0 |  | 100% | 2024-02-16
11.04A | 2023-10-05 | 55 |  | COMPLETE IN MILLING | 5651 | 5651 | 0 |  | 100% | 2024-02-23
11.04B | 2023-10-05 | 48 |  | COMPLETE IN MILLING | 5313 | 5313 | 0 |  | 100% | 2024-02-23
11.04C | 2024-01-09 | 44 |  | COMPLETE IN MILLING | 3893 | 3893 | 0 |  | 100% | 2024-03-22
11.01A | 2023-11-28 | 62 |  | COMPLETE IN MILLING | 5215 | 5215 | 0 |  | 100% | 2024-03-29
11.01B | 2023-10-17 | 42 |  | COMPLETE IN MILLING | 2989 | 2989 | 0 |  | 100% | 2024-04-05 | 2024-04-12
11.01C | 2023-12-04 | 36 |  | COMPLETE IN MILLING | 2751 | 2751 | 0 |  | 100% | 2024-04-12 | 2024-04-16
11.05A | 2024-01-09 | 70 |  | COMPLETE IN MILLING | 1893 | 1893 | 0 |  | 100% | 2024-04-19
11.05B | 2024-01-08 | 16 |  | COMPLETE IN MILLING | 698 | 698 | 0 |  | 100% | 2024-04-19 | MISSING 434 [38] FROM ABC REC'D MATERIAL 4/12
11.05C | 2023-11-27 | 8 |  | COMPLETE IN MILLING | 598 | 598 | 0 |  | 100% | 3/22/24 NEW DATE 4/19 | MISSING 434 [22] FROM ABC REC'D MATERIAL 4/12
13 |  | 581 | 0 |  | 47589 | 47589 | 0 |  | 100%
NEO BLDG. 9 BRICK LEFT TO FABRICATE FOR FRAMING
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
OF09.01A | 2023-12-05 | 27 |  | COMPLETE IN MILLING | 862 | 862 | 0 |  | 100% | 2024-01-05 | 2024-01-09
OF09.01B | 2023-12-06 | 43 |  | COMPLETE IN MILLING | 1233 | 1233 | 0 |  | 100% | 2024-01-12 | 2024-01-18
OF09.02A | 2023-12-06 | 49 |  | COMPLETE IN MILLING | 1325 | 1325 | 0 |  | 100% | 2024-01-26 | 2024-01-31
OF09.02B | 2023-12-06 | 68 |  | COMPLETE IN MILLING | 1833 | 1833 | 0 |  | 100% | 2024-01-26 | 2024-02-01
OF09.03A | 2023-12-06 | 21 |  | COMPLETE IN MILLING | 666 | 666 | 0 |  | 100% | 2024-02-02
OF09.03B | 2023-12-11 | 50 |  | COMPLETE IN MILLING | 1458 | 1458 | 0 |  | 100% | 2024-02-09
OF09.04A | 2023-12-12 | 49 |  | COMPLETE IN MILLING | 1454 | 1454 | 0 |  | 100% | 2024-02-16 | 2024-02-26
OF09.04B | 2023-12-12 | 54 |  | COMPLETE IN MILLING | 1483 | 1483 | 0 |  | 100% | 2024-02-23 | MISSING 442 [3] FROM ABC
OF09.05A | 2023-12-12 | 3 |  | COMPLETE IN MILLING | 92 | 92 | 0 |  | 100% | 2024-03-01 | 2024-03-08
OF09.05B | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A
OF09.05C | 2023-12-12 | 10 |  | COMPLETE IN MILLING | 270 | 270 | 0 |  | 100% | 2024-03-01 | MISSING 442 [4] FROM ABC
11 |  | 374 | 0 |  | 10676 | 10676 | 0 |  | 100%
NEO BLDG. 9 CW LEFT TO FABRICATE FOR 707
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
OF09.05A | 2024-02-22 | 9 |  | COMPLETE IN MILLING | 1046 | 1046 | 0 |  | 100% | 2024-03-22 | 2024-03-26
OF09.04A | 2024-02-22 | 40 |  | COMPLETE IN MILLING | 5110 | 5110 | 0 |  | 100% | 2024-04-05
OF09.03B | 2024-02-26 | 62 |  | COMPLETE IN MILLING | 8679 | 8679 | 0 |  | 100% | 2024-04-26
OF09.03A | 2024-02-26 | 36 |  | COMPLETE IN MILLING | 4044 | 4044 | 0 |  | 100% | 2024-05-03 | 2024-05-07
OF09.02B | 2024-02-26 | 65 |  | COMPLETE IN MILLING | 8133 | 8133 | 0 |  | 100% | 2024-05-10 | MISSING 1272 [48] FROM KM
OF09.02A | 2024-02-26 | 48 |  | COMPLETE IN MILLING | 6361 | 6361 | 0 |  | 100% | 2024-05-24 | MISSING 384 [24] FROM KM
OF09.01A | 2024-01-29 | 44 |  | COMPLETE IN MILLING | 4601 | 4601 | 0 |  | 100% | 2024-05-31
OF09.01B | 2024-02-26 | 44 |  | COMPLETE IN MILLING | 5800 | 5800 | 0 |  | 100% | 2024-06-07 | 2024-06-14
OF09.04B | 2024-02-26 | 54 |  | COMPLETE IN MILLING | 6528 | 6528 | 0 |  | 100% | 2024-06-14 | MISSING 384 [36], 437 [54], 438 [54] FROM KM
OF09.05B | 2024-02-26 | 17 |  | COMPLETE IN MILLING | 724 | 724 | 0 |  | 100% | 2024-06-14 | MISSING 301 [2] FROM KM
OF09.05C | 2024-02-26 | 8 |  | COMPLETE IN MILLING | 962 | 962 | 0 |  | 100% | 2024-06-14 | MISSING 437 [6], 438 [6] FROM KM
REL-NEO-09-POST PAINT BULK (400SP) TO SHIPPING | 2024-02-21 | CAPS |  | COMPLETE IN MILLING | 2263 | 2263 | 0 |  | 100% | 2024-03-08 | OUTSOURCE PAINT
11 |  | 427 | 0 |  | 54251 | 54251 | 0 |  | 100%
NEO BLDG. 8 BRICK LEFT TO FABRICATE FOR FRAMING
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
OF08.02B | 2024-04-01 | 58 |  | COMPLETE IN MILLING | 1620 | 1620 | 0 |  | 100% | 2024-04-19
OF08.02A | 2024-04-01 | 64 |  | COMPLETE IN MILLING | 1715 | 1715 | 0 |  | 100% | 2024-04-26 | 2024-05-01
OF08.01B | 2024-04-03 | 85 |  | COMPLETE IN MILLING | 2611 | 2611 | 0 |  | 100% | 2024-05-17
OF08.05A | 2024-04-03 | 14 |  | COMPLETE IN MILLING | 483 | 483 | 0 |  | 100% | 2024-05-24
OF08.01A | 2024-04-03 | 86 |  | COMPLETE IN MILLING | 2620 | 2620 | 0 |  | 100% | 2024-06-07
OF08.04A | 2024-04-03 | 58 |  | COMPLETE IN MILLING | 1616 | 1616 | 0 |  | 100% | 2024-06-21
OF08.04B | 2024-04-03 | 64 |  | COMPLETE IN MILLING | 1630 | 1630 | 0 |  | 100% | 2024-08-16
OF08.03A | 2024-04-03 | 46 |  | COMPLETE IN MILLING | 1455 | 1455 | 0 |  | 100% | 2024-08-09
OF08.05B | 2024-04-03 | 1 |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2024-07-19
OF08.03B | 2024-04-03 | 69 |  | COMPLETE IN MILLING | 2023 | 2023 | 0 |  | 100% | 2024-07-19
OF08.05C | 2024-04-03 | 9 |  | COMPLETE IN MILLING | 226 | 226 | 0 |  | 100% | 2024-07-19
11 |  | 554 | 0 |  | 16023 | 16023 | 0 |  | 100%
NEO BLDG. 8 CW LEFT TO FABRICATE FOR 707
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
OF08.02B | 2024-05-28 | 75 |  | COMPLETE IN MILLING | 5911 | 5911 | 0 |  | 100% | 2024-06-21 | MISSING 1/4" ALU SHEETS
OF08.02A | 2024-06-10 | 70 |  | COMPLETE IN MILLING | 5692 | 5692 | 0 |  | 100% | 2024-07-12 | MISSING 1149 [303] FROM KM
OF08.01B | 2024-05-28 | 110 |  | COMPLETE IN MILLING | 8168 | 8168 | 0 |  | 100% | 2024-07-19 | MISSING 1149 [196] FROM KM
OF08.05A | 2024-06-10 | 39 |  | WAITING ON MATERIAL | 1106 | 1106 | 0 |  | 100% | 2024-08-02 | MISSING 1149 [92] FROM KM
OF08.01A | 2024-06-10 | 112 |  | COMPLETE IN MILLING | 5995 | 5995 | 0 |  | 100% | 2024-08-16 | MISSING 1149 [393] FROM KM
OF08.04A | 2024-06-10 | 75 |  | COMPLETE IN MILLING | 3697 | 3697 | 0 |  | 100% | 2024-09-20 | MISSING 1149 [340] FROM KM
OF08.04B | 2024-06-10 | 88 |  | COMPLETE IN MILLING | 4939 | 4939 | 0 |  | 100% | 2024-10-11 | MISSING 1149 [406] FROM KM
OF08.03A | 2024-06-10 | 72 |  | COMPLETE IN MILLING | 5485 | 5485 | 0 |  | 100% | 2024-10-25
OF08.05B | 2024-06-10 | 17 |  | COMPLETE IN MILLING | 663 | 663 | 0 |  | 100% | 2024-11-01
OF08.03B | 2024-06-10 | 85 |  | COMPLETE IN MILLING | 6479 | 6479 | 0 |  | 100% | 2024-11-15 | MISSING 432 [45] FROM KM
OF08.05C | 2024-06-10 | 10 |  | COMPLETE IN MILLING | 668 | 668 | 0 |  | 100% | 2024-11-15 | MISSING 432 [10] FROM KM
11 |  | 753 | 0 |  | 48803 | 48803 | 0 |  | 100%
|  | TOTAL UNITS RELEASED | TOTAL DELTA |  | TOTAL PARTS COMPLETE | TOTAL PARTS | TOTAL DELTA |  | TOTAL % OF COMPLETION
170 |  | 6453 | 0 |  | 400201 | 400201 | 0 |  | 100%
LEGEND
NEED MATERIAL
NEED INFORMATION
NEED INFO/MATERIAL
COMPLETE
NEO BLDG. SITE MATERIAL
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
REL-NEO-09.FINS - LVL 01 | 2024-01-02 | FINS |  | COMPLETE IN MILLING | 274 | 274 | 0 |  | 100% | 2024-05-10
REL-NEO-OF02_REGLAZING Release | 2024-01-11 | REGLAZING |  | COMPLETE IN MILLING | 2100 | 2100 | 0 |  | 100% | 2024-02-02
REL-NEO-02-BOP | 2024-01-16 | BOP |  | COMPLETE IN MILLING | 5004 | 5004 | 0 |  | 100% | 2024-02-09
REL-NEO-11 STARTER SILL | 2024-02-06 | STARTER |  | COMPLETE IN MILLING | 331 | 331 | 0 |  | 100% | 2024-03-08 | MISSING 1281 [30] FROM ABC
REL-NEO-03-BOP | 2024-02-19 | 261 |  | COMPLETE IN MILLING | 5038 | 5038 | 0 |  | 100% | 2024-03-01 | 2024-03-15
REL-NEO-FIELD - Bulk Korolath Hip shims Request | 2024-02-12 | SHIMS |  | COMPLETE IN MILLING | 5000 | 5000 | 0 |  | 100%
REL-NEO - OF02 closure sheets Level 02 coping | 2024-02-27 | BOP |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-03-08
REL-NEO-10-BOP | 2024-02-27 | 289 |  | COMPLETE IN MILLING | 3681 | 3681 | 0 |  | 100% | 2024-03-15
REL-NEO-OF11 STL BRACKETS | 2024-02-29 | BRACKETS |  | COMPLETE IN MILLING | 182 | 182 | 0 |  | 100% | 2024-03-13
REL-NEO-BOP-TYP-OF12 | 2024-03-04 | 184 |  | COMPLETE IN MILLING | 2208 | 2208 | 0 |  | 100% | 2024-04-05
REL-NEO-BOP-TYP-OF11 | 2024-03-04 | 213 |  | COMPLETE IN MILLING | 2556 | 2556 | 0 |  | 100% | 2024-05-03
REL-NEO-BOP-TYP-OF09 | 2024-03-04 | 166 |  | COMPLETE IN MILLING | 1905 | 1905 | 0 |  | 100% | 2024-05-31
REL-NEO-BOP-TYP-OF07 | 2024-03-04 | 184 |  | COMPLETE IN MILLING | 2085 | 2085 | 0 |  | 100% | 2024-06-28
REL-NEO-BOP-TYP-OF08 | 2024-03-04 | 225 |  | TO ARK | 2775 | 2775 | 0 |  | 100% | 2024-11-08
REL-NEO-OF08.BRACKETS.STL | 2024-03-04 | BRACKETS |  | COMPLETE IN MILLING | 188 | 188 | 0 |  | 100% | 2024-03-22
REL-NEO-FF_STL_BRACKET_BATCH3 | 2024-03-04 | BRACKETS |  | COMPLETE IN MILLING | 200 | 200 | 0 |  | 100% | 2024-04-01
FIELD REQUESTS | RELEASED MISSING LOADING DOCK CANOPY [3] 3/27/24 RELEASED URGENT FIELD REQUEST [1220] 3/27/24 RELEASED BULKHEAD ANCHOR FIX 4/9/24 RELEASED HIP SHIMS 4/9/24 RELEASED STEEL ANCHOR REQUEST 4/11/24 RELEASED NEO- CAPS FOR SITE 4/29/24 RELEASED REL-NEO-OF11 - ROOF BRACKETS 5/3/24 RELEASED REL-NEO-FIELD REQUEST - HOT 5/13/24 RELEASED REL-OF09. CAPS 5/28/24 RELEASED REL-NEO-OF06-09 ROOF EMBEDS 5/28/24 RELEASED REL-NEO-OF03.PROTECTION FRAME RELEASE 5/28/24 RELEASED Urgent Field request - Bumblefck Alabama 4.0 (400sp) 6/13/24 RELEASED REL-NEO-OF01 - COIL REMEDIATION SOUTH - FPN's (400SP) RELEASED 6/14/24 RELEASED REL-NEO-OF01 COIL REMEDIATION WEST 6/25/24 RELEASED REL-NEO-OF01 COIL REMEDIATION EAST 6/25/24 RELEASED REL-NEO-CAPS-SILVER SHADOW 6/25/24 RELEASED REL-NEO- Washer for J hooks 6/28/24 Urgent Field request - Bumblefck Alabama (400SP) to shipping SITE REL-NEO-FIELD WASHERS - (400A) to FIELD |  |  | COMPLETE IN MILLING | 22786 | 22786 | 0 |  | 100% | OF11 4/1/24 LOADING DOCK 4/12/24 MORE LOADING DOCK 4/12/24 STEEL ANCHOR REQUEST 4/19 BULKHEAD FIX 4/19/24 OF09 5/10/24 UREGENT FIELD REQUEST 4/26/24 HIP SHIMS 4/29/24 ROOF BRACKS FOR OF11 5/10 CAPS 5/10/24 REL-NEO-FIELD REQUEST - HOT REL-NEO-OF06-09 ROOF EMBEDS 6/14/24 REL-OF09. CAPS 6/21/24 REL-NEO-OF01 - COIL REMEDIATION SOUTH - FPN's (400SP) 6/21/24 REL-NEO-OF03.PROTECTION FRAME RELEASE 6/28/24 Urgent Field request - Bumblefck Alabama 4.0 (400sp) 6/28/24 REL-NEO-OF01 COIL REMEDIATION WEST 7/5/24 REL-NEO-OF01 COIL REMEDIATION EAST 7/5/24 REL-NEO-CAPS-SILVER SHADOW 7/5/24 Urgent Field request - Bumblefck Alabama (400SP) to shipping SITE 10/11/24 REL-NEO-FIELD WASHERS - (400A) to FIELD 10/25/24
REL-NEO OF05 North Entry Door Header Fix | 2024-03-14 | SITE FIX |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-03-22
REL-NEO - OF06 OF12 Steel chair brackets bulkhead | 2024-03-14 | BRACKETS |  | COMPLETE IN MILLING | 229 | 229 | 0 |  | 100% | OF 9 5/1/24 OF 7 5/15/24 OF 8 7/1/24 OF 6 8/1/24
REL-NEO-COP-UNTYPICAL-OF12 BULK TYPICAL | 2024-03-27 | 29 |  | COMPLETE IN MILLING | 297 | 297 | 0 |  | 100% | 2024-04-05
REL-NEO - OF01 Level 01 canopy and Level 04 Terrace - BEAMS + COLUMNS | 2024-04-01 | 32 |  | COMPLETE IN MILLING | 6338 | 6338 | 0 |  | 100% | 2024-07-12 | 129PCS READY FOR POST PAINT
REL-NEO - OF01 Level 01 canopy and Level 04 Terrace - COPING | 2024-04-01 | 196 |  | COMPLETE IN MILLING | 6042 | 6042 | 0 |  | 100% | 2024-07-12 | 382PCS READY FOR POST PAINT
REL-NEO - OF01 Level 04 Terrace Cladding | 2024-04-01 | 24 |  | COMPLETE IN MILLING | 403 | 403 | 0 |  | 100% | 2024-07-12 | 39PCS READY FOR POST PAINT
REL-NEO-COP-TYP-OF02 BULK TYPICAL | 2024-03-27 | 222 |  | COMPLETE IN MILLING | 2011 | 2011 | 0 |  | 100% | 2024-04-26
REL-NEO-COP-UNTYPICAL-OF02 BULK | 2024-03-27 | 79 |  | COMPLETE IN MILLING | 323 | 323 | 0 |  | 100% | 2024-04-26
REL-NEO-OF11 STARTER SILL RELEASE 2 | 2024-04-02 | STARTER |  | COMPLETE IN MILLING | 586 | 586 | 0 |  | 100% | 2024-05-31
REL-NEO - WW HEADER FLASHNGS OF05 | 2024-04-03 | FLASHING |  | COMPLETE IN MILLING | 41 | 41 | 0 |  | 100% | 2024-05-17
REL-NEO - WW HEADER FLASHNGS OF01 | 2024-04-03 | FLASHING |  | COMPLETE IN MILLING | 94 | 94 | 0 |  | 100% | 2024-04-19 | 94 PCS READY FOR POST PAINT 4/30/24
REL-NEO - WW HEADER FLASHNGS OF02 - BENT SHAPES (400SP) TO SITE | 2024-04-03 | FLASHING |  | COMPLETE IN MILLING | 96 | 96 | 0 |  | 100% | 2024-05-17
REL-NEO - WW HEADER FLASHNGS OF03 - BENT SHAPES (400SP) TO SITE | 2024-04-03 | FLASHING |  | COMPLETE IN MILLING | 96 | 96 | 0 |  | 100% | 2024-05-17
REL-NEO - WW HEADER FLASHNGS OF06 - BENT SHAPES (400SP) TO POST PAINT TO SITE | 2024-04-03 | FLASHING |  | COMPLETE IN MILLING | 79 | 79 | 0 |  | 100% | 2024-05-10 | 79PCS READY FOR POST PAINT 4/30/24
REL-NEO - WW HEADER FLASHNGS OF12 - BENT SHAPES (400SP) TO POST PAINT TO SITE | 2024-04-03 | FLASHING |  | COMPLETE IN MILLING | 34 | 34 | 0 |  | 100% | 2024-05-10 | 34PCS READY FOR POST PAINT 4/30/24
REL-NEO-BOP-UNTYPICAL-OF11 | 2024-04-08 | 39 |  | COMPLETE IN MILLING | 444 | 444 | 0 |  | 100% | 2024-05-03
REL-NEO - OF01 COIL REMEDIATION VMU - FPN (400SP) TO SITE ASAP | 2024-04-09 | SITE VMU |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-04-11
REL-NEO-BOP-UNTYPICAL-OF09 | 2024-04-15 | 29 |  | COMPLETE IN MILLING | 505 | 505 | 0 |  | 100% | 2024-05-31
REL-NEO-BOP-UNTYPICAL-OF07 | 2024-04-15 | 29 |  | COMPLETE IN MILLING | 271 | 271 | 0 |  | 100% | 2024-06-28
REL-NEO-BOP-UNTYPICAL-OF08 | 2024-04-15 | 63 |  | TO ARK | 594 | 594 | 0 |  | 100% | 2024-11-08
REL-NEO-BOP-TYP-OF06 | 2024-04-18 | 177 |  | COMPLETE IN MILLING | 1594 | 1594 | 0 |  | 100% | 2024-11-22
REL-NEO-BOP-UNTYPICAL-OF06 | 2024-04-18 | 37 |  | COMPLETE IN MILLING | 264 | 264 | 0 |  | 100% | 2024-11-22
REL-NEO-OF01 COPINGS & PARAPETS | 2024-04-18 | 14 |  | COMPLETE IN MILLING | 129 | 129 | 0 |  | 100% | 2024-07-12 | 14PCS POST PAINT READY FOR POST PAINT
REL-NEO-COP-UNTYPICAL-OF03 | 2024-04-19 | 50 |  | COMPLETE IN MILLING | 450 | 450 | 0 |  | 100% | 2024-09-13 | 50 POST PAITNED PART READY FOR MASTERCRAFT 7/19/24
REL-NEO - OF03 Level 01 - BEAMS & COLUMNS | 2024-04-19 | 30 |  | TO ARK | 5747 | 5747 | 0 |  | 100% | 2024-09-13 | 30 POST PAITNED PART READY FOR MASTERCRAFT 7/19/24
REL-NEO - OF03 - Level 01 Terrace COPING | 2024-04-19 | 78 |  | TO ARK | 4050 | 4050 | 0 |  | 100% | 2024-09-13 | 78 POST PAITNED PART READY FOR MASTERCRAFT 7/19/24
REL-NEO-OF03 LVL 4 TERRACE CLADDING | 2024-04-19 | 19 |  | TO ARK | 216 | 216 | 0 |  | 100% | 2024-09-13 | 19 POST PAITNED PART READY FOR MASTERCRAFT 7/19/24
REL-NEO-COP-TYP-OF03 | 2024-04-22 | 170 |  | COMPLETE IN MILLING | 4158 | 4158 | 0 |  | 100% | 2024-09-13 | 170 POST PAITNED PART READY FOR MASTERCRAFT 7/19/24
REL-NEO-OF08-CAP BULK RELEASE | 2024-05-28 | CAPS |  | COMPLETE IN MILLING | 1876 | 1876 | 0 |  | 100% | 2024-06-21 | 1876PCS READY FOR POST PAINT 6/20/24
REL-NEO-COP-TYP-OF12 | 2024-05-29 | 108 |  | COMPLETE IN MILLING | 2160 | 2160 | 0 |  | 100% | 2024-08-16
REL-NEO-COP-UNTYPICAL-OF12 | 2024-05-29 | 37 |  | COMPLETE IN MILLING | 488 | 488 | 0 |  | 100% | 2024-08-16
REL-NEO-OF12 LVL 01 BEAMNS & COLUMNS | 2024-06-06 | 42 |  | COMPLETE IN MILLING | 2977 | 2977 | 0 |  | 100% | 2024-11-15
REL-NEO-OF12 CANOPIES COPINGS | 2024-06-05 | 78 |  | COMPLETE IN MILLING | 3627 | 3627 | 0 |  | 100% | 2024-11-15
REL-NEO- OF12 TERRACE CLADDING LVL 04 | 2024-06-05 | 25 |  | COMPLETE IN MILLING | 705 | 705 | 0 |  | 100% | 2024-11-29
REL-NEO-COP-TYP-OF10 | 2024-06-06 | 85 |  | COMPLETE IN MILLING | 86 | 86 | 0 |  | 100% | 2024-09-27
REL-NEO-COP-UNTYPICAL-OF10 | 2024-06-10 | 86 |  | COMPLETE IN MILLING | 86 | 86 | 0 |  | 100% | 2024-09-27 | TO ANACOLOR FOR PAINT
REL-NEO-COP-TYP-OF11 | 2024-06-05 | 128 |  | COMPLETE IN MILLING | 1945 | 1945 | 0 |  | 100% | 2024-12-20
REL-NEO-COP-UNTYPICAL-OF11 | 2024-06-05 | 37 |  | COMPLETE IN MILLING | 558 | 558 | 0 |  | 100% | 2024-12-20
REL-NEO-OF11.TERRACE CLADDING LVL04 | 2024-06-06 | 16 |  | COMPLETE IN MILLING | 90 | 90 | 0 |  | 100% | 2024-11-15
REL-NEO-SOF-OF11-LVL1-BEAM & COLUMNS | 2024-06-06 | 18 |  | COMPLETE IN MILLING | 1152 | 1152 | 0 |  | 100% | 2024-12-20
REL-NEO-OF11.CANOPIES COPING LVL01 | 2024-06-06 | 183 |  | COMPLETE IN MILLING | 1332 | 1332 | 0 |  | 100% | 2025-01-10
REL-NEO-OF09.CANOPIES BEAM AND COLUMN COVERS LVL01 | 2024-06-06 | 24 |  | COMPLETE IN MILLING | 6423 | 6423 | 0 |  | 100% | 2025-02-07
REL-NEO-OF09.TERRACE CLADDING LVL04 | 2024-06-06 | 24 |  | COMPLETE IN MILLING | 789 | 789 | 0 |  | 100% | 2025-01-24
REL-NEO-COP-TYP-OF08 | 2024-06-14 | 153 |  | COMPLETE IN MILLING | 155 | 155 | 0 |  | 100% | 2024-12-20
REL-NEO-COP-UNTYPICAL-OF08 | 2024-06-14 | 49 |  | COMPLETE IN MILLING | 51 | 51 | 0 |  | 100% | 2024-12-20
REL-NEO-COP-TYP-OF06 | 2024-06-14 | 93 |  | COMPLETE IN MILLING | 94 | 94 | 0 |  | 100% | 2024-12-20
REL-NEO-COP-UNTYPICAL-OF06 | 2024-06-14 | 37 |  | COMPLETE IN MILLING | 38 | 38 | 0 |  | 100% | 2024-12-20
REL-NEO-OF07-TORNADO-REMAKES CW | 2024-07-10 |  |  | COMPLETE IN MILLING | 414 | 414 | 0 |  | 100% | 2024-07-19
REL-NEO-OF07-TORNADO-REMAKES BRK | 2024-07-10 |  |  | COMPLETE IN MILLING | 139 | 139 | 0 |  | 100% | 2024-07-19
REL-NEO-OF11-05A ADDITIONAL SLIDING DOOR PANELS | 2024-07-16 |  |  | COMPLETE IN MILLING | 199 | 199 | 0 |  | 100% | 2024-08-30
REL-NEO-STARTER SILL BULK | 2024-08-05 | STARTER |  | COMPLETE IN MILLING | 313 | 313 | 0 |  | 100% | 2024-08-30
REL-NEO-OF01 VESTIBULES ADDITIONAL PRESSWORKS | 2024-08-06 | VESTIBULES |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2024-08-30
REL-NEO-S1106-FIELD | 2024-08-06 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-08-16
REL-NEO-OF12-OF01 skins | 2024-08-06 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2024-08-09
REL-NEO-OF11 UNITS | 2024-08-07 |  |  | COMPLETE IN MILLING | 39 | 39 | 0 |  | 100% | 2024-08-30
REL-NEO-OF02COP-TORNADO REMAKES | 2024-08-15 |  |  | COMPLETE IN MILLING | 270 | 270 | 0 |  | 100% | 2024-08-30
REL-NEO-WT brackets for OF06 | 2024-08-22 |  |  | COMPLETE IN MILLING | 95 | 95 | 0 |  | 100% | 2024-09-13
REL-NEO ¦ REL-NEO-OF02_OF06_OF07_BH_DOOR_FIX | 2024-08-26 | 21 |  | COMPLETE IN MILLING | 128 | 128 | 0 |  | 100% | 2024-09-27
NEO-REL-OF01-Missing Skin | 2024-08-26 |  |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2024-09-06
REL-NEO-OF01 IN PLACE REMAKES | 2024-09-10 |  |  | COMPLETE IN MILLING | 91 | 91 | 0 |  | 100% | 2024-10-25
REL-NEO - OF01 NEW UPDATED DOOR FLASHINGS | 2024-09-10 | 16 |  | COMPLETE IN MILLING | 36 | 36 | 0 |  | 100% | 2024-09-20
REL-NEO-C-002 FIELD PANEL | 2024-09-10 |  |  | COMPLETE IN MILLING | 54 | 54 | 0 |  | 100% | 2024-10-11
REL-NEO-OF03 MFC5509-0001 BEAM CUTOUT COVERS | 2024-09-10 |  |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-10-11
REL-NEO-OF02 LEVEL 01 SOFFIT | 2024-09-10 |  |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2024-10-25
REL-NEO-FIELD ANCHOR - S1225 (400A) to field | 2024-09-10 |  |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-10-11
REL-NEO-OF05 DOOR HEIGHT REMEDIAL | 2024-09-10 |  |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2024-10-11
REL-NEO-OF02-COPING REMAKES REVISED | 2024-09-25 |  |  | COMPLETE IN MILLING | 102 | 102 | 0 |  | 100% | 2024-09-27
REL-NEO-LONGBOARD - BSH's | 2024-10-02 |  |  | COMPLETE IN MILLING | 250 | 250 | 0 |  | 100% | 2024-10-11
REL-NEO-OF05 LEVEL 01 NORTH SOUTH CANOPIES | 2024-10-02 |  |  | COMPLETE IN MILLING | 282 | 282 | 0 |  | 100% | 2024-10-11
REL-NEO-OF05 REMEDIAL DOOR FLASHINGS | 2024-10-17 |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2024-10-18
NEO-REL-OF12-COPING-REMAKES | 2024-10-17 | 11 |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100%
REL-NEO-OF02 REMAKES | 2024-10-29 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-11-08
REL-NEO-OF06 Anchors. | 2024-11-14 |  |  | COMPLETE IN MILLING | 2050 | 2050 | 0 |  | 100% | 2025-01-17
REL-NEO - OF07 BEAMS & COLUMNS | 2024-11-18 | 60 |  | COMPLETE IN MILLING | 79 | 79 | 0 |  | 100% | 2025-02-07
REL-NEO-OF07 LVL 01 CANOPIES AND TERRACE CLADDINGS | 2024-11-18 | 93 |  | COMPLETE IN MILLING | 279 | 279 | 0 |  | 100% | 2025-02-07
REL-NEO-OF07 LVL 04 TERRACE CLADDING | 2024-11-18 | 25 |  | COMPLETE IN MILLING | 27 | 27 | 0 |  | 100% | 2025-01-31
REL-NEO-OF08 LVL 01 CANOPIES COPING | 2024-11-18 | 93 |  | COMPLETE IN MILLING | 277 | 277 | 0 |  | 100% | 2025-02-28
REL-NEO-OF08- BEAMS & COLUMNS | 2024-11-18 | 102 |  | COMPLETE IN MILLING | 115 | 115 | 0 |  | 100% | 2025-02-28
REL-NEO-OF08 LVL 04 TERRACE CLADDINGS | 2024-11-18 | 25 |  | COMPLETE IN MILLING | 27 | 27 | 0 |  | 100% | 2025-02-28
REL-NEO-OF06-BEAM & COVERS | 2024-11-18 | 27 |  | COMPLETE IN MILLING | 46 | 46 | 0 |  | 100% | 2025-02-28
REL-NEO-OF06-CANOPY COPINGS | 2024-11-18 | 120 |  | COMPLETE IN MILLING | 496 | 496 | 0 |  | 100% | 2025-03-14
REL-NEO-OF06-TERRACE CLADDING LVL 04 | 2024-11-18 | 35 |  | COMPLETE IN MILLING | 39 | 39 | 0 |  | 100% | 2025-02-28
REL-NEO-OF10 Window Wall top flashing | 2024-11-18 |  |  | COMPLETE IN MILLING | 44 | 44 | 0 |  | 100% | 2025-01-03
REL-NEO-OF05 PANS - ALU.S (400SP) TO SITE | 2024-11-18 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-11-22
REL-NEO- OF01-OF06 TERRACE SOFFIT WITH NO COLUMN | 2024-11-18 |  |  | COMPLETE IN MILLING | 89 | 89 | 0 |  | 100% | 2025-01-10
REL-NEO-OF01-WEST STAIRCASE | 2024-11-18 |  |  | COMPLETE IN MILLING | 101 | 101 | 0 |  | 100% | 2025-01-10
REL-NEO-OF01-EAST STAIRCASE | 2024-11-18 |  |  | COMPLETE IN MILLING | 82 | 82 | 0 |  | 100% | 2025-01-10
REL-NEO-OF10 - Loading Dock | 2024-11-18 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2025-01-03
REL-NEO-OF12 - Loading dock canopy | 2024-12-09 |  |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2024-01-03
REL-NEO-OF01 Reclad final | 2024-12-09 |  |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2024-12-13
REL-NEO-OF11 Header Flashing | 2024-12-09 |  |  | COMPLETE IN MILLING | 39 | 39 | 0 |  | 100% | 2024-12-13
REL-NEO-OF07 Header flashing | 2024-12-09 |  |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2024-12-13
REL-NEO-OF09 Header flashing | 2024-12-09 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-12-13
REL-NEO-OF05 TERRACE SOFFIT PRESSWORKS | 2024-12-09 |  |  | COMPLETE IN MILLING | 36 | 36 | 0 |  | 100% | 2024-12-06
REL-NEO-OF05 PRESSWORK REQUESTED BY SITE TEAM | 2024-12-09 |  |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2024-12-06
REL-NEO-OF01-Loading dock skin | 2024-08-26 |  |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100%
REL-NEO-OF10 LEVEL 04 TERRACE CLADDING | 2025-01-02 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2025-01-17
REL-NEO-OF10-SOUTH CANOPIES CLADDING | 2025-01-02 |  |  | COMPLETE IN MILLING | 158 | 158 | 0 |  | 100% | 2025-01-17
REL-NEO-OF10-NORTH CANOPIES CLADDING | 2025-01-02 |  |  | COMPLETE IN MILLING | 158 | 158 | 0 |  | 100% | 2025-01-17
REL-NEO-STAIRWELL SPANDREL PANS - FPNS (400SP) TO SITE | 2025-01-03 |  |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2025-01-09
REL-NEO-ASI MESSAP - ALU (400SP) TO SITE - SUPAHHH HOT | 2025-01-06 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2025-01-09
REL NEO-Added Steel Anchors | 2025-01-10 |  |  | COMPLETE IN MILLING | 52 | 52 | 0 |  | 100% | 2025-01-22
REL-NEO-OF10 terrace coping | 2025-01-13 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-01-31
REL-NEO-OF02 North elevation Level 1 caps for view cable | 2025-01-24 |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2025-01-31
RE-NEO-OF09 - Additional Canopy | 2025-01-24 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2025-01-31
REL-NEO-OF02 Base cap at east and west entrance | 2025-01-24 |  |  | COMPLETE IN MILLING | 31 | 31 | 0 |  | 100% | 2025-01-31
REL-NEO-OF11 TERRACE FIELD REMAKE PAN | 2025-01-24 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-01-27
REL-NEO-NORTH CANOPY - PATS MASSIVE PIECE | 2025-01-24 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-01-27
REL-NEO-OF09-COPING-TYPICAL | 2025-01-24 |  |  | COMPLETE IN MILLING | 101 | 101 | 0 |  | 100% | 2025-01-31
REL-NEO-OF09-COPING-ATYPICAL | 2025-01-24 |  |  | COMPLETE IN MILLING | 45 | 45 | 0 |  | 100% | 2025-01-31
REL-NEO-OF12 View Cable caps | 2025-01-30 |  |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100% | 2025-02-07
REL-NEO-OF01- Metal pans at Open Collab, RFI - 1363 | 2025-01-31 |  |  | COMPLETE IN MILLING | 15 | 15 | 0 |  | 100% | 2025-02-14
REL-NEO-OF02 - LEVEL 01 SOFFIT INCORRECT FROM ASI | 2025-01-31 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-02-05
REL-NEO-OF07-COPING-TYPICAL | 2025-01-31 |  |  | COMPLETE IN MILLING | 119 | 119 | 0 |  | 100% | 2025-02-14
REL-NEO-OF07-COPING-ATYPICAL | 2025-01-31 |  |  | COMPLETE IN MILLING | 37 | 37 | 0 |  | 100% | 2025-02-14
REL-NEO-OF07 LOADING DOCK | 2025-02-04 |  |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2025-02-21
REL-NEO-OF12- CANOPY REMAKES | 2025-02-07 |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2025-02-10
REL-NEO-OF05 Level 4-View cable caps | 2025-02-17 |  |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2025-02-21
REL-NEO-BOP MISC | 2025-02-17 |  |  | COMPLETE IN MILLING | 400 | 400 | 0 |  | 100% | 2025-02-21
REL-NEO-OF10 LEVEL 05 FINS ( CORNICE PANELS ) | 2025-02-17 |  |  | COMPLETE IN MILLING | 274 | 274 | 0 |  | 100% | 2025-02-28
REL-NEO-OF11-SLIDING_DOOR | 2025-02-17 |  |  | COMPLETE IN MILLING | 53 | 53 | 0 |  | 100% | 2025-02-28
REL-NEO-OF02-North elevation Level 1 caps for view cable | 2025-02-19 |  |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100% | 2025-02-28
REL-NEO-OF02 South revolving door corner skin | 2025-02-19 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-28
REL-NEO-OF02 South canopy door vertical cover | 2025-02-19 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-02-28
REL-NEO-ANTI WALKING BLOCK | 2025-02-19 |  |  | COMPLETE IN MILLING | 700 | 700 | 0 |  | 100% | 2025-02-28
REL-NEO-OF 10- East elevation- Right grain direction. | 2025-02-20 |  |  | COMPLETE IN MILLING | 32 | 32 | 0 |  | 100% | 2025-03-07
REL-NEO-OF10 East elevation - Left Direction | 2025-02-20 |  |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2025-03-07
REL-NEO-OF09 SILL LEVEL 01 EXTERNAL COVERS REMEDIAL | 2025-02-21 |  |  | COMPLETE IN MILLING | 108 | 108 | 0 |  | 100% | 2025-03-07
REL-NEO-OF02 Bumblefvck - FPN (400SP) TO SITE | 2025-02-24 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-03-07
REL-NEO-OF03 BEAM COVER CANOPY EAST (NEW ARCH. REQUEST) | 2025-02-27 | 48 |  | COMPLETE IN MILLING | 1632 | 1632 | 0 |  | 100% | 2025-03-21
REL-NEO-OF11-COPING_REMAKES | 2025-03-03 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-03-07
REL-NEO-OF12-BEANS & TAPAS REMAKES | 2025-03-03 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-03-07
REL-NEO-OF09-COPING_REMAKES | 2025-03-03 |  |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2025-03-07
REL-NEO-OF02-COPING_REMAKES | 2025-03-03 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-03-07
REL-NEO-OF06-BOP_REMAKES | 2025-03-03 |  |  | COMPLETE IN MILLING | 240 | 240 | 0 |  | 100% | 2025-03-14
REL-NEO-OF06 FINS LEVEL 04 ( eyebrow copings ) | 2025-03-05 | 50 |  | COMPLETE IN MILLING | 1398 | 1398 | 0 |  | 100% | 2025-04-04
REL-NEO-END CAPS | 2025-03-07 |  |  | COMPLETE IN MILLING | 80 | 80 | 0 |  | 100% | 2025-03-14
REL-NEO-OF07 REMAKE - PAN(SP) TO SITE | 2025-03-07 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-03-07
REL-NEO-OF10-South elevation _ Right Grain Direction | 2025-03-07 |  |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2025-03-21
REL-NEO-OF09 typical coping pieces Remakes | 2025-03-13 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-03-21
REL-NEO-OF11-COPING_REMAKE | 2025-03-13 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-03-21
REL-NEO-BOP_Z's | 2025-03-14 |  |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2025-03-21
REL-NEO-OF10_MISC PANS | 2025-03-20 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2025-04-04
REL-NEO-OF09- NE corner level 1 fix | 2025-03-20 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-04
REL-NEO-OF11 - Additional Bas cover above south canopy | 2025-03-20 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-04
REL-NEO-OF11 - Canopy pan remake | 2025-03-20 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-04-04
REL-NEO-OF09- Skin for Lev 4 Soffit | 2025-03-20 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-04-04
REL-NEO-OF08 Terrace Soffit | 2025-03-21 |  |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100% | 2025-04-04
REL-NEO-OF03-Revolving door cover pieces | 2025-03-24 |  |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2025-04-11
REL-NEO-OF02- Revolving door cover trim | 2025-03-24 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-04-11
REL-NEO-OF05 - Loading dock Extended pans - | 2025-03-24 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-04-11
REL-NEO-OF01-cover for dented pan on south | 2025-03-24 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-04-04
REL-NEO - OF03 LVL 01 ADDITIONAL BEAMS & COVERS CANOPY - FPNS (SP) | 2025-03-25 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-04-11
REL-NEO-OF10 - West Reclad | 2025-03-28 |  |  | COMPLETE IN MILLING | 94 | 94 | 0 |  | 100% | 2025-04-11
REL-NEO-COP-TYP-OF08 - COP ASSEMBLY | 2025-03-31 |  |  | COMPLETE IN MILLING | 82 | 82 | 0 |  | 100% | 2025-04-18 | PAT HAS REMAINING 71PCS WITH HIM FOR ASSEMBLY
REL-NEO-COP-UNTYPICAL-OF08 COP ASSY | 2025-03-31 |  |  | COMPLETE IN MILLING | 49 | 49 | 0 |  | 100% | 2025-04-18
REL-NEO-OF02 View cable covers. | 2025-04-04 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-04-18
REL-NEO-OF10 Hollow metal doors flashing | 2025-04-04 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2025-04-18
REL-NEO-OF11- Pans for Flyby units | 2025-04-10 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-18
REL-NEO-OF10-Terrace corner pieces | 2025-04-10 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-04-18
REL-NEO-OF11 - North canopy pieces | 2025-04-10 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-18
REL-NEO-OF07-SOUTH CANOPY | 2025-04-10 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-18
REL-NEO-OF05 - Extended loading dock pans | 2025-04-11 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-04-18
REL-NEO-TEST PIECES (SP) TO SITE | 2025-04-14 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2025-04-18
REL-NEO-OF08 REMAKE | 2025-04-15 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-18
REL-NEO-OF08 LVL 01 CANOPIES COPING | 2025-04-18 |  |  | COMPLETE IN MILLING | 93 | 93 | 0 |  | 100% | 2025-05-09
REL-NEO-OF08 LVL 04 TERRACE CLADDINGS | 2025-04-18 |  |  | IN PROGRESS | 0 | 25 | 25 | DEAN | 0% | 2025-05-16
REL-NEO-OF08- BEAMS & COLUMNS | 2025-04-18 |  |  | IN PROGRESS | 0 | 102 | 102 | DEAN | 0% | 2025-05-23
REL-NEO-Drip pans for OF08 louver | 2025-04-24 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2025-05-02
REL-NEO-OF06 Drip pans | 2025-04-24 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-05-02
REL-NEO-OF10- Canopy missing pieces | 2025-04-24 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-05-02
REL-NEO-OF09 canopy pieces. | 2025-04-29 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-05-02
189 |  | 4788 | 0 |  | 128968 | 129095 | 127 |  | 99.9%

## 10WT
10WT LEFT TO FABRICATE
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
1.01 | x | 27 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
1.02 | x | 85 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
1.03 | x | 92 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
1.04 | x | 99 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
1.05 | x | 104 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
1.06 | 2023-08-24 | 74 |  | COMPLETE IN MILLING | 3805 | 3805 | 0 |  | 100% | 2023-12-13
2.01 | x | 30 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
2.02 | x | 97 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
2.03 | x | 101 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
2.04 | x | 109 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
2.05 | x | 114 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
2.06 | 2023-08-28 | 79 |  | COMPLETE IN MILLING | 4045 | 4045 | 0 |  | 100% | 2024-01-17 | WAITING ON 496 [14] FROM KM
3.01 | x | 34 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
3.02 | x | 107 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
3.03 | x | 114 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
3.04 | x | 121 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
3.05 | x | 127 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
3.06 | 2023-08-29 | 89 |  | COMPLETE IN MILLING | 5569 | 5569 | 0 |  | 100% |  | WAITING ON 506 [89] FROM KM
4.01 | x | 49 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
4.02 | x | 119 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
4.03 | x | 126 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
4.04 | x | 134 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
4.05 | x | 140 |  | COMPLETE IN MILLING | 0 | 0 | 0 |  | 100%
4.06 | 2023-09-05 | 98 |  | COMPLETE IN MILLING | 5053 | 5053 | 0 |  | 100% | 2024-03-01 | WAITING ON 507 [15], 506 [94] FROM KM
5.02 | 2023-06-20 | 30 |  | COMPLETE IN MILLING | 981 | 981 | 0 |  | 100%
6.02 | 2023-06-20 | 32 |  | COMPLETE IN MILLING | 973 | 973 | 0 |  | 100%
7.01 | 2023-06-07 | 18 |  | COMPLETE IN MILLING | 1512 | 1512 | 0 |  | 100%
7.02 | 2023-06-20 | 36 |  | COMPLETE IN MILLING | 1055 | 1055 | 0 |  | 100%
7.03 | 2023-06-20 | 18 |  | COMPLETE IN MILLING | 1616 | 1616 | 0 |  | 100%
8.02 | 2023-06-21 | 32 |  | COMPLETE IN MILLING | 1045 | 1045 | 0 |  | 100%
5.01 |  | 0 |  | TYPICAL PARTS ONLY | 1390 | 1390 | 0 |  |  |  | REFER TO 20.XX
5.03 |  | 0 |  | TYPICAL PARTS ONLY | 1463 | 1463 | 0 |  |  |  | REFER TO 20.XX
6.01 |  | 0 |  | TYPICAL PARTS ONLY | 1323 | 1323 | 0 |  |  |  | REFER TO 20.XX
6.03 |  | 0 |  | TYPICAL PARTS ONLY | 1466 | 1466 | 0 |  |  |  | REFER TO 20.XX
8.01 |  | 0 |  | TYPICAL PARTS ONLY | 1316 | 1316 | 0 |  |  |  | REFER TO 20.XX
8.03 |  | 0 |  | TYPICAL PARTS ONLY | 369 | 369 | 0 |  |  |  | REFER TO 20.XX
20.01 | 2023-07-18 | 23 |  | COMPLETE IN MILLING | 1360 | 1360 | 0 |  | 100% | 2023-09-22
20.02 | 2023-07-31 | 24 |  | COMPLETE IN MILLING | 1407 | 1407 | 0 |  | 100% | 2023-10-13
20.03 | 2023-08-08 | 30 |  | COMPLETE IN MILLING | 1635 | 1635 | 0 |  | 100% | 2024-01-22 | WAITING ON 517 [20] FROM KM
20.04 | 2023-09-18 | 18 |  | COMPLETE IN MILLING | 1112 | 1112 | 0 |  | 100% | 2024-01-23 | WAITING ON 517 [13] FROM KM
40 |  | 2530 | 0 |  | 38495 | 38495 | 0 |  | 100% |  |  | 0 | NEED MATERIAL
SCREENWALL
10.01 | 2023-11-27 | 60 |  | COMPLETE IN MILLING | 1365 | 1365 | 0 |  | 100% | 2024-01-05 | SITE
10.02 | 2023-12-05 | 104 |  | COMPLETE IN MILLING | 3733 | 3733 | 0 |  | 100% | 2024-01-19 | SITE
10.03 | 2024-01-02 | 113 |  | COMPLETE IN MILLING | 2600 | 2600 | 0 |  | 100% | 2024-04-26 | PICKING AWAY NOT A PRIORITY SAYS JT/SITE
10.04 | 2024-01-02 | 74 |  | COMPLETE IN MILLING | 691 | 691 | 0 |  | 100% | 2024-04-26 | OFF HOLD 3/27/24/SITE
10.08 | 2024-01-02 | 10 |  | COMPLETE IN MILLING | 29 | 29 | 0 |  | 100% | 2024-04-26 | PICKING AWAY NOT A PRIORITY SAYS JT/SITE
REL-1WT-10.01_CRN_ACM | 2024-01-04 |  |  | COMPLETE IN MILLING | 45 | 45 | 0 |  | 100% | 2024-01-19 | SITE
REL-1WT-10.02_CRN_ACM | 2024-01-15 |  |  | COMPLETE IN MILLING | 149 | 149 | 0 |  | 100% | 2024-02-09 | SITE
REL-1WT-10.03_CRN_ACM | 2024-01-19 |  |  | COMPLETE IN MILLING | 235 | 235 | 0 |  | 100% | 2024-04-26 | PICKING AWAY NOT A PRIORITY SAYS JT/SITE
REL-1WT-10.04_CRN_ACM | 2024-01-19 | 10 |  | COMPLETE IN MILLING | 45 | 45 | 0 |  | 100% | 2024-04-26 | OFF HOLD 3/27/24/SITE
REL-1WT-10.XX | 2024-01-23 |  |  | COMPLETE IN MILLING | 6004 | 6004 | 0 |  | 100% | 2024-03-01 | SITE
10 |  | 371 | 0 |  | 14896 | 14896 | 0 |  | 100%
STOREFRONT
REL-1WT-11 | 2023-11-08 | 214 |  | COMPLETE IN MILLING | 9141 | 9141 | 0 |  | 100% | 2024-08-02 | WORKING WITH QISI ON SCHEDULE STAYINBG AHEAD OF SITE/SITE
REL-1WT-10.01_EGRESS DOOR | 2024-01-19 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-03-29
REL-1WT-EWA-13 | 2024-01-23 |  |  | COMPLETE IN MILLING | 35 | 35 | 0 |  | 100% | 2024-03-29 | SITE/SOME PARTS NEED TO GO TO ANACOLOR
REL-1WT-EWA-13 SITE | 2024-01-23 |  |  | COMPLETE IN MILLING | 39 | 39 | 0 |  | 100% | 2024-03-29 | SITE
REL-1WT-BACK SILL TRIM TEMP | 2024-02-20 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-03-22 | SITE
REL-1WT-13 ESA04&06 | 2024-02-20 | 37 |  | BEING ASM'D IN 393 | 841 | 841 | 0 |  | 100% |  | SITE/WAITING ON PARTS TO COME BACK FROM SPECTRUM
REL-11.00 DOOR | 2024-02-20 |  |  | COMPLETE IN MILLING | 421 | 421 | 0 |  | 100% | 3/1/24-3/15/24 | FLASHING RELEASED ON 2/20/24- SST PARTS RELEASED ON 2/27/24 STEEL PARTS RELEASED ON 3/6/24 1X3 [2] TUBE NOT ORDERED YET-ARRIVED 3/12/24
REL-1WT-20.04 Request | 2024-02-27 |  |  | COMPLETE IN MILLING | 25 | 25 | 0 |  | 100% | 2024-03-15 | SITE
REL-1WT-14 EWA15&15A | 2024-03-05 | 45 |  | COMPLETE IN MILLING | 213 | 213 | 0 |  | 100% | 2024-10-11 | SITE/WAITING ON PARTS TO COME BACK FROM SPECTRUM
REL-1WT-FF007.1 | 2024-03-06 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2024-03-22 | SITE
REL-1WT-FASCIA | 3/11/24 ON HOLD 5/28/24 OFF HOLD | 64 |  | COMPLETE IN MILLING | 193 | 193 | 0 |  | 100% | 2024-09-06 | SITE/POST PAINT PARTS [64] TO SPECTRUM 6/7/24
REL-1WT-Fascia Template | 3/11/24 ON HOLD 5/28/24 OFF HOLD | 64 |  | COMPLETE IN MILLING | 460 | 460 | 0 |  | 100% | 2024-09-06 | SITE
REL-1WT-11.00 HEAD PLATE West | 2024-03-13 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-04-05 | STILL WAITING ON A FEW PARTS FROM WATERJET/SITE
ALU.T-GA-1001-10 - [STEEL] TO 401 | 2024-03-18 |  |  | COMPLETE IN MILLING | 105 | 105 | 0 |  | 100% | 2024-04-05 | SITE
EGA03-11 REMAKE | 2024-03-26 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-03-29
REL-1WT-11.00 HEAD PLATE N&E - STL [WJ] TO STEEL | 2024-03-26 |  |  | COMPLETE IN MILLING | 58 | 58 | 0 |  | 100% | 2024-04-05 | SITE
10WT - WoodMock - [401] TO [707] | 2024-03-27 | WOOD MU |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-04-05 | SITE
REL-1WT-FF007.2 | 2024-03-29 | ANCHORS |  | COMPLETE IN MILLING | 80 | 80 | 0 |  | 100% | 2024-04-01 | SITE
REL-1WT-SOFFIT_SOUTH | 2024-03-29 | 61 |  | COMPLETE IN MILLING | 628 | 628 | 0 |  | 100% | 2024-11-29 | SITE
REL-1WT-SOFFIT_NORTH | 2024-03-29 | 48 |  | COMPLETE IN MILLING | 1349 | 1349 | 0 |  | 100% | 2024-11-15 | SITE
1215 10WT FIX - ALU TO SITE | 2024-03-29 | ERECTION ANGLE |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-04-05 | SITE
REL-1WT-11.00 Door WEST | 2024-04-01 | DOOR |  | COMPLETE IN MILLING | 435 | 435 | 0 |  | 100% | 2024-04-19 | SITE
REL-1WT-SOFFIT_EAST | 2024-04-01 | 89 |  | COMPLETE IN MILLING | 927 | 927 | 0 |  | 100% | 2024-11-15 | SITE
REL-1WT-TIE-BACK REGLAZING | 2024-04-01 | REGLAZE |  | COMPLETE IN MILLING | 92 | 92 | 0 |  | 100% | 2024-05-17 | SITE/WAITING ON HARDWARE MATERIAL REC'D 6/4/24
REL-11.02 | 2024-04-01 |  |  | COMPLETE IN MILLING | 176 | 176 | 0 |  | 100% | 2024-04-19 | SITE
REL-1WT-EMBED(Extra) LVL17 | 2024-04-01 | EMBED |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2024-04-19 | SITE
REL-1WT-BACK SILL TRIM BULK 1 | 2024-04-01 | SILL TRIM |  | COMPLETE IN MILLING | 1141 | 1141 | 0 |  | 100% | 2024-05-31 | SITE
REL-11.03 | 2024-04-03 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-04-12 | SITE
REL-1WT-EGA-04 (BOH) EMBED | 2024-04-04 | EMBED |  | COMPLETE IN MILLING | 17 | 17 | 0 |  | 100% | 2024-05-17 | SITE
REL-1WT-EMBED(Extra) LVL18 | 2024-04-04 | EMBED |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-04-19 | SITE
REL-1WT-EWA-13 | 4/5/24 7/3/24 | ANCHORS BSH ASM |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 4/12/24 8/2/24 | SITE
REL-1WT-11.04 | 2024-04-08 | SITE FIX |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-04-12 | SITE
REL-1WT-11.00 Door NORTH | 2024-04-23 | DOOR |  | COMPLETE IN MILLING | 157 | 157 | 0 |  | 100% | 2024-05-10 | SITE
REL-1WT-FF010 | 2024-05-01 |  |  | COMPLETE IN MILLING | 127 | 127 | 0 |  | 100% | 2024-05-24 | SITE
REL-1WT-11.00 Door WEST ADD. - FLA [400SP] TO POST PAINT | 2024-05-03 | DOOR |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2024-05-17 | TO SPECTRUM
REL-1WT-11.05 - SST [STEEL] 2 PARTS TO 400A | 2024-05-03 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-05-03 | SITE
REL-1WT-SOUTH-MSC | 2024-05-08 |  |  | COMPLETE IN MILLING | 32 | 32 | 0 |  | 100% | 2024-05-10 | SITE
REL-1WT-SOFFIT_NORTH-WEST | 2024-05-13 | 88 |  | COMPLETE IN MILLING | 1043 | 1043 | 0 |  | 100% | 2024-11-22 | SITE
REL-1WT-SOFFIT_WEST | 2024-05-13 | 130 |  | COMPLETE IN MILLING | 1669 | 1669 | 0 |  | 100% | 2024-11-29 | SITE
REL-1WT-CURVED BENT TRIM 3 | 2024-05-13 | TRIMS |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100% | 2024-05-31 | TO SPECTRUM
REL-1WT-BACK SILL TRIM BULK 2 | 2024-05-20 | SILL TRIM |  | COMPLETE IN MILLING | 6900 | 6900 | 0 |  | 100% | 2024-08-23 | SITE/NEED MATERIAL 1326, 1427 FROM KM
REL-1WT-11.00 DOOR EAST + NW | 5/20/24 ON HOLD 5/28/24 OFF HOLD | DOOR |  | COMPLETE IN MILLING | 192 | 192 | 0 |  | 100% | 2024-06-21 | TO CARNEY 6/18/24
REL-1WT-11.06 | 5/20/24 5/21/24 | SHIMS REMAINING PARTS |  | COMPLETE IN MILLING | 236 | 236 | 0 |  | 100% | 2024-08-16 | SITE MISSING SHM MATERIAL
REL-1WT-FF012 | 2024-05-21 |  |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2024-05-24 | SITE
REL-1WT-BACK SILL TRIM BULK 3 | 5/28/24 7/1/24 | SILL TRIM ADDED 4PCS |  | COMPLETE IN MILLING | 107 | 107 | 0 |  | 100% | 7/1/24 11/22/24 | POST PAINTED PARTS TO SPECTRUM 6/7/24 BOM WAS WRONG/ADDED 4 MORE PCS NEEDING TO GO TO PAINT 7/5/24 POST PAINTED PARTS READY FOR MASTERCRAFT 7/8/24
REL-1WT-11.00 DOOR WEST-PIVOT ONLY | 2024-06-05 | DOOR |  | COMPLETE IN MILLING | 70 | 70 | 0 |  | 100% | 2024-08-02 | POST PAINTED PARTS TO CARNEY 6/28/24
REL-1WT-PAINTED TRIM ESA 04&06 | 2024-06-05 | TRIMS |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2024-06-28 | POST PAINTED PARTS READY FOR SPECTRUM 6/28/24
REL-1WT-SITE MATERIAL ESA 04&06 | 2024-06-05 |  |  | COMPLETE IN MILLING | 185 | 185 | 0 |  | 100% | 2024-07-05
REL-1WT-EWA-04 | 2024-06-05 | 6 |  | COMPLETE IN MILLING | 518 | 518 | 0 |  | 100% |  | POST PAINTED PARTS READY FOR SPECTRUM 6/28/24
REL-1WT-14 EWA15&15A SITE | 6/5/24 7/9/24 |  |  | COMPLETE IN MILLING | 125 | 125 | 0 |  | 100% | 2024-07-05 | POST PAINTED PARTS READY FOR SPECTRUM 6/28/24 ADDED 6 MORE PCS TO THIS RELEASE 7/9/24
CURVED BENT TRIM | 2024-06-10 |  |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-06-14 | POST PAINTED PARTS TO SPECTRUM 6/14/24
REL-1WT-COPING | 2023-10-06 |  |  | COMPLETE IN MILLING | 1666 | 1666 | 0 |  | 100% |  | NEEDS TO GO TO AACRON/SITE
REL-1WT-COPING ASSEMBLY | 2024-06-19 | 187 |  | COMPLETE IN MILLING | 187 | 187 | 0 |  | 100% | 2024-08-16 | REC'D MATERIAL FROM AACRON 6/27/24
REL-1WT-PIVOT | 2024-06-19 |  |  | COMPLETE IN MILLING | 72 | 72 | 0 |  | 100% | 2024-07-19
REL-1WT-EWA-04 SITE MATERIALS | 2024-06-19 |  |  | COMPLETE IN MILLING | 1315 | 1315 | 0 |  | 100% | 2024-07-26 | 13PCS POST PAINT TO SPECTRUM 7/5/24
REL-1WT-WEST-MSC | 2024-06-19 |  |  | COMPLETE IN MILLING | 28 | 28 | 0 |  | 100% | 2024-07-05 | SITE
REL-1WT-EGA-04 EMBED_02 | 2024-06-24 |  |  | COMPLETE IN MILLING | 17 | 17 | 0 |  | 100% | 2024-07-05 | SITE
REL-1WT-ACM TEMPS_BI-FOLD | 2024-07-01 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-07-05 | SITE
REL-1WT-SOFFIT SITE MATERIAL | 2024-07-01 |  |  | COMPLETE IN MILLING | 31 | 31 | 0 |  | 100% | 2024-09-06 | SITE
REL-1WT-11.07 | 2024-07-03 |  |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-07-12 | SITE
REL-1WT-PARAPET PAINTED PARTS | 2023-10-06 |  |  | COMPLETE IN MILLING | 195 | 195 | 0 |  | 100%
REL-1WT-EGA-04 (BOH) EMBED SHIMS | 2024-07-17 | SHM |  | COMPLETE IN MILLING | 43 | 43 | 0 |  | 100% | 2024-07-26 | SITE
REL-1WT-SITE-SHIMS MSC(401) - TO SHIPPING | 2024-08-16 | SHM |  | COMPLETE IN MILLING | 1500 | 1500 | 0 |  | 100% | 2024-08-30 | SITE
REL-1WT-EWA15&15A_2 | 2024-08-20 |  |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2024-09-06 | SITE
REL-1WT-FF013 | 2024-08-20 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-09-13 | SITE
REL-1WT-11.09 | 2024-08-23 |  |  | COMPLETE IN MILLING | 206 | 206 | 0 |  | 100% | 2024-09-13 | SITE
REL-1WT-EMBED(EXTRA 2) LVL17 | 2024-09-08 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-09-13 | SITE
REL-1WT-REGLAZING | 2024-09-08 |  |  | COMPLETE IN MILLING | 250 | 250 | 0 |  | 100% | 2024-09-20 | SITE
Misc. Parts | 9/13/24 10/25/24 |  |  | COMPLETE IN MILLING | 123 | 123 | 0 |  | 100% | 2024-09-20 | SITE
REL-1WT-11.00 HEAD PLATE NW | 2024-09-25 |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2024-10-02 | SITE
REL-1WT-11.10 | 2024-10-03 |  |  | COMPLETE IN MILLING | 86 | 86 | 0 |  | 100% | 2024-10-11 | SITE
REL-1WT-EXTRA CLADDING ESA04&06 | 2024-10-16 |  |  | COMPLETE IN MILLING | 19 | 19 | 0 |  | 100% | 2024-11-22 | POST PAINT TO SPECTRUM
REL-1WT-THRESHOLD-EGA-03 | 2024-10-28 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2024-11-15 | SITE
REL-1WT-11.12 | 2024-11-07 |  |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2024-11-29 | SITE
REL-1WT-10.04 EXTRA FINS | 2024-11-18 |  |  | COMPLETE IN MILLING | 68 | 68 | 0 |  | 100% | 2024-12-06 | SITE
REL-1WT-11.13 | 2024-11-27 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-12-06
REL-1WT-GLAZING-FIN | 2024-12-13 | 10 |  | COMPLETE IN MILLING | 85 | 85 | 0 |  | 100% | 2024-01-17 | SITE
REL-1WT-LVL 17 ANGLES | 2024-12-18 |  |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100% | 2024-12-27 | SITE
10WT DOOR SPACERS | 2025-01-03 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100%
REL-1WT-11.14 | 2025-01-17 |  |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2025-01-20 | SITE
REL-1WT-REGLAZING 2 | 2025-01-21 |  |  | COMPLETE IN MILLING | 200 | 200 | 0 |  | 100% | 2025-01-27 | SITE
REL-1WT-11.15 | 2025-01-28 |  |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2025-02-07 | SITE
REL-1WT-14 EWA15&15A SITE | 2025-01-31 |  |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2025-02-07 | SITE
Misc. Parts | 2025-01-31 |  |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2025-02-07 | SITE
REL-1WT-BACK SILL TRIM BULK 4 | 2025-02-12 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2025-03-14 | REC'D 3/10/25 1326 [10] FROM KM
Misc. Parts | 2025-02-12 |  |  | COMPLETE IN MILLING | 44 | 44 | 0 |  | 100% | 2025-02-28 | SITE
REL-1WT-THRESHOLD_EGA-03 (2) | 2025-02-14 |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2025-04-04 | WAITING ON THRESHOLD MATERIAL
REL-1WT-SOFFIT SITE MATERIAL | 2025-02-26 |  |  | COMPLETE IN MILLING | 305 | 305 | 0 |  | 100% | 2025-03-07 | SITE
REL-1WT-EWA-04 EXTRA ANGLES | 2025-03-03 |  |  | COMPLETE IN MILLING | 26 | 26 | 0 |  | 100% | 2025-03-07 | SITE
REL-1WT-SOFFIT SITE MATERIAL BULK RELEASE 2 | 2025-03-11 |  |  | COMPLETE IN MILLING | 200 | 200 | 0 |  | 100% | 2025-03-14 | SITE
Misc. Parts | 2025-03-13 |  |  | COMPLETE IN MILLING | 913 | 913 | 0 |  | 100% | 2025-03-21 | SITE
REL-1WT-11.16 | 2025-03-27 |  |  | COMPLETE IN MILLING | 46 | 46 | 0 |  | 100% | 2025-03-31 | SITE
10WT-SOFFIT MISC | 2025-03-31 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-04-11 | SITE
REL-1WT-EWA-04 ADD FLASHING | 2025-04-10 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-04-18 | SITE
MISC PARTS 2 | 4/15/25 4/17/25 |  |  | IN PROGRESS | 235 | 237 | 2 | DEAN | 99.16% | 2025-04-25 | WAITING ON WELD INFO ADDED PARTS 4/17/25 [15] SITE
95 |  | 1033 | 0 |  | 36160 | 36162 | 2 |  | 99.99% | SITE PARTS
145 |  | 3934 | 0 | TOTAL COMPLETE | 89551 | 89553 | 2 |  | 100% | TOTAL PARTS
LEGEND
NEED MATERIAL
NEED INFORMATION
NEED INFO/MATERIAL
COMPLETE

## PRI ES
PRINCETON LEFT TO FABRICATE
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
1.01 | 2023-04-25 | 114 |  | COMPLETE IN MILLING | 16648 | 16648 | 0 |  | 99% | 2023-11-07
BULK 1 EMBEDS | 2023-03-30 | N/A |  | COMPLETE IN MILLING | 5275 | 5275 | 0 |  | 100% |  | SITE
EMB LVL 2 | 2023-02-13 | N/A |  | COMPLETE IN MILLING | 588 | 588 | 0 |  | 100% |  | SITE
BULK 2 | 2023-03-02 | PAINTED CAPS |  | COMPLETE IN MILLING | 4317 | 4317 | 0 |  | 100% |  | SHIPPED TO SPECTRUM
BULK 1 | 2023-02-16 | TYPICAL SMALL PARTS |  | COMPLETE IN MILLING | 12774 | 12774 | 0 |  | 100%
BULK 3 | 2023-03-23 | SHIMS/ALU PARTS |  | COMPLETE IN MILLING | 32360 | 32360 | 0 |  | 100%
1.02 | 2023-05-08 | 104 |  | COMPLETE IN MILLING | 7885 | 7885 | 0 |  | 100% | 2023-11-07 | 2023-11-08
ANC-1008/ANC-1008 | 2023-05-07 | ANC PARTS |  | COMPLETE IN MILLING | 40 | 40 | 0 |  | 100% |  | SITE
BRICK VMU | 2023-05-24 | VMU |  | COMPLETE IN MILLING | 193 | 193 | 0 |  | 100%
BRICK VMU ALU | 2023-06-07 | ALU PART |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100%
1.03A | 2023-05-24 | 16 |  | COMPLETE IN MILLING | 1916 | 1916 | 0 |  | 100%
REL-PRI-STS | 2023-05-30 | STARTER SILL&FLASHING |  | COMPLETE IN MILLING | 1745 | 1745 | 0 |  | 100% |  | SITE
ANC-1003 | 2023-05-31 | ANCHORS |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% |  | SITE
STARTER SILL CRIMP TEST | 2023-06-02 | TEST |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100%
3.01A | 2023-06-12 | 59 |  | COMPLETE IN MILLING | 28020 | 28020 | 0 |  | 100%
REL-PRI-STS2 | 2023-06-20 | STARTER SILL&FLASHING |  | COMPLETE IN MILLING | 399 | 399 | 0 |  | 100% |  | SITE
REL-PRI-1.02 - Revision | 2023-07-03 | REVISED PARTS |  | COMPLETE IN MILLING | 27 | 27 | 0 |  | 100%
REL-PRI-WELD - Priority #1 | 2023-07-11 | ANCHORS |  | COMPLETE IN MILLING | 137 | 137 | 0 |  | 100% |  | SITE
1.04 | 2023-07-12 | 28 |  | COMPLETE IN MILLING | 2776 | 2776 | 0 |  | 100%
2.01A | 2023-07-18 | 39 |  | COMPLETE IN MILLING | 2266 | 2266 | 0 |  | 100% | 2023-09-20 | MISSING 1402 SITE INSTALLED [216] FROM KM
REL-PRI-WELD2 | 2023-07-18 | ANCHORS |  | COMPLETE IN MILLING | 804 | 804 | 0 |  | 100% |  | SITE
ANC-1001 | 2023-07-19 | ANCHORS |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% |  | SITE HOT RUSH
REL-PRI-3.02A | 2023-07-21 | 75 |  | COMPLETE IN MILLING | 30015 | 30015 | 0 |  | 100% | 9/15 MINUS THE BT'S 10/6
REL-PRI-3.01B | 2023-07-21 | 7 |  | COMPLETE IN MILLING | 4173 | 4173 | 0 |  | 100% | 2023-09-15 | ADDED RELEASES 8/15
REL-PRI-STS2 | 2023-07-21 | REVISED PARTS |  | COMPLETE IN MILLING | 15 | 15 | 0 |  | 100% |  | SITE
DLT 01 | 2023-07-21 | ERECTION ANGLES |  | COMPLETE IN MILLING | 480 | 480 | 0 |  | 100% |  | SITE
REL-PRI-Additional Site Embeds | 2023-07-28 | EMBEDS |  | COMPLETE IN MILLING | 40 | 40 | 0 |  | 100% |  | SITE
REL-PRI-STS3AB | 2023-08-14 | STARTER SILL&FLASHING |  | COMPLETE IN MILLING | 492 | 492 | 0 |  | 100% | 2023-09-15 | SITE
WT05 VMU | 2023-08-15 | 1 |  | COMPLETE IN MILLING | 33 | 33 | 0 |  | 100% | 2023-09-15
REL-PRI-2.02A | 2023-08-21 | 18 |  | COMPLETE IN MILLING | 1904 | 1904 | 0 |  | 100% | 2023-09-21
SS4 | 2023-08-24 | BRACKETS |  | COMPLETE IN MILLING | 21 | 21 | 0 |  | 100% |  | SITE
REL-PRI-1.05A | 2023-08-25 | 27 |  | COMPLETE IN MILLING | 2328 | 2328 | 0 |  | 100% | 2023-09-29 | REVISED PARTS [30]
REL-PRI-DLT2 | 2023-08-25 | ANCHORS |  | COMPLETE IN MILLING | 471 | 471 | 0 |  | 100% | 2023-09-15 | SITE
REL-PRI-3.02B | 2023-08-30 | 44 |  | COMPLETE IN MILLING | 13574 | 13574 | 0 |  | 100%
REL-PRI-ANC-4X | 2023-09-01 | 5 |  | COMPLETE IN MILLING | 15 | 15 | 0 |  | 100%
REL-PRI-STS | 2023-09-05 | STARTER SILL&FLASHING |  | COMPLETE IN MILLING | 101 | 101 | 0 |  | 100% |  | SITE
REL-PRI-3.03A | 2023-09-08 | 80 |  | COMPLETE IN MILLING | 35362 | 35362 | 0 |  | 100% | 2023-11-10 | 2023-12-07
REL-PRI-2.01B | 2023-09-08 | 69 |  | COMPLETE IN MILLING | 3303 | 3303 | 0 |  | 100% | 2023-11-10 | REVISED PARTS [17]/11/21
REL-PRI-Commons Batch 1 | 2023-09-13 | ANCHORS |  | COMPLETE IN MILLING | 213 | 213 | 0 |  | 100% |  | SITE
REL-PRI-LIFTING | 2023-09-13 | LIFTING BRACKET |  | COMPLETE IN MILLING | 66 | 66 | 0 |  | 100% |  | SITE
REL-PRI-1.05B | 2023-09-13 | 21 |  | COMPLETE IN MILLING | 3731 | 3731 | 0 |  | 100% | 2023-10-13
REL-PRI-1.05C | 2023-09-13 | 13 |  | COMPLETE IN MILLING | 2086 | 2086 | 0 |  | 100% | 2023-12-22 | MISSING ANGLES 1401-01 [1], 1405-01 [1]
REL-PRI-2.02B | 2023-09-27 | 33 |  | COMPLETE IN MILLING | 3992 | 3992 | 0 |  | 100% | 2023-12-01 | 2023-12-11
Release 1.05D | 2023-09-27 | 23 |  | COMPLETE IN MILLING | 5192 | 5192 | 0 |  | 100% | 2023-10-16 | REVISED PARTS [25]
REL-PRI-ANC1030 | 2023-10-03 | ANCHORS |  | COMPLETE IN MILLING | 36 | 36 | 0 |  | 100% | 2023-10-27 | SITE
ANC-NEU-S-1152-001-001 | 2023-10-03 | ANCHORS |  | COMPLETE IN MILLING | 150 | 150 | 0 |  | 100% | 2023-10-06 | SITE
REL-PRI-STS-PRIORITY-2-FLASHING | 2023-10-06 | FLASHING |  | COMPLETE IN MILLING | 189 | 189 | 0 |  | 100% | 10/12 & 10/27 | SITE
REL-PRI-STS3 | 2023-10-12 | STARTER SILL |  | COMPLETE IN MILLING | 608 | 608 | 0 |  | 100% | 2023-10-20 | SITE
ANC-NEU-S-1152-001-001 | 2023-10-13 | ANCHORS |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2023-10-20 | SHOP RUSH
J to J.3 North Starter Sill Field Fix | 2023-10-17 | STARTER SITE FIX |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2023-10-23 | SITE HOT RUSH
REL-PRI-STS - SHM | 1902-10-14 | SITE SHIMS |  | COMPLETE IN MILLING | 1000 | 1000 | 0 |  | 100% | 2023-10-23 | SITE HOT RUSH
PRI-WT05-PMU | 2023-10-24 | PMU |  | COMPLETE IN MILLING | 99 | 99 | 0 |  | 100% | 2023-10-03 | 2023-11-08
Field Additional Material ¦ 90 Degree Corner Splice Plate - ALU.P | 2023-10-24 | PLATES |  | COMPLETE IN MILLING | 80 | 80 | 0 |  | 100% | 2023-10-27 | SITE
REL-PRI-COMMONS2 | 2023-10-30 | ANCHORS |  | COMPLETE IN MILLING | 562 | 562 | 0 |  | 100% | 2023-11-17 | MISSING S-162354 [36], S-162355 [16]/SITE
REL-PRI-MT91 | 2023-10-30 | FLASHING |  | COMPLETE IN MILLING | 117 | 117 | 0 |  | 100% | 2023-11-10 | SITE
REL-PRI-CW21 | 2023-10-30 | FLASHING |  | COMPLETE IN MILLING | 36 | 36 | 0 |  | 100% | 2023-11-10 | SITE
REL-PRI-ANC Field Fix [2 Units] | 2023-11-01 | ANCHORS |  | COMPLETE IN MILLING | 27 | 27 | 0 |  | 100% | 2023-11-10 | SITE
STS - Priority 3 | 2023-11-07 | BENT SHAPES |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2023-11-10 | SITE
STS3AB STS Greenhouse Fin Update | 2023-11-08 | STARTER SILL FIX |  | COMPLETE IN MILLING | 46 | 46 | 0 |  | 100% | 2023-11-10 | 393 HOT RUSH
REL-PRI-1.03B | 2023-11-08 | 16 |  | COMPLETE IN MILLING | 2231 | 2231 | 0 |  | 100% | 2023-12-15 | 2024-01-08
REL-PRI-3.03B | 2023-11-08 | 22 |  | COMPLETE IN MILLING | 10434 | 10434 | 0 |  | 100% | 2023-12-15 | 2024-01-03
REL-PRI-WT05-PMU | 2023-11-13 | 10 |  | COMPLETE IN MILLING | 751 | 751 | 0 |  | 100% | 2023-12-08 | WAITING FOR FPN TO COME BACK FROM PAINT MC
REL-PRI-PARAPET-FLASHING | 2023-11-14 | FLASHING |  | COMPLETE IN MILLING | 462 | 462 | 0 |  | 100% | 2024-03-15 | SITE/MATERIAL REC'D 1/26/MT9.2&3 ON HOLD
REL-PRI-SKIRT-GREENHOUSE | 2023-11-28 | SKIRT FPN |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2023-12-08 | SITE
REL-PRI-STS-ZONEB-DOOR | 2023-11-28 | DOOR |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2023-12-08
REL-PRI-ANC-5004 Anchor Test [2 Units] | 2023-11-28 | TEST ANCHOR |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2023-12-06
REL-PRI-Coping-BR-1 | 2023-12-07 | COPING |  | RE-RELEASED BELOW | 323 | 323 | 0 |  | 100% | 12/14-12/22-12/29 | SITE/MATERIAL REC'D 1/26
REL-PRI-Coping-MT9-1 | 2023-12-07 | COPING |  | RE-RELEASED BELOW | 543 | 543 | 0 |  | 100% | 12/14-12/22 | SITE/MATERIAL REC'D 1/26
3.02A Fin Field Fix | 2023-12-11 | FIELD FIX |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2023-12-15 | SITE
REL-PRI-2.02B - Z-Panel Depth Update | 2023-12-11 | REVISED PARTS |  | COMPLETE IN MILLING | 101 | 101 | 0 |  | 100% | 2023-12-20
ANC-2060 | 2023-12-11 | REVISED PARTS |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2023-12-11 | SITE HOT RUSH
REL-PRI-MT9-1-LV4 | 2023-12-12 | SKIRT FPN |  | COMPLETE IN MILLING | 335 | 335 | 0 |  | 100% | 2024-03-01 | SITE/MATERIAL REC'D 1/26
REL-PRI-MT9-1-LV5 | 2023-12-12 | SKIRT FPN |  | COMPLETE IN MILLING | 182 | 182 | 0 |  | 100% | 2024-03-01 | SITE/MATERIAL REC'D 1/26
REL-PRI-MT9-2 Lv5 | 2023-12-18 | SKIRT FPN |  | COMPLETE IN MILLING | 705 | 705 | 0 |  | 100% | 2024-03-22 | SITE/MATERIAL REC'D 1/26/OFF HOLD 3/5/24
REL-PRI-MT9-3 Lv5 | 2023-12-18 | SKIRT FPN |  | COMPLETE IN MILLING | 618 | 618 | 0 |  | 100% | 2024-03-22 | SITE/MATERIAL REC'D 1/26/OFF HOLD 3/5/24
REL-PRI-ANC-2021 Field Fix | 2023-12-18 | ANCHORS |  | COMPLETE IN MILLING | 28 | 28 | 0 |  | 100% | 2023-12-22 | SITE HOT RUSH
WT05 PMU - Field Items | 2024-01-02 | FIELD ITEMS |  | COMPLETE IN MILLING | 756 | 756 | 0 |  | 100% | 2024-01-12 | SITE HOT RUSH
REL-PRI-STS-MISSING | 2024-01-02 | PARTS FOR THE SHOP |  | COMPLETE IN MILLING | 82 | 82 | 0 |  | 100% | 2024-01-12
REL-PRI-ES-CLOSEOUT-ANC | 2024-01-18 | ANCHORS |  | COMPLETE IN MILLING | 526 | 526 | 0 |  | 100% | 2024-01-26 | SITE HOT RUSH
Misc. Field Items | 2024-01-22 | ANCHORS |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-01-26 | SITE
REL-PRI-WT05 STL-PRI-GA-2000-01 | 2024-01-26 | ANCHORS |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-01-29 | SITE
REL-PRI-WT05-PMU- MISSING ALU | 2024-01-29 | MISSING PARTS |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-01-30 | SITE
1.02 BPN/Fin Revision | 2024-01-30 | REVISED PARTS |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2024-01-31
1.05C - BPN REV (400SP) [To 350] *Use Coil Coat* | 2024-01-30 | REVISED PARTS |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2024-01-31
Vestibule Canopy Frames | 2024-01-30 | STEEL CANOPY |  | COMPLETE IN MILLING | 29 | 29 | 0 |  | 100% | 2024-02-09 | TO GALV/SITE/2/13/24
REL-PRI-ES-MISSING-ANC | 2024-01-31 | ANCHORS |  | COMPLETE IN MILLING | 26 | 26 | 0 |  | 100% | 2024-02-06 | SITE
Release 3.03B_Damaged Unit | 2024-02-05 | REPLACEMENT UNIT |  | COMPLETE IN MILLING | 114 | 114 | 0 |  | 100% | 2024-02-16 | SITE
REL-PRI-CW2-1-LV1-SKIRT-MISC | 2024-02-12 | SKIRT |  | COMPLETE IN MILLING | 32 | 32 | 0 |  | 100% | 2024-03-01 | SITE
REL-PRI-CW2-1-LV2-SKIRT-MISC | 2024-02-12 | SKIRT |  | COMPLETE IN MILLING | 174 | 174 | 0 |  | 100% | 2024-03-15 | SITE
REL-PRI-CW2-2-LV1-SKIRT-MISC | 2024-02-12 | SKIRT |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2024-03-01 | SITE
REL-PRI-CW2-2-LV2-SKIRT-MISC | 2024-02-12 | SKIRT |  | COMPLETE IN MILLING | 68 | 68 | 0 |  | 100% | 2024-03-15 | SITE
REL-PRI-MT9-1-LV2-SKIRT-MISC | 2024-02-12 | SKIRT |  | COMPLETE IN MILLING | 298 | 298 | 0 |  | 100% | 2024-03-15 | SITE
REL-PRI-MT9-2-LV2-SKIRT-MISC | 2024-02-12 | SKIRT |  | COMPLETE IN MILLING | 232 | 232 | 0 |  | 100% | 2024-03-22 | SITE
REL-PRI-MT9-3-LV2-SKIRT-MISC | 2024-02-12 | SKIRT |  | COMPLETE IN MILLING | 288 | 288 | 0 |  | 100% | 2024-03-22 | SITE
REL-PRI-FIELD-FIX-ANC-1001-FF-1017 | 2024-02-14 | ANCHORS |  | COMPLETE IN MILLING | 61 | 61 | 0 |  | 100% | 2024-02-23 | SITE
REL-PRI-FIELD-FIX-ANC-1001-FF-1018 | 2024-02-14 | ANCHORS |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-02-23 | SITE
REL-PRI-ES-ADDL-END-DAM-PLATE | 2024-02-22 | PLATES |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2024-02-23 | SITE
REL-PRI-FIELD-FIX-1016 | 2024-03-08 | SITE FIX |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2024-03-13 | SITE
Field Fix 01 | 2024-03-14 | SITE FIX |  | COMPLETE IN MILLING | 186 | 186 | 0 |  | 100% | 2024-03-29 | SITE
REL-PRI-MT9 REMAKES | 2024-04-01 | REMAKES |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-04-26 | SITE
REL-PRI-4.01 [28 Units] | 2024-04-09 | 28 |  | WAITING ON MATERIAL WAITING ON POST PAINT COMPLETE IN MILLING | 6385 | 6385 | 0 |  | 100% | 2024-05-20 | POST PAINT TO SPECTRUM 5/7- COMPLETE MISSING 5/16 SS SHEET [REC'ING PARTIAL WEEK OF 5/17] MISSING S-1408 [28] FROM KM
REL-PRI-5.01 [10 Units] | 2024-04-11 | 10 |  | COMPLETE IN MILLING | 465 | 465 | 0 |  | 100% | 2024-04-26 | POST PAINT TO SPECTRUM 5/7- COMPLETE
REL-PRI-MT9-1-LV4-SKIRT-FPN-REV1 | 2024-04-16 | REVISED PANS |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-05-03 | SITE
REL-PRI-4.01B | 4/18/24 PAINTED PARTS 4/29/24 FRM PARTS ONLY 5/21/24 REMAINING PARTS | 16 |  | COMPLETE IN MILLING | 3925 | 3925 | 0 |  | 100% | 4/26/24 PP 5/10/24 PP 5/10/24 FRM 5/31/24 COMPLETE | 1ST POST PAINT PARTS TO SPECTRUM 5/7- COMPLETE 2ND REVISED POST PAINT PARTS TO SPECTRUM 5/10 MISSING 358 [1] FROM KM/4x4x1/2 [11] FOR 1544
REL-PRI-221B | 2024-04-19 | BSH PART FOR SITE |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-04-26 | SITE
REL-PRI-MT9-1-LV2-SKIRT-MISC FPN(400SP) - TO 401 | 2024-05-09 | REMAKES |  | COMPLETE IN MILLING | 21 | 21 | 0 |  | 100% | 2024-05-17 | SITE
REL-PRI-Coping-BR-1 | 2024-05-13 | 38 |  | COMPLETE IN MILLING | 383 | 383 | 0 |  | 100% | 2024-06-21 | SITE
REL-PRI-Coping-MT9-1 | 2024-05-13 | 63 |  | COMPLETE IN MILLING | 584 | 584 | 0 |  | 100% | 2024-06-21 | SITE
REL-PRI-STS-COMMONS | 2024-05-13 | STARTER SILL |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2024-05-31 | SITE
REL-PRI-West Loading Dock Skirts | 2024-05-14 | SKIRT |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2024-05-16 | SITE
REL-PRI-West Commons Plaza Skirts | 2024-05-14 | SKIRT |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-05-16 | SITE/NEED 1.25X1.25X 1/8 TUBE MATERIAL
REL-PRI-PENETRATION SLEEVE | 2024-05-20 | SLEEVE |  | COMPLETE IN MILLING | 252 | 252 | 0 |  | 100% | 2024-05-31 | SITE
REL-PRI-MT9-2 LV2 Skirt FPN | 2024-05-20 | SKIRTS |  | COMPLETE IN MILLING | 21 | 21 | 0 |  | 100% | 2024-06-07 | SITE
REL-PRI-CW2-1 LV1 Skirt FPN | 2024-05-20 | SKIRTS |  | COMPLETE IN MILLING | 58 | 58 | 0 |  | 100% | 2024-06-07 | SITE
REL-PRI-CW2-1 LV2 Skirt FPN | 2024-05-20 | SKIRTS |  | COMPLETE IN MILLING | 19 | 19 | 0 |  | 100% | 2024-06-07 | SITE
REL-PRI-SKIRT FPN SUPPORT ANGLES | 2024-05-20 | ANGLES |  | COMPLETE IN MILLING | 130 | 130 | 0 |  | 100% | 2024-05-31 | SITE
REL-PRI-5.01_REV01 | 2024-05-20 | REVISED PARTS |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-05-24
REL-PRI-CW2-2 Lv2 Skirt | 2024-05-28 | SKIRTS |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-06-14 | SITE
REL-PRI-ES FLASHING COMMONS | 2024-05-28 | FLASHING |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-06-04 | SITE
REL-PRI-CW2-2 Lv1 Skirt FPN | 2024-05-28 | SKIRTS |  | COMPLETE IN MILLING | 64 | 64 | 0 |  | 100% | 2024-06-14 | SITE
REL-PRI-MT9-3 LV2 SKIRT FPN | 2024-05-29 | 14 |  | COMPLETE IN MILLING | 180 | 180 | 0 |  | 100% | 2024-06-28 | SITE
REL-PRI-COPING-BR-2 | 2024-05-29 | 40 |  | COMPLETE IN MILLING | 519 | 519 | 0 |  | 100% | 2024-08-30 | 8/2/24 FOR SUB PARTS ONLY OLD BATCH COIL
REL-PRI-COPING-BR-3 | 2024-05-29 | 40 |  | COMPLETE IN MILLING | 504 | 504 | 0 |  | 100% | 2024-08-30 | 8/2/24 FOR SUB PARTS ONLY OLD BATCH COIL
REL-PRI-ES-CW1 COPING TEST | 2024-05-30 | TEST |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2024-06-07 | SITE
REL-PRI-CW2B_5.01_FLASHING | 2024-05-31 | FLASHING |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-05-31 | SITE
5.01 Steel Bracket Remakes | 2024-06-04 | REMAKES |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2024-06-07 | SITE
REL-PRI-Privacy Screen | 2024-06-10 | SCREENS |  | COMPLETE IN MILLING | 136 | 136 | 0 |  | 100% | 2024-07-31 | 136PCS TO SPECTRUM 7/31/24
ES Soffit Remake | 2024-06-10 | REMAKES |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-06-14 | SITE
REL-PRI-ES CANOPY FINISH | 2024-06-10 | 13 |  | COMPLETE IN MILLING | 116 | 116 | 0 |  | 100% | 2024-07-26 | 13 POST PAINTED PARTS READY FOR SPECTRUM 7/19/24
5.01 Site Shims | 2024-06-10 | SHIMS |  | COMPLETE IN MILLING | 300 | 300 | 0 |  | 100% | 2024-06-14 | SITE
REL-PRI-CW-3 Antiwalk Plates | 2024-06-12 | PLATES |  | COMPLETE IN MILLING | 60 | 60 | 0 |  | 100% | 2024-06-13 | SITE
ES Hoist Close Out | 2024-06-17 | CLOSE OUT |  | COMPLETE IN MILLING | 582 | 582 | 0 |  | 100% | 2024-07-05 | MISSING 477 [2] FROM KM
REL-PRI-MT9-2 Lv2 Skirt Flashing | 2024-06-20 | SKIRTS |  | COMPLETE IN MILLING | 26 | 26 | 0 |  | 100% | 2024-06-28
5.01 Steel Brackets | 2024-07-01 |  |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2024-07-01 | SITE
ALU-PRI-1201-1001-03 - ALU (400) [To Field] | 2024-07-02 |  |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-07-12 | SITE
REL-PRI-Coping-MSC-MT9-2 | 2024-07-08 | COPING SUM PARTS |  | COMPLETE IN MILLING | 376 | 376 | 0 |  | 100% | 2024-08-09
REL-PRI-Coping-MSC-MT9-3 | 2024-07-08 | COPING SUM PARTS |  | COMPLETE IN MILLING | 195 | 195 | 0 |  | 100% | 2024-08-09
REL-PRI-Coping-MSC-CW2-1 | 2024-07-08 | COPING SUM PARTS |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2024-08-02
REL-PRI-Coping-MSC-CW2-2 | 2024-07-08 | COPING SUM PARTS |  | COMPLETE IN MILLING | 99 | 99 | 0 |  | 100% | 2024-08-02
REL-PRI-ES ZONEF FAN WELL COPING | 2024-07-12 | COPING |  | COMPLETE IN MILLING | 125 | 125 | 0 |  | 100% | 2024-07-19 | SITE
REL-PRI-U-CHANNEL_TEST | 2024-07-16 | TEST |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-08-02 | SITE
REL-PRI-Coping-CW2-1 | 2024-07-23 | 19 |  | COMPLETE IN MILLING | 157 | 157 | 0 |  | 100% | 2024-08-16 | OLD BATCH COIL
REL-PRI-Coping-CW2-2 | 2024-07-23 | 25 |  | COMPLETE IN MILLING | 242 | 242 | 0 |  | 100% | 2024-09-27 | OLD BATCH COIL [12PCS ON HOLD DUE TO OVERSIZED]
REL-PRI-Coping-MT9-2 | 2024-07-23 | 72 |  | COMPLETE IN MILLING | 668 | 668 | 0 |  | 100% | 2024-11-22 | 137 POST PAINTED PARTS FOR SPECTRUM 10/9/24
REL-PRI-Coping-MT9-3 | 2024-07-23 | 67 |  | COMPLETE IN MILLING | 564 | 564 | 0 |  | 100% | 2024-11-22 | 118 POST PAINTED PARTS FOR SPECTRUM 10/9/24
REL-PRI-Commons_Field FPN | 2024-07-24 | 22 |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2024-08-16 | OLD BATCH COIL
REL-PRI-Commons Parapet Flashing | 2024-07-26 | 67 |  | COMPLETE IN MILLING | 67 | 67 | 0 |  | 100% | 2024-08-16
REL-PRI-Commons Coping MSC | 2024-07-26 |  |  | COMPLETE IN MILLING | 92 | 92 | 0 |  | 100% | 2024-08-16
REL-PRI-Commons Coping | 2024-07-26 | 21 |  | COMPLETE IN MILLING | 239 | 239 | 0 |  | 100% | 2024-09-06 | OLD BATCH COIL
REL-PRI-ES A-Wing Sill Field Items | 2024-08-06 | SILL SUB PARTS |  | COMPLETE IN MILLING | 430 | 430 | 0 |  | 100% | 2024-08-16 | SITE
REL-PRI-ES B-Wing Sill Field Items | 2024-08-07 | SILL SUB PARTS |  | COMPLETE IN MILLING | 742 | 742 | 0 |  | 100% | 2024-10-11
REL-PRI-ES C-Wing Sill Field Items | 2024-08-07 | SILL SUB PARTS |  | COMPLETE IN MILLING | 679 | 679 | 0 |  | 100% | 2024-10-18
REL-PRI-ES Additional J-trim | 2024-08-13 | J-TRIMS |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-08-16 | SITE
REL-PRI-ES A-Wing Sill Front Pans | 2024-08-27 | 60 |  | COMPLETE IN MILLING | 181 | 181 | 0 |  | 100% | 2024-10-11 | SENT SPECTRUM 9/25/24
REL-PRI-ES B-Wing Sill Front Pans | 2024-08-27 | 100 |  | COMPLETE IN MILLING | 301 | 301 | 0 |  | 100% | 2024-11-22 | TO SPECTRUM 10/14/24
REL-PRI-ES C-Wing Sill Front Pans | 2024-08-27 | 93 |  | COMPLETE IN MILLING | 280 | 280 | 0 |  | 100% | 2024-11-22 | TO SPECTRUM 10/14/24
REL-PRI-ES Inside Corner Skirt Redo | 2024-09-06 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-09-06 | SITE
REL-PRI-CW1 & CW2 ES Interior Sill Trim Splice Plate Bulk Release | 2024-09-08 |  |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-10-11 | READY FOR SPECTRUM 10/14/24
STL-T-PRI-GA-1013-03 | 2024-09-08 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-09-13 | SITE
REL-PRI-ES Additional J-trim_Remaining Doors | 2024-09-08 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2024-09-27 | SITE
REL-PRI-ES EMR WALL COPING | 2024-09-10 |  |  | COMPLETE IN MILLING | 29 | 29 | 0 |  | 100% | 2024-10-04 | TO SPECTRUM 10/9/24
Missing Skirt Pans 2 | 2024-09-10 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-09-27 | SITE
REL-PRI-Commons Louver Sill Pan | 2024-09-13 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-09-16 | SITE
REL-PRI-CW-2 OSC SKIRT | 2024-09-16 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-10-11 | SITE
REL-PRI-ES East Canopy Additional Cladding | 2024-09-18 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-10-11 | COIL
REL-PRI-ES West Canopy Additional Cladding | 2024-09-18 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-10-11 | COIL
REL-PRI-Commons Coping Sample | 2024-09-18 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-10-08 | SITE
REL-PRI-Commons_Field FPN -Missing | 2024-09-30 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-10-04 | SITE
REL-PRI-ES Louver Sill Pan | 2024-10-01 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-10-11 | SITE
REL-PRI-ES_BIOE PENET SLEEVE ADDITIONAL | 2024-10-01 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-10-04 | SITE
REL-PRI-ES_SEAS - ELEC_PENET COVER PLATES | 2024-10-03 |  |  | COMPLETE IN MILLING | 67 | 67 | 0 |  | 100% | 2024-10-04 | SITE
FPN-PRI-1101-04 | 2024-10-09 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-10-11 | SITE
FPN-PRI-6111-011 | 2024-10-09 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-10-11 | SITE
REL-PRI-Missing Finish At Duct Penetration | 2024-10-15 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-10-25 | SITE
REL-PRI-ES Lv1 Closure Pan | 2024-10-15 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-10-25 | SITE
REL-PRI-Coping-CW2-2 - Missing | 2024-11-07 |  |  | COMPLETE IN MILLING | 91 | 91 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-3.02A Fin Field Fix | 2024-11-18 |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-ES North Mullion Extension | 2024-11-27 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-12-06 | SITE
REL-PRI-ADDITIONAL_PRIVACYSCREEN_FRAMING_RELEASE | 2024-12-10 |  |  | COMPLETE IN MILLING | 592 | 592 | 0 |  | 100% | 2025-02-07 | MISSING 1402 [296] FROM KM CAME IN 1/27/25
REL-PRI-ES-ADDITIONAL_2IN_PENET_SLEEVES | 2024-12-10 |  |  | COMPLETE IN MILLING | 45 | 45 | 0 |  | 100% | 2024-12-27 | SITE
REL-PRI-ES SHADOWBOX BPNS | 2024-12-10 |  |  | WAITING ON REVISION | 32 | 32 | 0 |  | 100% | 2024-12-27 | MISSING 470 [4] FROM KM
REL-PRI-ES Smoke Purge Covers | 2024-12-16 |  |  | COMPLETE IN MILLING | 140 | 140 | 0 |  | 100% | 2025-02-28 | [14] POST PAINTED MATERIAL AT SPECTRUM
PRI-REL-ES C-Wing Additional Splice Plates | 2024-12-16 |  |  | COMPLETE IN MILLING | 71 | 71 | 0 |  | 100% | 2024-12-27 | USING COIL
REL-PRI-Commons Trim Splice Plates | 2024-12-20 |  |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2025-01-10 | SITE
REL-PRI-ES_L2 Area C Gutter Flashing | 2025-01-23 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-01-23 | SITE
REL-PRI-ES Shadowbox Retro Install | 2025-01-29 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2025-02-07 | SITE
MT9-2 - Coping Remake | 2025-01-31 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-02-14 | SITE
REL-PRI-3.02A Fin Field Fix | 2025-02-07 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-12 | SITE
REL-PRI-ES East Canopy Additional Cladding | 2025-02-07 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-12 | SITE
BSH-PRI-4383-01 | 2025-02-07 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-02-12 | SITE
REL-PRI-ES East Canopy Back Cladding | 2025-02-10 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-02-21 | SITE
ES SIILL FPN REMAKES | 2025-02-17 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-02-21 | SITE
REL-PRI-ADDITIONAL_PRIVACYSCREEN_FRAMING_RELEASE | 2025-02-19 |  |  | COMPLETE IN MILLING | 40 | 40 | 0 |  | 100% | 2025-02-28 | SITE
REL-PRI-Coping-MT9-3 | 2025-02-19 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-28 | SITE
REL-PRI-Privacy Screen | 2025-02-19 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-02-28 | 10PCS READY FOR SPECTRUM 2/26/25
MISC SITE PARTS2 | 2025-03-17 | REMAKES |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2025-03-21 | SITE
REL-PRI-SEAS | 2025-03-19 | ADDED QTY |  | COMPLETE IN MILLING | 700 | 700 | 0 |  | 100% | 2025-03-28 | SITE
REL-PRI-SEAS-SOUTH CANOPY FIX | 2025-03-20 | ADDED QTY |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-03-21 | SITE
REL-PRI-COMMONS_ADDITIONAL_COVER PLATES | 2025-04-28 | REMAKES |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2025-05-02 | SITE
REL-PRI-COMMONS METAL PAN INFILL | 2025-04-29 | REMAKES |  | IN PROGRESS | 0 | 1 | 1 | TIM | 0% | 2025-05-02 | SITE
200 |  | 1632 | 0 |  | 271212 | 271213 | 1 |  | 100%

## PRI BIO
PRINCETON BIO LEFT TO FABRICATE
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
REL-PRI-13.1 | 2023-09-08 | 108 |  | COMPLETE IN MILLING | 44179 | 44179 | 0 |  | 100% | 2024-01-05 | 2024-02-14
REL-PRI-11.1 [BULK PARTS] | 2023-09-08 | BULK |  | COMPLETE IN MILLING | 13903 | 13903 | 0 |  | 100% |  | 2024-01-17
REL-PRI-11.2 [BULK PARTS] | 2023-09-26 | BULK |  | COMPLETE IN MILLING | 1948 | 1948 | 0 |  | 100%
REL-PRI-SEAS BULK EMB 01 | 2023-09-27 | EMBEDS |  | COMPLETE IN MILLING | 6779 | 6779 | 0 |  | 100% |  | SITE
REL-PRI-16.1 | 2023-10-11 | 60 |  | COMPLETE IN MILLING | 25055 | 25055 | 0 |  | 100% |  | SHIMS RELEASED 2/27
REL-SEAS-EMB02 | 2023-10-11 | EMBEDS |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% |  | SITE
REL-PRI-SEAS EMB 03 ANC-2036 | 2023-10-20 | EMBEDS |  | COMPLETE IN MILLING | 15 | 15 | 0 |  | 100% |  | SITE
REL-PRI-SEAS EMB03 | 2023-10-20 | EMBEDS |  | COMPLETE IN MILLING | 590 | 590 | 0 |  | 100% | 2023-11-14 | SITE
REL-PRI-EMB04 | 2023-11-20 | EMBEDS |  | COMPLETE IN MILLING | 604 | 604 | 0 |  | 100% | 2023-11-30 | 2023-12-11
REL-PRI-ADDL-EMB2 | 2023-11-20 | EMBEDS |  | COMPLETE IN MILLING | 115 | 115 | 0 |  | 100% | 2023-11-30 | SITE
REL-PRI-SEAS-EMB05 | 2023-11-27 | EMBEDS |  | COMPLETE IN MILLING | 821 | 821 | 0 |  | 100% | 2023-12-06 | REC'D 1321 ERECTION ANGLE 1/15/24
REL-PRI-SEAS-EMB06 | 2023-11-30 | EMBEDS |  | COMPLETE IN MILLING | 409 | 409 | 0 |  | 100% | 2023-12-15 | REC'D 1321 ERECTION ANGLE 1/15/ REC'D PLOW BOLTS 2/15
REL-PRI-SEAS-EMB07 | 2023-11-30 | EMBEDS |  | COMPLETE IN MILLING | 370 | 370 | 0 |  | 100% | 2023-12-15 | REC'D 1321 ERECTION ANGLE 1/15/26
REL-PRI-11.4A [11 Units] | 2023-12-19 | 11 |  | COMPLETE IN MILLING | 2145 | 2145 | 0 |  | 100% | 2024-01-19
CBE JAN Embeds | 2023-12-28 | EMBEDS |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-01-03 | SITE
REL-PRI-12.1A [30 Units] | 1/2/24/REVISED 1/21/24 | 30 |  | COMPLETE IN MILLING | 2627 | 2627 | 0 |  | 100% | 2024-02-16 | ONLY REVISED PARTS LEFT
REL-PRI-11.1B [36 Units] | 2024-01-03 | 36 |  | COMPLETE IN MILLING | 3030 | 3030 | 0 |  | 100% | 2024-03-22 | SMALL MILLED PARTS LEFT ALU PART [16] TO 400BC RELEASED 3/22/24 3/27/24
REL-PRI-11.1A [113 Units] | 2024-01-03 | 113 |  | COMPLETE IN MILLING | 9498 | 9498 | 0 |  | 100% | 1/19/24--1/26/2024 | 50 UNITS BY 1/19/24
REL-PRI-11.2 [52 UNITS] | 2024-01-08 | 52 |  | COMPLETE IN MILLING | 12654 | 12654 | 0 |  | 100% | 2024-03-01
REL-PRI-MISSING-ANC | 2024-01-09 | ANCHORS |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2024-01-19 | SITE/1/25/24
REL-PRI-SEAS-CBE-GFRC | 2024-01-09 | 224 |  | COMPLETE IN MILLING | 5600 | 5600 | 0 |  | 100% | 2024-02-16 | FIRST 1/2 COMPLETE 2/9/24/REC'D PLATE REVISION INFO 1/23/24
REL-PRI-13.2 [24 Units] | 2024-01-09 | 24 |  | COMPLETE IN MILLING | 14252 | 14252 | 0 |  | 100% | 2024-02-16 | MISSING 528 [15] FROM KM
REL-PRI-STS-SEAS01 | 2024-01-09 | STARTER SILL |  | COMPLETE IN MILLING | 490 | 490 | 0 |  | 100% | 2024-01-19 | SITE
REL-PRI-CBE-EMB02 | 2024-01-12 | EMBEDS |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-01-15 | SITE/1/25/24
REL-PRI-11.3 [30 Units] | 2024-01-15 | 30 |  | COMPLETE IN MILLING | 9084 | 9084 | 0 |  | 100% | 2024-03-08 | 8 REVISED PARTS RELEASED 2/29/24-13 REVISED FPN'S 3/11/24 COMPLETE 3/12/24
REL-PRI-STS-3-6 | 2024-01-22 | STARTER SILL |  | COMPLETE IN MILLING | 312 | 312 | 0 |  | 100% | 2024-02-02 | SITE
REL-PRI-COMMONS-MISSING-ANC | 2024-01-31 | ANCHORS |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2024-02-06 | SITE
REL-PRI-12.1B [37 Units] | 2024-02-06 | 37 |  | COMPLETE IN MILLING | 2410 | 2410 | 0 |  | 100% | 2024-03-15
REL-PRI-26.1 [44 Units] | 2024-02-06 | 44 |  | COMPLETE IN MILLING | 6893 | 6893 | 0 |  | 100% | 2024-04-19 | POST PAINTED BPN'S RELEASED 3/21/24 TO SPECTRUM 4/16/24
REL-PRI-STS-08-09-11-12 | 2024-02-08 | STARTER/FLASHING |  | COMPLETE IN MILLING | 637 | 637 | 0 |  | 100% | 2024-03-01 | SITE
REL-PRI-11.2-DOOR-REV [2 Units] | 2024-02-08 | 2 |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-02-23
REL-PRI-16.2 [33 UNITS] | 2/8/24 BT ONLY | 31 |  | COMPLETE IN MILLING | 12067 | 12067 | 0 |  | 100% | 2024-04-12 | FRM RELEASED 3/21/24 REMAINING PARTS RELEASED 3/26/24 MISSING 528 [6] FROM KM PARTS ADDED [24] ON 4/18/24 ADDED PARTS MISSING 552 [22] FROM KM
REL-PRI-11.4B [16 UNITS] | 2024-02-08 | 16 |  | COMPLETE IN MILLING | 4142 | 4142 | 0 |  | 100% | 2024-03-22 | FPN'S LEFT
REL-PRI-CBE-EMB-04 | 2024-02-14 | EMBEDS |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2024-02-23 | SITE
REL-PRI-STS-07-10 Flashing Only | 2024-02-21 | FLASHING |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-03-15 | SITE
REL-PRI-CBE-EMB-03 | 2024-02-21 | EMBEDS |  | COMPLETE IN MILLING | 1131 | 1131 | 0 |  | STEEL | 2024-03-15 | SITE
REL-PRI-18.1 [23 Units] | 2024-02-22 | 23 |  | COMPLETE IN MILLING | 1105 | 1105 | 0 |  | 100% | 2024-06-28 | MISSING 1X4 [110], 1X3 [26] FROM KM
REL-PRI-STS-07-10 [7 Units] | 2024-02-22 | STARTER SILL |  | COMPLETE IN MILLING | 223 | 223 | 0 |  | 100% | 2024-03-15 | SITE
REL-PRI-28.1 [27 Units] | 2024-02-26 | 27 |  | COMPLETE IN MILLING | 7074 | 7074 | 0 |  | 100% | 2024-07-05 | POST PAINTED BPN'S RELEASED 3/21/24 TO SPECTRUM 4/16/24 MISSING 1305 [219] FROM KM
REL-PRI-MISSING-ANC2 | 2024-02-27 | ANCHORS |  | COMPLETE IN MILLING | 96 | 96 | 0 |  | 100% | 2024-03-01 | SITE
REL-PRI-STS-21-22 Flashing Only | 2024-02-29 | FLASHING |  | COMPLETE IN MILLING | 35 | 35 | 0 |  | 100% | 2024-03-22 | SITE
REL-PRI-STS-21-22 [13 Units] | 2024-02-29 | STARTER SILL |  | COMPLETE IN MILLING | 518 | 518 | 0 |  | 100% | 2024-03-22 | SITE
REL-PRI-CBE-EMB-05 | 2024-03-07 | EMBEDS |  | COMPLETE IN MILLING | 903 | 903 | 0 |  | 100% | 2024-04-05 | PARTS ADDED [158] 3/25/24/SITE
REL-PRI-25.1 [45 Units] | 2024-03-07 | 45 |  | COMPLETE IN MILLING | 6336 | 6336 | 0 |  | 100% | 2024-05-17 | MANY PARTS ON HOLD- BSH, BPN, FPN, FRM, MSC, SHM, STL PARTS OFF HOLD 4/9/24 RELEASED FPN REVSIONS 5/9 ONLY FPN LEFT WAITING ON REVISED 2PCS FPN'S
REL-PRI-12.1C [3 units] | 2024-03-07 | 3 |  | COMPLETE IN MILLING | 121 | 121 | 0 |  | 100% | 2024-03-15 | MISSING 6X6X3/8 ANGLE [4] FROM YARD [ETA 3/21/24]
REL-PRI-11.3-FPN-REV | 2024-03-11 | REMAKE FPN'S |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-03-15
REL-PRI-24.1 [33 Units] | 2024-03-18 | 33 |  | COMPLETE IN MILLING | 5964 | 5964 | 0 |  | 100% | 2024-04-05
REL-PRI-STS-13_21_LV5 | 2024-03-19 | STARTER SILL |  | COMPLETE IN MILLING | 1108 | 1108 | 0 |  | 100% | 2024-03-29 | FLASHING 3/27/24 TO SITE/SITE 4/3/24
REL-PRI-11.4C [24 Units] | 2024-03-19 | 24 |  | COMPLETE IN MILLING | 4345 | 4345 | 0 |  | 100% | 2024-04-26 | REMAINING INFORMATION RELEASED 3/28/24 POST PAINTED PARTS TO SPECTRUM 4/16/24 PARTS ON HOLD- 470 [6] DURANAR/DURACRON
REL-PRI-BIOE EMB 01 | 2024-03-20 | FIELD FIX |  | COMPLETE IN MILLING | 60 | 60 | 0 |  | 100% | 2024-03-22 | SITE
REL-PRI-CBE EMB 06 | 2024-03-21 | FIELD FIX |  | COMPLETE IN MILLING | 252 | 252 | 0 |  | 100% | 2024-04-19 | NEED 3/4 SHEET MATERIAL/SITE
REL-PRI-CBE-EMB-07 | 2024-03-25 | FIELD FIX |  | COMPLETE IN MILLING | 101 | 101 | 0 |  | 100% | 2024-04-19 | NEED 3/4 SHEET MATERIAL/SITE
REL-PRI-BIOE_PARP_FLASHING_LV4 | 2024-03-25 | FLASHING |  | COMPLETE IN MILLING | 119 | 119 | 0 |  | 100% | 2024-04-05 | SITE
REL-PRI-16.2B | 2024-04-01 | 2 |  | COMPLETE IN MILLING | 595 | 595 | 0 |  | 100% | 2024-04-26 | MISSING 528 [1] FROM KM
REL-PRI-25.3 [4 Units] | 2024-04-02 | 4 |  | COMPLETE IN MILLING | 1282 | 1282 | 0 |  | 100% | 2024-05-10 | ONLY FPN LEFT ADDED 11PCS REVISED EXTRUSIONS
PARP_Flashing_LV5 | 2024-04-02 | FLASHING |  | COMPLETE IN MILLING | 230 | 230 | 0 |  | 100% | 2024-04-19 | SITE
SHM-PRI-PV-1002-01 | 2024-04-04 | SHIMS |  | COMPLETE IN MILLING | 96 | 96 | 0 |  | 100% | 2024-04-05 | SITE
REL-PRI-STS-24-30 [14 Units] | 2024-04-04 | STARTER |  | COMPLETE IN MILLING | 83 | 83 | 0 |  | 100% | 2024-04-26
REL-PRI-STS-24-30-FLASHING | 2024-04-04 | FLASHING |  | COMPLETE IN MILLING | 431 | 431 | 0 |  | 100% | 2024-04-26 | SITE
REL-PRI-Reglazing | 2024-04-08 | REGLAZING |  | COMPLETE IN MILLING | 160 | 160 | 0 |  | 100% | 2024-04-19 | SITE
REL-PRI-29.1 [29 Units] | 2024-04-08 | 29 |  | COMPLETE IN MILLING | 4888 | 4888 | 0 |  | 100% | 2024-06-21 | 40PCS POST PAINT PARTS TO SPECTRUM 5/7/24- COMPLETE MISSING 1305 [145] FROM KM
REL-PRI-MISSING-ANC-1057 | 2024-04-12 | MISSING ANCHORS |  | COMPLETE IN MILLING | 52 | 52 | 0 |  | 100% | 2024-04-26 | SITE
REL-PRI-17.1 [110 units] | BULK AND PAINTED 4/12/24 FRM 5/20/24 | 110 |  | COMPLETE IN MILLING | 9954 | 9954 | 0 |  | 100% | 2024-06-28 | 1ST 168PCS POST PAINT PARTS TO SPECTRUM 5/7/24- COMPLETE ADDED 2ND 63PCS POST PAINTED PARTS TO SPECTRUM 5/10/24 563PCS TO HDG 6/14/24 MISSING 4X6X1/2 [110] FROM VENDOR REC'D 7/3/24
REL-PRI-24.2 [15 Units] | 2024-04-17 | 15 |  | COMPLETE IN MILLING | 1283 | 1283 | 0 |  | 100% | 2024-05-24 | TO HDG/ REC'D 5X5 TUBE 5/17/24 PARTS TO HDG READY TO GO 5/17/24 MISSING TUBE 1106 [1], 1107 [1]
REL-PRI-30.1 [44 Units] | 2024-04-17 | 44 |  | COMPLETE IN MILLING | 3899 | 3899 | 0 |  | 100% | 2024-05-24 | 12PCS POST PAINTED PARTS TO SPECTRUM 5/10/24-COMPLETE MISSING 4X4X1/8 TUBE [79] FROM KM
REL-PRI-Field Fix_FF-1021 | 2024-04-18 | FIELD FIX |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2024-04-19 | SITE
CBE EMB 08 | 2024-04-18 | REVISED ANCHORS |  | COMPLETE IN MILLING | 70 | 70 | 0 |  | 100% | 2024-04-19 | SITE
REL-PRI-SEAS CANOPY STEEL | 2024-04-19 |  |  | COMPLETE IN MILLING | 13 | 13 | 0 |  | 100% | 2024-05-03 | TO HDG 5/3/24
ALU-PRI-S1322-1002-02 (400A) [To Paint Shop] | 2024-04-19 | MISSING WASHERS |  | COMPLETE IN MILLING | 300 | 300 | 0 |  | 100% | 2024-04-19 | SITE
REL-PRI-27.1 [24 Units] | 2024-04-19 | 24 |  | COMPLETE IN MILLING | 5776 | 5776 | 0 |  | 100% | 2024-06-07 | 24PCS POST PAINTED PARTS TO SPECTRUM 5/10/24-COMPLETE 48PCS POST PAINTED PARTS TO SPECTRUM 5/10/24-COMPLETE MISSING 6X6X1/4 TUBE [11] FROM VENDOR
REL-PRI-ANC-5018 | 2024-04-29 | ANCHOR FIX |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-05-10 | SITE
REL-PRI-ANC-5019 | 2024-04-29 | ANCHOR FIX |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2024-05-10 | SITE
REL-PRI-Field Fix_FF-1022 | 2024-04-29 | ANCHOR FIX |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2024-05-10 | SITE
REL-PRI-Field Fix_FF-1023 | 2024-04-29 | ANCHOR FIX |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-05-10 | SITE
REL-PRI-CBE EMB 10 | 2024-05-03 | EMBEDS |  | COMPLETE IN MILLING | 126 | 126 | 0 |  | 100% | 2024-05-17 | SITE
REL-PRI-Missing EMB | 2024-05-03 | MISSING EMBEDS |  | COMPLETE IN MILLING | 458 | 458 | 0 |  | 100% | 2024-05-17 | SITE
REL-PRI-25.2 [18 UNITS] | 2024-05-06 | 18 |  | COMPLETE IN MILLING | 2930 | 2930 | 0 |  | 100% | 2024-08-09 | MISSING 1305 [16] FROM KM
REL-PRI-STS-25_26_Flashing | 2024-05-06 | FLASHING |  | COMPLETE IN MILLING | 466 | 466 | 0 |  | 100% | 2024-05-24 | SITE
REL-PRI-STS-25_26 | 5/6/24 5/20/24 | STARTER SILL STEEL PARTS |  | COMPLETE IN MILLING | 119 | 119 | 0 |  | 100% | 5/24/24 5/31/24 | SITE
REL-PRI-GFRC North Portal | 5/6/24 5/20/24 ON HOLD 5/24/24 OFF HOLD 5/29/24 ON HOLD 6/6/24 OFF HOLD | STEEL FRAMES |  | COMPLETE IN MILLING | 1413 | 1413 | 0 |  | 100% | 2024-07-05 | MISSING 1 1/2 TUBE FOR THE FRAMES READY FOR HDG 7/8/24
REL-PRI-GFRC South Portal | 5/6/24 5/20/24 ON HOLD 5/24/24 OFF HOLD 5/29/24 ON HOLD 6/3/24 OFF HOLD | STEEL FRAMES |  | COMPLETE IN MILLING | 1824 | 1824 | 0 |  | 100% | 2024-06-21 | READY FOR HDG 6/25/24
REL-PRI-Field Fix_FF-1024 | 2024-05-08 | ANCHOR FIX |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-05-10 | SITE
REL-PRI-CBE EMB 11 | 2024-05-08 | ANCHOR |  | COMPLETE IN MILLING | 21 | 21 | 0 |  | 100% | 2024-05-10 | SITE
REL-PRI-CBE STATER SILL PL | 2024-05-10 | STARTER SILL |  | COMPLETE IN MILLING | 71 | 71 | 0 |  | 100% | 2024-05-24 | BLDG 350
REL-PRI-ANC-2021 Field Fix | 2024-05-10 | ANCHOR FIX |  | COMPLETE IN MILLING | 32 | 32 | 0 |  | 100% | 2024-05-31 | SITE
REL-PRI-16.2B_REV2 [2 UNITS] | 2024-05-10 | 2 |  | COMPLETE IN MILLING | 37 | 37 | 0 |  | 100% | 2024-05-17
REL-PRI-PAV EMB 01 | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 956 | 956 | 0 |  | 100% | 2024-06-07 | SITE
REL-PRI-SEAS Expansion Joint Covers | 2024-05-16 | FPN |  | COMPLETE IN MILLING | 44 | 44 | 0 |  | 100% | 2024-05-31 | SITE
REL-PRI-STS-BRG_LV5 | 2024-05-20 | STARTER SILL |  | COMPLETE IN MILLING | 175 | 175 | 0 |  | 100% | 2024-05-31 | SITE
REL-PRI-17.1 Bulk 04 | 2024-05-20 | POST PAINTED |  | COMPLETE IN MILLING | 930 | 930 | 0 |  | 100% | 2024-06-07 | 930PCS POST PAINTED PARTS TO SPECTRUM 6/12/24
REL-PRI-Interior Trim Test | 2024-05-20 | TRIM TEST |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100% | 2024-05-31 | SITE/MISSING 1296 [1] FROM KM
REL-PRI-BIOE F FIX STARTER | 2024-05-22 | STARTER FIX |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2024-06-04 | SITE
REL-PRI-FIELD FIX 1026 | 2024-05-29 | ANCHOR FIX |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-06-14 | SITE
REL-PRI-STS-27 | 2024-05-31 | STARTER SILL |  | COMPLETE IN MILLING | 187 | 187 | 0 |  | 100% | 2024-06-14 | SITE
REL-PRI-CBE EMB ADD MATERIAL | 2024-06-05 | EMBEDS |  | COMPLETE IN MILLING | 44 | 44 | 0 |  | 100% | 2024-06-11 | SITE
ANC-2038 | 2024-06-10 | ANCHOR |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-06-14 | SITE
ANC-2042 | 2024-06-10 | ANCHORS |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-06-14 | SITE
REL-PRI-CW-3 Lifting Plates | 2024-06-10 | PLATES |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2024-06-14 | SITE
REL-PRI-STS-23 | 2024-06-17 | STARTER |  | COMPLETE IN MILLING | 87 | 87 | 0 |  | 100% | 2024-07-12 | SITE
REL-PRI-STS-23_FLASHING_ONLY | 2024-06-17 | FLASHING |  | COMPLETE IN MILLING | 481 | 481 | 0 |  | 100% | 2024-06-28 | SITE
REL-PRI-FIELD FIX 1028 | 2024-06-12 | ANCHOR FIX |  | COMPLETE IN MILLING | 28 | 28 | 0 |  | 100% | 2024-06-21 | SITE
Missing Z clips - BSH | 2024-06-19 | Z CLIPS |  | COMPLETE IN MILLING | 17 | 17 | 0 |  | 100% | 2024-06-28 | SITE
REL-PRI-17.1 Bulk 05 | 2024-06-20 | MISC. PARTS |  | COMPLETE IN MILLING | 1202 | 1202 | 0 |  | 100% | 2024-08-23 | FRAME SHOP IS ASSEMBLING TUBES
REL-PRI-NORTH PORTAL STEEL | 2024-06-20 |  |  | COMPLETE IN MILLING | 618 | 618 | 0 |  | 100% | 2024-07-12 | PARTS READY FOR HDG 7/12/24
REL-PRI-SEAS PAV. CANOPY F | 2024-06-24 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-07-05 | PARTS READY FOR HDG 7/10/24
REL-PRI-31.1 [54 UNITS] | 5/30/24 5/30/24 ON HOLD 6/24/24 OFF HOLD 6/27/24 ON HOLD 7/25/24 OFF HOLD | 54 |  | COMPLETE IN MILLING | 1289 | 1289 | 0 |  | 100% | 2024-09-06 | OLD BATCH COIL
ALU.P-PRI-1154-01 | 2024-06-25 |  |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-06-28 | SITE
ALU-PRI-S0998-1004-02 | 2024-06-25 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-07-05 | SITE
REL-PRI-STS-28_FLASHING_ONLY | 2024-07-02 | FLASHING |  | COMPLETE IN MILLING | 660 | 660 | 0 |  | 100% | 2024-07-26 | SITE
REL-PRI-STS-28 | 2024-07-02 | STARTER |  | COMPLETE IN MILLING | 94 | 94 | 0 |  | 100% | 2024-07-26 | SITE
GFRC Anchor Templates | 2024-07-08 |  |  | COMPLETE IN MILLING | 36 | 36 | 0 |  | 100% | 2024-07-12
REL-PRI-STS-17_29_FLASHING_ONLY | 2024-07-09 | FLASHING |  | COMPLETE IN MILLING | 846 | 846 | 0 |  | 100% | 2024-08-02 | SITE
REL-PRI-STS-17_29 | 2024-07-09 | STARTER |  | COMPLETE IN MILLING | 141 | 141 | 0 |  | 100% | 2024-08-02 | SITE
Site Anchor Shims - SHM | 2024-07-09 | SHM |  | COMPLETE IN MILLING | 330 | 330 | 0 |  | 100% | 2024-07-19 | SITE
STL.B-PRI-GA-1002-01 | 2024-07-12 | FIX |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2024-07-12 | SITE
REL-PRI-BRIDGE-PARP-FLASHING | 2024-07-16 | FLASHING |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2024-08-02 | SITE
REL-PRI-CBE_LV5_PARP_FLASH | 2024-07-16 | FLASHING |  | COMPLETE IN MILLING | 158 | 158 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-CBE_LV4_PARP_FLASH | 2024-07-16 | FLASHING |  | COMPLETE IN MILLING | 65 | 65 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-CW-5_PARP_FLASHING | 2024-07-16 | FLASHING |  | COMPLETE IN MILLING | 67 | 67 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-STS-18_FLASHING_ONLY | 2024-07-16 | FLASHING |  | COMPLETE IN MILLING | 1183 | 1183 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-STS-18 | 2024-07-16 | STARTER |  | COMPLETE IN MILLING | 136 | 136 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-STS-29_L4_FLASHING | 2024-07-16 | FLASHING |  | COMPLETE IN MILLING | 78 | 78 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-STS-29_L4 | 2024-07-16 | STARTER |  | COMPLETE IN MILLING | 21 | 21 | 0 |  | 100% | 2024-08-09 | SITE
L4 West Lab End Anchor Fist Anchor Field Fix | 2024-07-22 | FIX |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-STS-BIOE_CANOPY_S | 2024-07-22 | CANOPY |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-STS-BIOE_CANOPY_S_FLASHING | 2024-07-22 | CANOPY |  | COMPLETE IN MILLING | 26 | 26 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-11.3A Field FPN | 2024-07-22 | FPN |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-11.3A | 2024-07-23 | 50 |  | COMPLETE IN MILLING | 1961 | 1961 | 0 |  | 100% | 2024-09-25 | OLD BATCH COIL
STL-PRI-GA-4001-01 - STL | 2024-07-23 | ANCHORS |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-07-26 | SITE
REL-PRI-END DAM | 2024-07-25 | END DAM |  | COMPLETE IN MILLING | 36 | 36 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-ANC-1014A | 2024-07-25 | ANCHOR FIX |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-08-02 | SITE
REL-PRI-STS-23B | 2024-07-26 | STARTER |  | COMPLETE IN MILLING | 31 | 31 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-STS-23B_FLASHING_ONLY | 2024-07-26 | FLASHING |  | COMPLETE IN MILLING | 108 | 108 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-STS-31_FLASHING_ONLY | 2024-07-26 | FLASHING |  | COMPLETE IN MILLING | 599 | 599 | 0 |  | 100% | 2024-08-16 | SITE
REL-PRI-STS-31 | 2024-07-26 | STARTER |  | COMPLETE IN MILLING | 206 | 206 | 0 |  | 100% | 2024-08-16 | SITE
REL-PRI-Portal North Flashing | 2024-07-26 | FLASHING |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-08-16 | SITE
REL-PRI-Portal South Flashing | 2024-07-26 | FLASHING |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-BIOE_LV2 - SKIRT_N_ABC | 2024-07-26 | SKIRTS |  | COMPLETE IN MILLING | 447 | 447 | 0 |  | 100% | 2024-10-04 | START 9/23 NEW BATCH COIL
REL-PRI-BIOE_LV2 - SKIRT_S_AB | 2024-07-26 | SKIRTS |  | COMPLETE IN MILLING | 53 | 53 | 0 |  | 100% | 2024-10-04 | START 9/23 NEW BATCH COIL
REL-PRI-BIOE - COPING_MSC_LV4 | 2024-07-26 | SUB COPING |  | COMPLETE IN MILLING | 148 | 148 | 0 |  | 100% | 2024-10-04 | SITE
REL-PRI-BIOE - COPING_MSC_LV5 | 2024-07-26 | SUB COPING |  | COMPLETE IN MILLING | 255 | 255 | 0 |  | 100% | 2024-10-04 | SITE
REL-PRI-BIOE_COPING_LV4 | 2024-07-26 | 66 |  | COMPLETE IN MILLING | 641 | 641 | 0 |  | 100% | 2024-10-25 | NEW BATCH COIL
REL-PRI-BIOE_COPING_LV5 | 2024-07-26 | 121 |  | COMPLETE IN MILLING | 1184 | 1184 | 0 |  | 100% | 2024-11-15 | NEW BATCH COIL
ANC-2078 | 2024-08-05 | FIX |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-08-09 | SITE
REL-PRI-SITE ANCHORS 01 | 2024-08-05 | FIX |  | COMPLETE IN MILLING | 116 | 116 | 0 |  | 100% | 2024-08-23 | SITE
ANC-4008 | 2024-08-14 | SHIMS |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-08-14 | SITE
REL-PRI-17.1 Missing Parts | 2024-08-16 |  |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2024-08-30
REL-PRI-25.2 Missing BPN | 2024-08-22 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-08-23
REL-PRI-SEAS CANOPY BRIDGE | 2024-08-27 | 2 |  | COMPLETE IN MILLING | 197 | 197 | 0 |  | 100% | 2024-11-29 | REVISED INFO RELEASED 12/16/24
REL-PRI-SEAS CANOPY PAV N | 2024-08-27 | 2 |  | COMPLETE IN MILLING | 84 | 84 | 0 |  | 100% | 2024-11-22 | SITE
REL-PRI-SEAS CANOPY VESTIB N | 2024-08-27 | 1 |  | COMPLETE IN MILLING | 108 | 108 | 0 |  | 100% | 2024-11-22 | SITE
REL-PRI-SEAS CANOPY VESTIB S | 2024-08-27 | 5 |  | COMPLETE IN MILLING | 93 | 93 | 0 |  | 100% | 2024-11-22 | SITE
REL-PRI-SEAS Pav ANC Update | 2024-08-27 |  |  | COMPLETE IN MILLING | 32 | 32 | 0 |  | 100% | 2024-09-13 | SITE
REL-PRI-BIOE LV4 SKIRT | 2024-08-27 |  |  | COMPLETE IN MILLING | 452 | 452 | 0 |  | 100% | 2024-10-04 | NEW BATCH COIL
REL-PRI-BIOE - NE_FAN_WELL | 2024-08-27 | 10 |  | COMPLETE IN MILLING | 168 | 168 | 0 |  | 100% | 2024-11-15 | NEW BATCH COIL
REL-PRI-BIOE - NW_FAN_WELL | 2024-08-27 | 8 |  | COMPLETE IN MILLING | 87 | 87 | 0 |  | 100% | 2024-11-29 | NEW BATCH COIL
REL-PRI-SEAS GFRC Sill Brackets | 2024-08-29 |  |  | COMPLETE IN MILLING | 352 | 352 | 0 |  | 100% | 2024-09-06 | TO HDG
17.1 Pavilion - PNL-PRI-F54-000-0002 UPDATE | 2024-09-24 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-10-04 | SITE
REL-PRI-BIOE_LV2_SKIRT_W_A | 2024-09-25 | 4 |  | COMPLETE IN MILLING | 65 | 65 | 0 |  | 100% | 2024-10-11 | SITE
Steel Parts for DKI | 2024-09-26 |  |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2024-09-26
17.1 Remakes | 2024-09-26 |  |  | COMPLETE IN MILLING | 35 | 35 | 0 |  | 100% | 2024-09-30
REL-PRI-CBE_LV2_SKIRT_18 | 2024-10-09 | 23 |  | COMPLETE IN MILLING | 169 | 169 | 0 |  | 100% | 2024-11-15 | NEW BATCH COIL
REL-PRI-SEAS Bridge Canopy Additional Cladding | 2024-10-23 |  |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-11-01 | SITE
REL-PRI-SEAS Updated North Portal Flashing |  |  |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-SEAS ANC-4008 Field Fix |  |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2024-11-15 | SITE
REL-PRI-SEAS South Canopy Transom Fix |  |  |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-BIOE -ANCHOR HOOK UPDATE_ANC-2041 |  |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-11-01 | SITE
REL-PRI-SEAS Bridge Skirts Misc |  |  |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-SEAS Bridge Skirts FPN |  | 3 |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-SEAS North Vestibule Canopy Cladding |  |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-SEAS North Pavilion Canopy Cladding |  |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-SEAS South Canopy Cladding |  |  |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-CBE_LV2_SKIRT_29 | P2 |  |  | COMPLETE IN MILLING | 21 | 21 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-CBE_LV2_SKIRT_25 | P1 | 2 |  | COMPLETE IN MILLING | 39 | 39 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-Bridge_Coping_MSC | CP1 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-SEAS Bridge Angles | ANGLES |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-11-04 | SITE
REL-PRI-SEAS Bridge Canopy Post-Painted FPN | 2024-11-07 | 2 |  | COMPLETE IN MILLING | 42 | 42 | 0 |  | 100% | 2025-03-26 | 11/22/24 TO SPECTRUM BACK FROM PAINT 1/28/25
REL-PRI-CBE_LV2_SKIRT_N_31 | 2024-11-07 |  |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2024-12-13 | SITE
REL-PRI-CBE_COPING MSC_LV4 | 2024-11-07 |  |  | COMPLETE IN MILLING | 82 | 82 | 0 |  | 100% | 2024-12-13
REL-PRI-CBE-NE-FAN-WELL | 2024-11-07 | 4 |  | COMPLETE IN MILLING | 91 | 91 | 0 |  | 100% | 2024-12-13 | SITE
REL-PRI-CBE-SW-FAN-WELL | 2024-11-07 | 7 |  | COMPLETE IN MILLING | 120 | 120 | 0 |  | 100% | 2024-12-13 | SITE
REL-PRI-Pavilion_Coping_MSC | 2024-11-07 |  |  | COMPLETE IN MILLING | 127 | 127 | 0 |  | 100% | 2024-12-13
REL-PRI-CBE_LV2_SKIRT_24_31 | 2024-11-07 | 9 |  | COMPLETE IN MILLING | 177 | 177 | 0 |  | 100% | 2024-12-13 | SITE
REL-PRI-CBE COPING_MSC_LV5 | 2024-11-07 |  |  | COMPLETE IN MILLING | 192 | 192 | 0 |  | 100% | 2024-12-13
REL-PRI-SEAS CBE Sill Front Pans | 2024-11-18 | 67 |  | COMPLETE IN MILLING | 201 | 201 | 0 |  | 100% | 2025-02-28 | 12/20/24 TO SPECTRUM NEED TUBE TO COMPLETE
REL-PRI-CBE_LV2_SKIRT_30_31 | 2024-11-07 |  |  | COMPLETE IN MILLING | 269 | 269 | 0 |  | 100% | 2024-12-13
REL-PRI-SEAS Pavilion Sill Front Pans | 2024-11-11 | 60 |  | COMPLETE IN MILLING | 212 | 212 | 0 |  | 100% | 2025-02-14 | 12/13/24 TO SPECTRUM BACK FROM PAINT 1/28/25
REL-PRI-CBE LV4 SKIRT | 2024-11-07 |  |  | COMPLETE IN MILLING | 309 | 309 | 0 |  | 100% | 2024-12-13 | NEW BATCH COIL
REL-PRI-SEAS BioE Sill Front Pans | 2024-11-18 | 123 |  | COMPLETE IN MILLING | 369 | 369 | 0 |  | 100% | 2025-04-04 | 3/3/25 TO SPECTRUM
REL-PRI-SEAS Pavilion Sill Field Items | 2024-11-11 |  |  | COMPLETE IN MILLING | 375 | 375 | 0 |  | 100% | 2024-12-13 | SITE ITEMS
REL-PRI-CBE_COPING_LV4 | 2024-11-11 | 37 |  | COMPLETE IN MILLING | 384 | 384 | 0 |  | 100% | 2025-01-24 | SITE
REL-PRI-Pavilion_Coping | 2024-11-18 | 53 |  | COMPLETE IN MILLING | 444 | 444 | 0 |  | 100% | 2025-01-24 | SITE
REL-PRI-SEAS CBE Sill Field Items | 2024-11-18 |  |  | COMPLETE IN MILLING | 481 | 481 | 0 |  | 100% | 2025-01-24 | SITE ITEMS
REL-PRI-SEAS BioE Sill Field Items | 2024-11-18 |  |  | COMPLETE IN MILLING | 879 | 879 | 0 |  | 100% | 2025-01-24 | SITE ITEMS
REL-PRI-CBE_COPING_LV5 | 2024-11-18 | 92 |  | COMPLETE IN MILLING | 894 | 894 | 0 |  | 100% | 2025-01-03 | SITE
REL-PRI-SEAS_ES_SHADOW BOXES | 2024-11-18 |  |  | COMPLETE IN MILLING | 62 | 62 | 0 |  | 100% | 2024-12-06 | SITE
REL-PRI-CW5 New GFRC Corner Bracket | 2024-11-08 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-11-15 | SITE
ANC-1015 | 2024-11-22 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-11-29 | SITE
REL-PRI-SEAS FPN Replacement | 2024-12-09 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-12-13 | SITE
REL-PRI-ADDITIONAL ANCHORS FOR CBE | 2024-12-09 |  |  | COMPLETE IN MILLING | 28 | 28 | 0 |  | 100% | 2024-12-13 | SITE
REL-PRI-SEAS Pav PNL Rebuild [1 unit] | 2024-12-09 |  |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2024-12-13 | SITE
ANC-2099 | 2024-12-11 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-12-13 | SITE
REL-PRI-Bridge_Coping | 2024-12-13 | 10 |  | COMPLETE IN MILLING | 95 | 95 | 0 |  | 100% | 2025-01-31 | REC'D FEED BACK/MAKE AS IS
REL-PRI-SEAS Bridge Undercladding - Mtg Hardware | 2024-12-19 |  |  | COMPLETE IN MILLING | 554 | 554 | 0 |  | 100% | 2025-01-31 | NEED CLARIFICATION ON POST PAINT OR COIL
REL-PRI-SEAS Bridge Undercladding - Panels | 2024-12-19 | 48 |  | COMPLETE IN MILLING | 1964 | 1964 | 0 |  | 100% | 2025-01-31 | NEED CLARIFICATION ON POST PAINT OR COIL
BSH-PRI-GA-2221-01 | 2025-01-02 | 6 |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2025-01-31 | SITE
ALU.A-PRI-1B08-01 | 2025-01-02 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-01-03 | SITE
REL-PRI-ADDITIONAL COPING SUPPORTIVE ANGLES | 2025-01-09 |  |  | COMPLETE IN MILLING | 108 | 108 | 0 |  | 100% | 2025-01-11 | SITE
REL-PRI-ES_ANC-2051 & ANC-2080_FIX | 2025-01-24 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-01-28 | SITE
BSH-PRI-4384-01 Remake | 2025-01-30 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-01-31 | SITE
STS-23B - Missing Parts | 2025-01-31 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-02-03 | SITE
Missing cover cap fin for CBE | 2025-02-06 |  |  | COMPLETE IN MILLING | 60 | 60 | 0 |  | 100% | 2025-02-12 | SITE
REL-PRI-SEAS Additional Extended Hooks | 2025-02-07 |  |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2025-02-12 | SITE
Missing Field Parts | 2025-02-12 |  |  | COMPLETE IN MILLING | 13 | 13 | 0 |  | 100% | 2025-02-21 | SITE
Field Remake | 2025-02-17 |  |  | COMPLETE IN MILLING | 80 | 80 | 0 |  | 100% | 2025-02-21 | SITE
Pavillion Sill FPN Remake | 2025-02-17 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-21 | SITE
STL-T-PRI-GA-1018-02 | 2025-02-26 |  |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2025-02-26 | SITE
REL-PRI-24.2 Field Horizontal Fins | 2025-03-03 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2025-03-07 | SITE
REL-PRI-SEAS_ADDITIONAL COVER PLATES | 2025-03-03 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2025-03-07 | SITE
REL-PRI-SEAS Shadowbox Retro Install | 2025-03-21 |  |  | COMPLETE IN MILLING | 44 | 44 | 0 |  | 100% | 2025-04-03 | SITE
ALU TUBE ASSY | 2025-03-21 |  |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2025-04-04 | SITE
CANOPY MISC | 2025-03-24 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-04-05 | SITE
BSH-PRI-4366-99 | 2025-03-25 |  |  | COMPLETE IN MILLING | 150 | 150 | 0 |  | 100% | 2025-04-09 | SITE
MISC FPN ASSY | 2025-03-27 |  |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2025-04-11 | NEED REVISED INFO ON BSH &FPN MISSING 3X3X1/8 TUBE [1] NEEDS POST PAINT MADE FROM COIL AS PER JT SITE
Canopy MISC Remakes | 2025-03-31 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-04-11 | SITE
24-31 Skirt Remake | 2025-03-31 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2025-04-11 | SITE
REL-PRI-ADDITIONAL COPING SUPPORTIVE ANGLES-PART 2 | 2025-04-01 |  |  | COMPLETE IN MILLING | 240 | 240 | 0 |  | 100% | 2025-04-11 | SITE
REL-PRI-SEAS Level 4 Corner Coping | 2025-04-01 |  |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2025-04-18 | SITE
S0998 Connectors | 2025-04-08 |  |  | COMPLETE IN MILLING | 120 | 120 | 0 |  | 100% | 2025-04-18 | SITE
BSH-PRI-1369-01 | 2025-04-08 |  |  | COMPLETE IN MILLING | 336 | 336 | 0 |  | 100% | 2025-04-09 | SITE
FPN-PRI-11U2-01 | 2025-04-08 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-04-11 | SITE
REL-PRI-CBE_LV2_SKIRT_18 | 2025-04-15 | REVISION |  | COMPLETE IN MILLING | 170 | 170 | 0 |  | 100% | 2025-04-25 | SITE
MISC PARTS | 2025-04-18 | MISC. PARTS |  | COMPLETE IN MILLING | 67 | 67 | 0 |  | 100% | 2025-05-02 | SITE
REL-PRI-CBE_LV2 ADDITIONAL SKIRT REMAKE | 2025-04-24 | REMAKE FPN'S |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2025-05-02 | SITE
234 |  | 2090 | 0 |  | 275139 | 275139 | 0 |  | 100%
Roof panels | 2025-04-07 |  |  | COMPLETE IN MILLING | 194 | 194 | 0 |  | 100% | 2025-04-18
Wall panels Upper level | 2025-04-08 |  |  | COMPLETE IN MILLING | 242 | 242 | 0 |  | 100% | 2025-04-18
Spectrum Samples | 2025-04-28 |  |  | COMPLETE IN MILLING | 44 | 44 | 0 |  | 100% | 2025-05-02

## RUTGERS
RUTGERS LEFT TO FABRICATE
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
Release ¦ VMU | 2023-09-18 | VMU |  | COMPLETE IN MILLING | 302 | 302 | 0 |  | 100%
Release ¦ VMU - SITE MATERIAL | 2023-10-10 | VMU |  | COMPLETE IN MILLING | 93 | 93 | 0 |  | 100% | 2023-10-17
Release ¦ STEEL BRACKETS LVL6 - WELDED ON SITE | 2024-01-05 | BRACKETS |  | COMPLETE IN MILLING | 84 | 84 | 0 |  | 100% | 2024-01-12
Release ¦ PMU | 2024-01-31 | PMU |  | COMPLETE IN MILLING | 165 | 165 | 0 |  | 100% | 2024-02-09
Release ¦ LEVEL 02 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 1808 | 1808 | 0 |  | 100% | 2024-04-19 | 2024-05-01
Release ¦ LEVEL 03 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 3036 | 3036 | 0 |  | 100% | 2024-05-10
Release ¦ LEVEL 04 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 2832 | 2832 | 0 |  | 100% | 2024-05-17 | 2024-05-20
Release ¦ LEVEL 05 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 2878 | 2878 | 0 |  | 100% | 2024-05-24
Release ¦ LEVEL 06 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 1135 | 1135 | 0 |  | 100% | 2024-06-07
Release ¦ LEVEL 07 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 1564 | 1564 | 0 |  | 100% | 2024-06-21
Release ¦ LEVEL 08 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 1796 | 1796 | 0 |  | 100% | 2024-06-28
Release ¦ LEVEL 09 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 3177 | 3177 | 0 |  | 100% | 2024-07-12
Release ¦ LEVEL 10 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 2769 | 2769 | 0 |  | 100% | 2024-07-26
Release ¦ EMB-001 | 2024-03-08 | EMBEDS |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100%
Release ¦ LEVEL 02 UNTYPICAL EMBED ORDER | 2024-04-29 | EMBEDS |  | COMPLETE IN MILLING | 567 | 567 | 0 |  | 100% | 2024-05-03
Release ¦ LEVEL 03 UNTYPICAL EMBED ORDER | 2024-04-29 | EMBEDS |  | COMPLETE IN MILLING | 562 | 562 | 0 |  | 100% | 2024-05-10
Release ¦ LEVEL 04 UNTYPICAL EMBED ORDER | 2024-04-29 | EMBEDS |  | COMPLETE IN MILLING | 205 | 205 | 0 |  | 100% | 2024-05-17 | 2024-05-20
Release ¦ LEVEL 05 UNTYPICAL EMBED ORDER | 2024-04-29 | EMBEDS |  | COMPLETE IN MILLING | 168 | 168 | 0 |  | 100% | 2024-05-24
Release ¦ LEVEL 06 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 158 | 158 | 0 |  | 100% | 2024-06-07
Release ¦ LEVEL 07 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 228 | 228 | 0 |  | 100% | 2024-06-21
Release ¦ LEVEL 08 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 186 | 186 | 0 |  | 100% | 2024-06-28
Release ¦ LEVEL 09 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 76 | 76 | 0 |  | 100% | 2024-07-12
Release ¦ LEVEL 10 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 76 | 76 | 0 |  | 100% | 2024-07-26
Release ¦ LEVEL 11 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 2721 | 2721 | 0 |  | 100% | 2024-08-02
Release ¦ LEVEL 12 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 2046 | 2046 | 0 |  | 100% | 2024-08-09
Release ¦ LEVEL 02-04 EMBED EAR EXTENSION RELEASE | 2024-05-28 | EMBEDS |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2024-06-14
REL-RUT-4.1_1CW | 6/10/24 7/8/24 | 51 SHM |  | COMPLETE IN MILLING | 4473 | 4473 | 0 |  | 100% | 2024-07-05
REL-RUT-1.01 A [55 UNITS] | 2024-06-25 | 55 |  | COMPLETE IN MILLING | 4798 | 4798 | 0 |  | 100% | 2024-08-02 | MISSING 592 [58] FROM KM
REL-RUT-4.1_2CW [242 UNITS] | 2024-06-25 | 242 |  | COMPLETE IN MILLING | 13439 | 13439 | 0 |  | 100% | 2024-08-16 | MISSING 592 [10] FROM KM
REL-RUT-4.1ACW [4 UNITS] | 2024-06-25 | 4 |  | COMPLETE IN MILLING | 195 | 195 | 0 |  | 100% | 2024-08-30 | MISSING 592 [6] FROM KM
REL-RUT-BULK ORDER 5.2 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 2272 | 2272 | 0 |  | 100% | 2024-09-06
REL-RUT-BULK ORDER 5.1 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 9885 | 9885 | 0 |  | 100% | 2024-09-13
REL-RUT-BULK ORDER 4.2 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 2004 | 2004 | 0 |  | 100% | 2024-09-27
REL-RUT-BULK ORDER 4.3 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 6030 | 6030 | 0 |  | 100% | 2024-11-22
REL-RUT-BULK ORDER 4.4 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 10929 | 10929 | 0 |  | 100% | 2024-11-29 | TO 393
REL-RUT-BULK ORDER 4.6 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 1426 | 1426 | 0 |  | 100% | 2024-12-27 | TO 393
REL-RUT-BULK ORDER 5.3 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 603 | 603 | 0 |  | 100% | 2024-11-15
REL-RUT-BULK ORDER 7.1 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 2103 | 2103 | 0 |  | 100% | 2024-11-15
REL-RUT-EMB-903 | 2024-07-08 | EMBEDS |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-07-12
REL-RUT-4.1_3 CW [4 UNITS] | 2024-07-09 | 4 |  | COMPLETE IN MILLING | 267 | 267 | 0 |  | 100% | 2024-08-02
REL-RUT-FIN END CAPS | 2024-07-10 | CAPS |  | COMPLETE IN MILLING | 2290 | 2290 | 0 |  | 100% | 2024-07-19 | CAPS READY FOR PAINT 7/17/24
REL-RUT-EMB-005 LVL 02 | 2024-07-11 | EMBEDS |  | COMPLETE IN MILLING | 766 | 766 | 0 |  | 100% | 2024-08-16 | SITE
REL-RUT-EMB-005 LVL 03 | 2024-07-11 | EMBEDS |  | COMPLETE IN MILLING | 594 | 594 | 0 |  | 100% | 2024-08-16 | SITE
REL-RUT-BULK ORDER 11.2 | 2024-07-11 | BULK |  | COMPLETE IN MILLING | 442 | 442 | 0 |  | 100% | 2024-03-21
REL-RUT-SILL-001 | 2024-07-15 | STARTER |  | COMPLETE IN MILLING | 2292 | 2292 | 0 |  | 100% | 2024-08-16 | SITE
REL-RUT-EMB-904 | 2024-07-16 | EMBEDS |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2024-07-16 | SITE
RUT BPN PARTS | 2024-07-16 | BPN |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-07-16
RUT WOOD BUNK PARTS | 2024-07-17 | BUNK PARTS |  | COMPLETE IN MILLING | 4800 | 4800 | 0 |  | 100% | 2024-07-26
REL-RUT-2.1A CW [43 UNITS] | 2024-07-26 | 43 |  | COMPLETE IN MILLING | 8147 | 8147 | 0 |  | 100% | 2024-08-23 | MISSING 592 [397] FROM KM MISSING COUPLER NUTS [156] FROM VENDOR
REL-RUT-2.2A CW [16 UNITS] | 2024-07-26 | 16 |  | COMPLETE IN MILLING | 4785 | 4785 | 0 |  | 100% | 2024-08-09 | MISSING 592 [160] FROM KM
REL-RUT-2.1 CW [40 UNITS] | 2024-07-26 | 40 |  | COMPLETE IN MILLING | 5988 | 5988 | 0 |  | 100% | 2025-01-10 |  | 393
REL-RUT-2.2A STEEL FRAMES | 2024-07-31 | FRAMES |  | COMPLETE IN MILLING | 288 | 288 | 0 |  | 100% | 2024-08-23 | 4 PRIORITY FRAMES READY FOR HDG 8/28/24
REL-RUT-2.2B STEEL FRAMES | 2024-07-31 | FRAMES |  | COMPLETE IN MILLING | 56 | 56 | 0 |  | 100% | 2024-08-23 | HDG
REL-RUT-SILL-002 | 2024-08-05 | STARTER |  | COMPLETE IN MILLING | 523 | 523 | 0 |  | 100% | 2024-08-09
REL-RUT-8.1A CW [12 UNITS] | 2024-08-19 | 12 |  | COMPLETE IN MILLING | 2130 | 2130 | 0 |  | 100% | 2024-09-06 | MISSING 592 [24] FROM KM
REL-RUT-SILL-003 | 2024-08-19 | STARTER |  | COMPLETE IN MILLING | 364 | 364 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-SILL-004 | 2024-08-19 | STARTER |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-4.2 CW [28 UNITS] | 2024-08-19 | 28 |  | COMPLETE IN MILLING | 2903 | 2903 | 0 |  | 100% | 2024-10-11 | WAITING ON STL 1/8 and 1/4
REL-RUT-5.1 CW [268 UNITS] | 2024-08-21 | 268 |  | COMPLETE IN MILLING | 2808 | 2808 | 0 |  | 100% | 2024-09-20
REL-RUT-4.3 CW [226 UNITS] | 2024-08-21 | 226 |  | COMPLETE IN MILLING | 1844 | 1844 | 0 |  | 100% | 2024-11-22
REL-RUT-8.1 CW [13 UNITS] | 2024-08-23 | 13 |  | COMPLETE IN MILLING | 2066 | 2066 | 0 |  | 100% | 2024-10-18
REL-RUT-INFILL PANELS BULK ORDER | 2024-08-26 | BULK |  | COMPLETE IN MILLING | 304 | 304 | 0 |  | 100% | 2024-10-25
REL-RUT-LEVEL PH1 EMBED ORDER | 2024-08-26 | EMBEDS |  | COMPLETE IN MILLING | 2324 | 2324 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-LEVEL PH2 EMBED ORDER | 2024-08-26 | EMBEDS |  | COMPLETE IN MILLING | 2380 | 2380 | 0 |  | 100% | 2024-09-27 | SITE
REL-RUT-BULK ORDER 1.2 | 2024-08-26 | BULK |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-10-25
REL-RUT-BULK ORDER 1.1 | 2024-08-26 | BULK |  | COMPLETE IN MILLING | 54 | 54 | 0 |  | 100% | 2024-10-18
REL-RUT-LEVEL PH2 ROOF EMBED ORDER | 2024-08-26 | EMBEDS |  | COMPLETE IN MILLING | 1539 | 1539 | 0 |  | 100% | 2024-09-27 | SITE
REL-RUT-MISC-003 - SPREADER BAR | 2024-09-05 | MISC |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-5.2 CW [42 UNITS] | 2024-09-10 | 42 |  | COMPLETE IN MILLING | 4626 | 4626 | 0 |  | 100% | 2024-11-15 | WAITING ON STL 1/8 and 1/4
REL-RUT-MISC-004 | 2024-09-13 | MISC |  | COMPLETE IN MILLING | 3160 | 3160 | 0 |  | 100% | 2024-09-16 | SITE
ALU-RUT-S1520-5012-01 | 2024-09-13 | MISC |  | COMPLETE IN MILLING | 45 | 45 | 0 |  | 100% | 2024-09-16
REL-RUT-EMB-905 | 2024-09-20 | EMBEDS |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-09-27 | SITE
REL-RUT-MISC-006 | 2024-09-20 | MISC |  | COMPLETE IN MILLING | 120 | 120 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-MISC-002 | 2024-09-20 | MISC |  | COMPLETE IN MILLING | 430 | 430 | 0 |  | 100% | 2024-09-27 | SITE
RUT - CW7 CORNER SLIDERS | 2024-09-20 | SLIDERS |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-10-04 | READY FOR TO CARNEY
REL-RUT-SILL-005 | 2024-09-20 | STARTER |  | COMPLETE IN MILLING | 473 | 473 | 0 |  | 100% | 2024-10-11 | SITE
REL-RUT-5.3 [28 Units] | 2024-09-20 | 28 |  | COMPLETE IN MILLING | 237 | 237 | 0 |  | 100% | 2024-10-25
REL-RUT-10.1 [62 Units] | 2024-09-20 | 62 |  | COMPLETE IN MILLING | 8327 | 8327 | 0 |  | 100% | 2024-11-29
REL-RUT-10.3 [31 Units] | 2024-09-20 | 31 |  | COMPLETE IN MILLING | 3407 | 3407 | 0 |  | 100% | 2024-11-29
REL-RUT-2.2B [18 Units] | 2024-09-20 | 18 |  | COMPLETE IN MILLING | 3021 | 3021 | 0 |  | 100% | 2025-01-10 |  | 393
REL-RUT-MISC-005 | 2024-09-20 | MISC |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-10-04 | SITE
REL-RUT-EMB-008 | 2024-09-23 | EMBEDS |  | COMPLETE IN MILLING | 27 | 27 | 0 |  | 100% | 2024-09-27 | SITE
REL-RUT-EMB-007 | 2024-09-26 | EMBEDS |  | COMPLETE IN MILLING | 649 | 649 | 0 |  | 100% | 2024-11-01
REL-RUT-SILL-001.1 | 2024-09-26 | STARTER |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-09-30 | SITE
REL-RUT-1.1 CW [48 UNITS] | 2024-10-04 | 48 |  | COMPLETE IN MILLING | 4101 | 4101 | 0 |  | 100% | 2024-10-18
REL - MISSING FIELD PARTS | 2024-10-10 | MISSING PARTS |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-10-15 | SITE
REL-RUT-10.2 CW [17 Units] | 2024-10-16 | 17 |  | COMPLETE IN MILLING | 3359 | 3359 | 0 |  | 100% | 2024-11-29
REL-RUT-4.4 CW [360 Units] | 2024-10-16 | 360 |  | COMPLETE IN MILLING | 3740 | 3740 | 0 |  | 100% | 2024-11-29 | MISSING 580 [22] FROM KM | 393
REL-RUT-SILL-006 | 2024-10-16 | STARTER |  | COMPLETE IN MILLING | 411 | 411 | 0 |  | 100% | 2024-11-15 | SITE
REL-RUT-EMB-009 | 2024-10-17 | EMBEDS |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2024-10-18 | SITE
REL-RUT-4.5 CW [407 UNITS] | 2024-10-21 | 407 |  | COMPLETE IN MILLING | 15568 | 15568 | 0 |  | 100% | 2024-12-27 |  | 350
REL-RUT-7.1 CW [124 UNITS] | 2024-10-21 | 124 |  | COMPLETE IN MILLING | 913 | 913 | 0 |  | 100% | 2024-11-15 |  | 393
REL-RUT-EMB-010 | 2024-10-24 | EMBEDS |  | COMPLETE IN MILLING | 26 | 26 | 0 |  | 100% | 2024-11-01 | SITE
REL-RUT-FLA-002 | 2024-10-31 | FLASHING |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2024-11-15 | SITE
REL-RUT-MFP-002 | 2024-11-01 | MISC |  | COMPLETE IN MILLING | 128 | 128 | 0 |  | 100% | 2024-11-15 | SITE
REL-RUT-EMB-906 | 2024-11-01 | EMBEDS |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-11-08 | SITE
REL-RUT-BULK ORDER 11.1 | 2024-11-01 | BULK |  | COMPLETE IN MILLING | 412 | 412 | 0 |  | 100% | 2024-11-29
REL-RUT-BULK ORDER 7.2 | 2024-11-01 | BULK |  | COMPLETE IN MILLING | 142 | 142 | 0 |  | 100% | 2024-12-06
REL-RUT-MISC-008 | 2024-11-04 | MISC |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2024-11-15 | SITE
REL-RUT-MISC-STN SITE EAST | 2024-11-07 | STONE |  | COMPLETE IN MILLING | 193 | 193 | 0 |  | 100% | 2024-11-29
REL-RUT-MISC-STN SITE NORTH | 2024-11-07 | STONE |  | COMPLETE IN MILLING | 368 | 368 | 0 |  | 100% | 2024-11-29
REL-RUT-MISC-STN SITE SOUTH | 2024-11-07 | STONE |  | COMPLETE IN MILLING | 63 | 63 | 0 |  | 100% | 2024-12-06
REL-RUT-MISC-STN SITE WEST | 2024-11-07 | STONE |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2024-12-06
REL-RUT-4.7 CW [12 Units] | 2024-11-19 | 12 |  | COMPLETE IN MILLING | 1216 | 1216 | 0 |  | 100% | 2025-01-24 |  | 350
REL-RUT-4.6 CW [195 Units] | 2024-11-19 | 195 |  | COMPLETE IN MILLING | 6866 | 6866 | 0 |  | 100% | 2025-02-21 | MISSING 580 [54] FROM KM | 393
REL-RUT-MISC-009 | 2024-12-09 | MISC |  | COMPLETE IN MILLING | 28 | 28 | 0 |  | 100% | 2024-12-20
REL-RUT-MISC-010 | 2024-12-09 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-12-20
REL-RUT-FLA-001 | 2024-12-09 | FLASHING |  | COMPLETE IN MILLING | 482 | 482 | 0 |  | 100% | 2025-02-14 | REVISED INFO RELEASED 12/23/24
REL-RUT-SOF-001 | 2024-12-09 | SOFFIT |  | COMPLETE IN MILLING | 370 | 370 | 0 |  | 100% | 2025-03-14
REL-RUT-EMB-011 | 2024-12-09 | EMBEDS |  | COMPLETE IN MILLING | 1032 | 1032 | 0 |  | 100% | 2025-01-03 | WAITING ON 3/16 STEEL SHEET/NEEDS POST PAINT
REL-RUT-SILL-011 | 2024-12-09 | SILLS |  | COMPLETE IN MILLING | 220 | 220 | 0 |  | 100% | 2025-04-04 | NEEDS POST PAINT
REL-RUT-EMB-013 | 2024-12-09 | EMBEDS |  | COMPLETE IN MILLING | 267 | 267 | 0 |  | 100% | 2025-01-03
REL-RUT-SILL-007 | 2024-12-09 | SILLS |  | COMPLETE IN MILLING | 992 | 992 | 0 |  | 100% | 2025-01-17 | SITE
REL-RUT-SILL-008 | 2024-12-09 | SILLS |  | COMPLETE IN MILLING | 503 | 503 | 0 |  | 100% | 2025-01-24 | SITE
REL-RUT-SILL-009 | 2024-12-09 | SILLS |  | COMPLETE IN MILLING | 76 | 76 | 0 |  | 100% | 2025-01-24 | SITE
REL-RUT-SILL-010 | 2024-12-09 | SILLS |  | COMPLETE IN MILLING | 578 | 578 | 0 |  | 100% | 2025-01-24 | MISSING 1519 [18] FROM KM
REL-RUT-1.2 CW [49 Units] | 2024-12-09 | 49 |  | COMPLETE IN MILLING | 2595 | 2595 | 0 |  | 100% | 2025-01-24 |  | 350
REL-RUT-MISC-011 | 2024-12-09 | MISC |  | COMPLETE IN MILLING | 204 | 204 | 0 |  | 100% | 2025-02-14 | SITE
REL-RUT-3.1A CW [22 Units] | 2024-12-19 | 22 |  | COMPLETE IN MILLING | 1604 | 1604 | 0 |  | 100% | 2025-03-07 | FPN POST PAINT [83] TO SPECTRUM | 350
REL-RUT-9.1 CW | 2025-01-02 | 204 |  | COMPLETE IN MILLING | 14580 | 14580 | 0 |  | 100% | 2025-02-21 | REC'D 3/10/25 580 [21] FROM KM | 350
REL-RUT-FLA-001 - Priority | 2025-01-02 |  |  | COMPLETE IN MILLING | 31 | 31 | 0 |  | 100% | 2025-01-02 | HOT!!!!!!
REL-RUT-11.1 [70 Units] | 2025-01-10 | 70 |  | COMPLETE IN MILLING | 4192 | 4192 | 0 |  | 100% | 2025-02-28 | MISSING 580 [40], 596 [4] FROM KM | 350
REL-RUT-SOF-006 | 2025-01-16 | SOF |  | COMPLETE IN MILLING | 965 | 965 | 0 |  | 100% | 2025-03-21 | SITE
REL-RUT-SOF-002 | 2025-01-16 | SOF |  | COMPLETE IN MILLING | 207 | 207 | 0 |  | 100% | 2025-03-10 | SITE
REL-RUT-SOF-003 | 2025-01-16 | SOF |  | COMPLETE IN MILLING | 198 | 198 | 0 |  | 100% | 2025-03-10 | SITE
REL-RUT-COP-002 | 2025-01-16 | COPING |  | WAITING ON MATERIAL | 173 | 191 | 18 | DEAN | 90.58% | 2025-03-10 | MISSING ALPINE LEDGE BAR/SITE
REL-RUT-SOF-004 | 2025-01-16 | SOF |  | COMPLETE IN MILLING | 212 | 212 | 0 |  | 100% | 2025-04-04 | SITE
REL-RUT-SOF-005 | 2025-01-16 | SOF |  | COMPLETE IN MILLING | 43 | 43 | 0 |  | 100% | 2025-03-24 | SITE
REL-RUT-MISC-012 | 2025-01-16 | MISC |  | COMPLETE IN MILLING | 121 | 121 | 0 |  | 100% | 2025-01-20 | SITE
REL-RUT-FLA-005 | 2025-03-06 | FLASHING |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2025-03-14 | SITE
REL-RUT-COP-003 | 2025-01-21 | COPING |  | COMPLETE IN MILLING | 259 | 259 | 0 |  | 100% | 2025-03-21 | SITE
REL-RUT-FLA-003 | 2025-01-21 | FLASHING |  | COMPLETE IN MILLING | 64 | 64 | 0 |  | 100% | 2025-02-28 | SITE
REL-RUT-MISC-013 | 2025-01-21 | MISC |  | COMPLETE IN MILLING | 820 | 820 | 0 |  | 100% | 2025-02-28 | SITE
REL-RUT-FLA-008 | 2025-01-21 | FLASHING |  | COMPLETE IN MILLING | 135 | 135 | 0 |  | 100% | 2025-02-07 | SITE
REL-RUT-FLA-007 | 2025-03-06 | FLASHING |  | COMPLETE IN MILLING | 412 | 412 | 0 |  | 100% | 2025-03-28 | SITE
REL-RUT-FLA-006 | 2025-03-06 | FLASHING |  | COMPLETE IN MILLING | 168 | 168 | 0 |  | 100% | 2025-03-21 | SITE
EMB-011 - Slot Revision | 2025-02-03 | REVISION |  | COMPLETE IN MILLING | 60 | 60 | 0 |  | 100% | 2025-02-07 | SITE
REL-RUT-11.2 - UNIT RELEASE [91 UNITS] | 2025-02-05 | 91 |  | COMPLETE IN MILLING | 3731 | 3731 | 0 |  | 100% | 2025-03-07 | MISSING 580 [58], 1431 [55] FROM KM | 350
REL-RUT-FLA-009 CW1 EASE IC | 2025-02-20 | FLASHING |  | COMPLETE IN MILLING | 142 | 142 | 0 |  | 100% | 2025-03-21 | SITE
REL-RUT-FLA-009 CW1 NORTH EAST IC | 2025-02-20 | FLASHING |  | COMPLETE IN MILLING | 87 | 87 | 0 |  | 100% | 2025-03-21 | SITE
REL-RUT-FLA-009 CW1 NORTH IC | 2025-02-20 | FLASHING |  | COMPLETE IN MILLING | 90 | 90 | 0 |  | 100% | 2025-03-21 | SITE
REL-RUT-COP-007 CANOPY NORTH LV 2 | 2025-02-20 | COPING |  | COMPLETE IN MILLING | 435 | 435 | 0 |  | 100% | 2025-04-04 | NEED REVISED INFO SITE
REL-RUT-FLA-010 | 2025-02-20 | FLASHING |  | COMPLETE IN MILLING | 74 | 74 | 0 |  | 100% | 2025-03-21 | SITE
REL-RUT-COP-010 | 2025-02-20 | COPING |  | WAITING ON MATERIAL | 135 | 163 | 28 | DEAN | 82.82% | 2025-04-04 | MISSING ALPINE LEDGE BAR/SITE
REL-RUT-FLA-004 | 2025-03-06 | FLASHING |  | COMPLETE IN MILLING | 52 | 52 | 0 |  | 100% | 2025-03-21 | SITE
REL-RUT-MFP-003 NEW CW7 SLIDER LEVEL 9 | 2025-02-26 | REVISION |  | COMPLETE IN MILLING | 248 | 248 | 0 |  | 100% | 2025-03-07 | SITE
Starter Sill Shims | 2025-03-05 | SHIMS |  | COMPLETE IN MILLING | 400 | 400 | 0 |  | 100% | 2025-03-12 | SITE
REL-RUT-MISC-014 | 2025-03-13 | MISC |  | COMPLETE IN MILLING | 86 | 86 | 0 |  | 100% | 2025-03-28 | SITE
REL-RUT-FLA-011 | 2025-03-13 | FLASHING |  | COMPLETE IN MILLING | 1138 | 1138 | 0 |  | 100% | 2025-04-04 | SITE
SOF-003 Remake | 2025-03-14 | REVISION |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-03-21
BSH-RUT-5208-01 | 2025-03-14 | REVISION |  | COMPLETE IN MILLING | 60 | 60 | 0 |  | 100% | 2025-03-17 | SITE
REL-RUT-MFP-004 | 2025-03-20 | REVISION |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2025-03-25 | SITE
REL-EMB-014 | 2025-03-21 | REVISION |  | COMPLETE IN MILLING | 29 | 29 | 0 |  | 100% | 2025-03-28 | SITE
REL-RUT-FLA-012 FLASHINGS AROUND OVERHEAD DOORS | 2025-03-24 | FLASHING |  | COMPLETE IN MILLING | 414 | 414 | 0 |  | 100% | 2025-04-11 | SITE/POST ALODINE
REL-RUT-EMB-015 STEEL BRACKETS FOR OVERHEAD DOORS | 2025-03-24 | EMBEDS |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2025-03-28 | SITE
Missing Field Items | 2025-03-31 |  |  | COMPLETE IN MILLING | 56 | 56 | 0 |  | 100% | 2025-04-04 | SITE
STL.P-RUT-6101-XX | 2025-04-02 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2025-04-04 | SITE
REL-RUT-SILL-012 | 2025-04-08 | SILLS |  | IN PROGRESS | 102 | 144 | 42 | DEAN | 70.83% | 2025-05-09 | SITE
REL-RUT-SILL-013 | 2025-04-09 | SILLS |  | IN PROGRESS | 137 | 194 | 57 | DEAN | 70.62% | 2025-05-16 | SITE
REL-RUT-FLA-014 | 2025-04-11 | FLASHING |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-18 | SITE
REL-RUT-EMB-016 | 2025-04-14 | EMBEDS |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2025-04-18 | SITE
REL-RUT-MFP-005 | 2025-04-18 | REVISION |  | IN PROGRESS | 23 | 34 | 11 | DEAN | 67.65% | 2025-05-02 | SITE
REL-RUT-COP-001 | 2025-04-18 | COPING |  | IN PROGRESS | 623 | 665 | 42 | DEAN | 93.68% | 2025-05-09 | SITE
REl-RUT-COP-011 | 2025-04-21 | COPING |  | IN PROGRESS | 0 | 6 | 6 | ALL SHOPS | 0% | 2025-05-30 | SITE
Missing Field Parts 1 | 2025-04-28 | REVISION |  | IN PROGRESS | 5 | 15 | 10 | BRIAN | 33.33% | 2025-05-02 | SITE
STN-RUT-GA-1001-01 | 2025-04-28 | REVISION |  | IN PROGRESS | 8 | 10 | 2 | BRIAN | 80% | 2025-05-02 | SITE
ALU-RUT-S1518-2001-01 | 2025-04-28 | REVISION |  | IN PROGRESS | 0 | 500 | 500 | BRIAN | 0% | 2025-05-02 | SITE
Missing Field Parts 2 | 2025-04-29 | REVISION |  | IN PROGRESS | 3 | 38 | 35 | BRIAN | 7.895% | 2025-05-02 | SITE
SIL-RUT-GA-1001-73 | 2025-04-29 | REVISION |  | IN PROGRESS | 4 | 7 | 3 | DEAN | 57.14% | 2025-05-02 | SITE
SIL-RUT-GA-1001-68 | 2025-04-29 | REVISION |  | IN PROGRESS | 4 | 7 | 3 | DEAN | 57.14% | 2025-05-02 | SITE
SIL-RUT-GA-1001-67 | 2025-04-29 | REVISION |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-05-02 | SITE
ALU-RUT-S1321-XX | 2025-04-30 | REVISION |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-05-09 | SITE
172 |  | 2731 | 0 |  | 239138 | 239895 | 757 |  | 99.68%

## MT SINAI
MOUNT SINAI LEFT TO FABRICATE
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
REL-TCH-AMU I [2 units] | 2023-08-23 |  |  | COMPLETE IN MILLING | 32 | 32 | 0 |  | 100% | 2023-09-11
REL-TCH-AMU II [2 Units] | 2023-10-20 |  |  | COMPLETE IN MILLING | 36 | 36 | 0 |  | 100% | 2023-10-24
REL-TCH-GMU [3 units] | 2024-10-20 |  |  | COMPLETE IN MILLING | 176 | 176 | 0 |  | 100% | 2023-10-24
REL-TCH-AMU 1.2 [2 UNITS] | 2024-01-29 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2024-02-02 | MISSING S-1444 FROM KM 3/12/24 ALU [6] RELEASED
REL-TCH-WT7 VMU | 2024-01-29 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-02-14
Misc. Parts outside of releases | 2024-02-07 |  |  | COMPLETE IN MILLING | 37 | 37 | 0 |  | 100% | 2024-02-16
VMU [10 Units] CONT'D RELEASE | 2/22/24 RERELEASED 5/13/24 |  |  | COMPLETE IN MILLING | 732 | 732 | 0 |  | 100% | 2024-06-07 | PAINTED PARTS RELEASED ONLY 2/22/24 REMAINING PARTS RELEASED 4/2/24
PMU [13 Units] | 2/22/24-3/12/24 |  |  | COMPLETE IN MILLING | 1261 | 1261 | 0 |  | 100% | 3/1/24 PAINTED PARTS 3/22/24 PMU UNITS TCH-PMU 4/5/24 | 2/22/24 PAINTED PARTS RELEASED ONLY 3/12/24 UNIT PARTS RELEASED MISSING 617 [3] FORM KM
REL-TCH-VMU-SITE [10 Units] | 2024-05-20 | SITE MATERIAL |  | COMPLETE IN MILLING | 13 | 13 | 0 |  | 100% | 2024-06-14
VMU TEST [to steel shop] | 2024-06-28 | TEST |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-07-05
VMU [10 Units] ALU(400BC) [TO 707] | 2024-07-01 | VMU |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-07-08
REL-TCH-CW 1.01_A | 2024-11-18 | 20 |  | COMPLETE IN MILLING | 1995 | 1995 | 0 |  | 100% | 2025-02-21
REL-TCH-POST-PAINTED BULK RELEASE | 2024-12-11 |  |  | COMPLETE IN MILLING | 3736 | 3736 | 0 |  | 100% | 2025-01-24 | NEEDS TO GO TO POST PAINT
REL-TCH-JIG | 2024-12-12 |  |  | COMPLETE IN MILLING | 65 | 65 | 0 |  | 100% | 2025-01-31
REL-TCH-CW 1.01 [153 Units] | 2025-01-02 | 153 |  | COMPLETE IN MILLING | 12976 | 12976 | 0 |  | 100% | 2025-02-21
REL-TCH-CW 1.02 [150 Units] | 2025-01-02 | 150 |  | COMPLETE IN MILLING | 16681 | 16681 | 0 |  | 100% | 2025-02-21
REL-TCH-CW 1.03 [192 Units] | 2025-01-07 | 192 |  | COMPLETE IN MILLING | 16720 | 16720 | 0 |  | 100% | 2025-03-07
REL-TCH-CW 7.01 [324 UNITS] | 2025-01-24 | 324 |  | COMPLETE IN MILLING | 25598 | 25598 | 0 |  | 100% | 2025-03-28
REL-TCH-CW 1.04 [156 Units] | 2025-01-24 | 156 |  | COMPLETE IN MILLING | 15515 | 15515 | 0 |  | 100% | 2025-04-04
REL-TCH-CW 7.02 [190 Units] | 2025-02-03 | 190 |  | COMPLETE IN MILLING | 16015 | 16015 | 0 |  | 100% | 2025-04-18
REL-TCH-CW 1.05 [103 UNITS] | 2025-02-03 | 103 |  | COMPLETE IN MILLING | 10783 | 10783 | 0 |  | 100% | 2025-04-18
REL-TCH-CW 7.04 [20 UNITS] | 2025-02-03 | 20 |  | COMPLETE IN MILLING | 1685 | 1685 | 0 |  | 100% | 2025-04-18
Misc. Parts outside of releases | 2025-03-13 | SAMPLES |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2025-03-14 | TESTING SAMPLES
Misc. Parts outside of releases | 2025-03-17 | JIGS |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2025-03-21
Misc. Parts outside of releases | 2025-03-20 | SAMPLES |  | COMPLETE IN MILLING | 56 | 56 | 0 |  | 100% | 2025-03-28 | TESTING SAMPLES
REL-TCH-BULK PRJ WT7 | 2025-04-03 |  |  | COMPLETE IN MILLING | 35 | 35 | 0 |  | 100% | 2025-04-11 | NEEDS TO GO TO POST PAINT
REL-TCH-CW 5.01 [19 UNITS] 707 | 2025-04-04 | 19 | 19 | IN PROGRESS | 5291 | 6318 | 1027 | ALL SHOPS | 83.74% | 2025-05-30 | MISSING BPN MATERIAL [118]
REL-TCH-CW 5.02 [19 UNITS] | 2025-04-07 | 19 | 19 | IN PROGRESS | 3328 | 5741 | 2413 | ALL SHOPS | 57.97% | 2025-05-30 | MISSING BPN MATERIAL [115] NEEDS TO GO TO POST PAINT
Misc. Parts outside of releases | 2025-04-07 |  |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2025-05-02 | NEEDS TO GO TO POST PAINT
REL-TCH-7.03 [9 UNITS] | 2025-04-18 | 9 | 9 | IN PROGRESS | 746 | 1834 | 1088 | ALL SHOPS | 40.68% | 2025-05-30 | NEEDS TO GO TO POST PAINT
REL-TCH-CW 6.01 [18 UNITS] | 2025-04-22 | 18 | 18 | IN PROGRESS | 498 | 1836 | 1338 | ALL SHOPS | 27.12% | 2025-05-30 | MISSING 614 [204] FROM KM NEEDS TO GO TO POST PAINT
REL-TCH-CW 4.01 [33 UNITS] | 2025-04-30 | 33 | 33 | NOT IN PROGRESS | 0 | 1485 | 1485 | ALL SHOPS | 0%
32 |  | 1406 | 98 |  | 134208 | 141559 | 7351 |  | 94.81%

## BROWN (hidden)
BROWN LEFT TO FABRICATE FOR 707
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
VMU [4 Units] | 2023-01-22 | 4 |  | COMPLETE IN MILLING | 393 | 393 | 0 |  | 100% | 2024-01-25
1 |  | 4 |  |  | 393 | 393 | 0 |  | 100%

## FMG
FMG LEFT TO FABRICATE
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
REL-FMG-1.02 [42 Units] | 2024-06-27 | 42 |  | COMPLETE IN MILLING | 3384 | 3384 | 0 |  | 100% | 2024-07-19 | MISSING 1473 [2], 1474 [2] FROM KM BPN [113] ON HOLD
REL-FMG-1.02-FINS | 2024-06-27 | FINS |  | COMPLETE IN MILLING | 2552 | 2552 | 0 |  | 100% | 2024-07-19 | MISSING 631 [45] FROM KM
REL-FMG-BULK-FINCAPS | 2024-07-01 | CAPS |  | COMPLETE IN MILLING | 2340 | 2340 | 0 |  | 100% | 2024-07-19 | CAPS READY FOR POST PAINT 7/23/24
REL-FMG-EMB-BAR2-LVL3 | 2024-07-18 | EMBEDS |  | COMPLETE IN MILLING | 208 | 208 | 0 |  | 100% | 2024-08-16 | SITE
REL-FMG-SB-EWA-3 | 2024-07-18 | SHADOW BOXES |  | COMPLETE IN MILLING | 493 | 493 | 0 |  | 100% | 2024-11-29 | 707 TO ASSEMBLE
REL-FMG-1.03 [24 Units] | 2024-07-18 | 24 |  | COMPLETE IN MILLING | 1902 | 1902 | 0 |  | 100% | 2024-09-20
REL-FMG-1.03-FINS | 2024-07-18 | FINS |  | COMPLETE IN MILLING | 1295 | 1295 | 0 |  | 100% | 2024-09-20 | WAITING ON SNOW BUTTONS
REL-FMG-1.04 (42 Units) | 2024-07-22 | 42 |  | COMPLETE IN MILLING | 3286 | 3286 | 0 |  | 100% | 2024-10-11 | MISSING 1473 [2] FROM KM
REL-FMG-1.04-FINS | 2024-07-22 | FINS |  | COMPLETE IN MILLING | 3297 | 3297 | 0 |  | 100% | 2024-10-11
REL-FMG-1.02-FOAM | 2024-07-25 | FOAM |  | COMPLETE IN MILLING | 616 | 616 | 0 |  | 100% | 2024-08-02
REL-FMG-RIMU6 | 2024-07-26 | MOCKUP |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2024-07-29
REL-FMG-RIMU7 | 2024-07-26 | MOCKUP |  | COMPLETE IN MILLING | 89 | 89 | 0 |  | 100% | 2024-07-29
REL-FMG-RIMU8 | 2024-08-05 | MOCKUP |  | COMPLETE IN MILLING | 38 | 38 | 0 |  | 100% | 2024-08-09
REL-FMG-RIMU9 | 2024-08-06 | MOCKUP |  | COMPLETE IN MILLING | 17 | 17 | 0 |  | 100% | 2024-08-09
REL-FMG-RIMU7.2 | 2024-08-12 | MOCKUP |  | COMPLETE IN MILLING | 94 | 94 | 0 |  | 100% | 2024-08-14
REL-FMG-POSTPAINT-BULKBATCH1 | 2024-08-12 | BULK |  | COMPLETE IN MILLING | 142 | 142 | 0 |  | 100% | 2024-09-06
REL-FMG-1.01 [22 Units] | 2024-08-12 | 22 |  | COMPLETE IN MILLING | 1237 | 1237 | 0 |  | 100% | 2024-10-11
REL-FMG-1.01 FINS | 2024-08-12 | FINS |  | COMPLETE IN MILLING | 845 | 845 | 0 |  | 100% | 2024-10-11
REL-FMG-BAR2-PHROOF | 2024-08-12 | EMBEDS |  | COMPLETE IN MILLING | 424 | 424 | 0 |  | 100% | 2024-08-30 | SITE
REL-FMG-1.05 | 2024-08-12 | 21 |  | COMPLETE IN MILLING | 1606 | 1606 | 0 |  | 100% | 2024-11-29
REL-FMG-1.05 FINS | 2024-08-12 | FINS |  | COMPLETE IN MILLING | 764 | 764 | 0 |  | 100% | 2024-11-29
REL-FMG-BAR2-PENTHOUSE | 2024-08-12 | EMBEDS |  | COMPLETE IN MILLING | 107 | 107 | 0 |  | 100% | 2024-08-30 | SITE
REL-FMG-BAR2-LVL4 | 2024-08-12 | EMBEDS |  | COMPLETE IN MILLING | 154 | 154 | 0 |  | 100% | 2024-08-23 | SITE
REL-FMG-BAR1-LVL4 | 2024-08-12 | EMBEDS |  | COMPLETE IN MILLING | 437 | 437 | 0 |  | 100% | 2024-08-23 | SITE
REL-FMG-JIG-TEST | 2024-08-13 | JIG |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-08-16
REL-FMG-FOAM-BULK-BATCH2 | 2024-09-10 | BULK |  | COMPLETE IN MILLING | 3086 | 3086 | 0 |  | 100% | 2024-10-11
REL-FMG-STS-1.01 | 2024-09-10 | STARTER SILL |  | COMPLETE IN MILLING | 290 | 290 | 0 |  | 100% | 2024-11-22 | MISSING 1607 [25] FROM KM
REL-FMG-STS-1.07 | 2024-09-10 | STARTER SILL |  | COMPLETE IN MILLING | 157 | 157 | 0 |  | 100% | 2024-11-22 | MISSING 1607 [13] FROM KM
REL-FMG-EMB-BAR3-LVL2 | 2024-09-10 | EMBEDS |  | COMPLETE IN MILLING | 142 | 142 | 0 |  | 100% | 2024-10-25 | SITE
REL-FMG-EMB-BAR3-LVL3 | 2024-09-10 | EMBEDS |  | COMPLETE IN MILLING | 132 | 132 | 0 |  | 100% | 2024-11-01 | SITE
REL-FMG-EMB-BAR4-LVL1 | 2024-09-10 | EMBEDS |  | COMPLETE IN MILLING | 134 | 134 | 0 |  | 100% | 2024-10-25 | SITE
REL-FMG-EMB-BAR4-LVL2 | 2024-09-10 | EMBEDS |  | COMPLETE IN MILLING | 382 | 382 | 0 |  | 100% | 2024-10-25 | SITE
REL-FMG-EMB-BAR3-LVL4 | 2024-09-10 | EMBEDS |  | COMPLETE IN MILLING | 148 | 148 | 0 |  | 100% | 2024-11-01 | SITE
REL-FMG-EMB-BAR4-LVL3 | 2024-09-10 | EMBEDS |  | COMPLETE IN MILLING | 308 | 308 | 0 |  | 100% | 2024-11-01 | SITE
REL-FMG-EMB-BAR4-LVL4 | 2024-09-10 | EMBEDS |  | COMPLETE IN MILLING | 418 | 418 | 0 |  | 100% | 2024-11-01 | SITE
REL-FMG-MP-FIELDFIX | 2024-09-17 | FIX |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-09-30 | SITE
REL-FMG-STS-11.03 | 2024-09-30 | STARTER SILL |  | COMPLETE IN MILLING | 44 | 44 | 0 |  | 100% | 2024-12-27
REL-FMG-STS-11.01 | 2024-09-30 | STARTER SILL |  | COMPLETE IN MILLING | 259 | 259 | 0 |  | 100% | 2024-12-27
REL-FMG-STS-11.05 | 2024-09-30 | STARTER SILL |  | COMPLETE IN MILLING | 165 | 165 | 0 |  | 100% | 2024-12-27
REL-EMBED-STEEL-BAR1-LVL2 | 2024-09-30 | EMBEDS |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR2-PENTHOUSE | 2024-09-30 | EMBEDS |  | COMPLETE IN MILLING | 33 | 33 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR1-LVL4 | 2024-09-30 | EMBEDS |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR1-LVL3 | 2024-09-30 | EMBEDS |  | COMPLETE IN MILLING | 57 | 57 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR2-LVL2 | 2024-09-30 | EMBEDS |  | COMPLETE IN MILLING | 47 | 47 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR2-MECH PLATFORM | 2024-09-30 | EMBEDS |  | COMPLETE IN MILLING | 377 | 377 | 0 |  | 100% | 2024-10-18 | SITE
REL-FMG-1.06 [44 Units] | 2024-09-10 | 44 |  | COMPLETE IN MILLING | 3246 | 3246 | 0 |  | 100% | 2024-11-22
REL-FMG-1.06 FINS | 2024-10-01 | FINS |  | COMPLETE IN MILLING | 4635 | 4635 | 0 |  | 100% | 2024-11-22
REL-FMG-1.07 [19 UNITS] | 2024-10-01 | 19 |  | COMPLETE IN MILLING | 1349 | 1349 | 0 |  | 100% | 2024-11-22
REL-FMG-1.07_FIN | 2024-10-01 | FINS |  | COMPLETE IN MILLING | 1082 | 1082 | 0 |  | 100% | 2024-11-22
REL-FMG-1.08 [36 UNITS] | 2024-10-01 | 36 |  | COMPLETE IN MILLING | 2029 | 2029 | 0 |  | 100% | 2024-12-06
REL-FMG-1.08-FINS | 2024-10-01 | FINS |  | COMPLETE IN MILLING | 1449 | 1449 | 0 |  | 100% | 2024-12-06
REL-FMG-3.01 [30 Units] | 2024-10-16 | 30 |  | COMPLETE IN MILLING | 1479 | 1479 | 0 |  | 100% | 2024-12-20 | MISSING 626 [50] FROM KM
REL-FMG-3.02 [40 Units] | 2024-10-16 | 40 |  | COMPLETE IN MILLING | 1459 | 1459 | 0 |  | 100% | 2025-01-10 | MISSING 626 [50] FROM KM
REL-FMG-EMB-BAR3-PENTHOUSE | 2024-09-10 | EMBEDS |  | COMPLETE IN MILLING | 332 | 332 | 0 |  | 100% | 2024-11-22 | SITE
REL-FMG-EMBED-STEEL-BAR3-PENTHOUSE | 2024-10-18 | EMBEDS |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2024-11-22 | SITE
REL-FMG-EMBED-STEEL-BAR3-LVL2 | 2024-10-18 | EMBEDS |  | COMPLETE IN MILLING | 57 | 57 | 0 |  | 100% | 2024-11-22 | SITE
REL-FMG-EMBED-STEEL-BAR4-LVL3 | 2024-10-18 | EMBEDS |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2024-11-22 | SITE
REL-FMG-EMBED-STEEL-BAR4-LVL2 | 2024-10-18 | EMBEDS |  | COMPLETE IN MILLING | 74 | 74 | 0 |  | 100% | 2024-11-22 | SITE
REL-FMG-EMBED-STEEL-BAR3-LVL3 | 2024-10-18 | EMBEDS |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100% | 2024-11-22 | SITE
REL-FMG-EMBED-STEEL-BAR3-LVL4 | 2024-10-18 | EMBEDS |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2024-11-22 | SITE
REL-FMG-38.1 | 2024-11-18 |  |  | COMPLETE IN MILLING | 32 | 32 | 0 |  | 100% | 2024-11-18 | SITE
REL-FMG-38.2 | 2024-11-27 |  |  | COMPLETE IN MILLING | 33 | 33 | 0 |  | 100% | 2024-12-06
REL-FMG-55.1 | 2024-11-27 |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2024-12-06
REL-FMG-1.07_FIN-REV | 2024-12-09 |  |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-11-22
REL-FMG-IS-MOCKUP | 2024-12-10 |  |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2024-12-20
REL-FMG-STS-3.04 | 2024-12-10 |  |  | COMPLETE IN MILLING | 86 | 86 | 0 |  | 100% | 2025-01-17 | MISSING 629 [5] FROM CORT
REL-FMG-STS-13.03 | 2024-12-10 |  |  | COMPLETE IN MILLING | 78 | 78 | 0 |  | 100% | 2025-01-10 | SITE
REL-FMG-58.1 | 2024-12-10 |  |  | COMPLETE IN MILLING | 25 | 25 | 0 |  | 100% | 2025-01-24
REL-FMG-TYP-PARTS-BULK-BATCH3 | 2024-12-10 | FOAM |  | COMPLETE IN MILLING | 2800 | 2800 | 0 |  | 100% | 2025-01-24
REL-FMG-EMB-EXTRA | 2024-12-10 |  |  | COMPLETE IN MILLING | 136 | 136 | 0 |  | 100% | 2025-01-10 | SITE
REL-FMG-3.03 [18 Units] | 2024-12-10 | 18 |  | COMPLETE IN MILLING | 1026 | 1026 | 0 |  | 100% | 2025-01-24 | MISSING 1480 [20], 1481 [20] FROM CORT
REL-FMG-3.13 [2 Units] | 2024-12-10 | 2 |  | COMPLETE IN MILLING | 58 | 58 | 0 |  | 100% | 2025-01-24 | MISSING 1480 [2], 1481 [2] FROM CORT
REL-FMG-3.04 [26 Units] | 2024-12-10 | 26 |  | WAITING ON MATERIAL | 1561 | 1561 | 0 |  | 100% | 2025-01-24 | MISSING 1480 [27], 1481 [27] FROM CORT
REL-FMG-11.01 [19 Units] | 2024-12-10 | 19 |  | COMPLETE IN MILLING | 920 | 920 | 0 |  | 100% | 2025-01-17
REL-FMG-11.01-FINS | 2024-12-10 |  |  | COMPLETE IN MILLING | 774 | 774 | 0 |  | 100% | 2025-01-17
REL-FMG-11.01-FINS-BATCH2 | 2024-12-10 |  |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2025-01-17
REL-FMG-1.17 | 2024-12-16 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-12-17
REL-FMG-11.02 [45 Units] | 2024-12-17 | 45 |  | COMPLETE IN MILLING | 2208 | 2208 | 0 |  | 100% | 2025-01-17 | MISSING S0233 [173], S0310 [129]
REL-FMG-11.02-FINS | 2024-12-17 |  |  | COMPLETE IN MILLING | 1680 | 1680 | 0 |  | 100% | 2024-01-17
FMG-EWA6-TEST | 2024-12-18 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-12-26
REL-FMG-EMBED-SHORT-ORDER | 2024-12-23 |  |  | COMPLETE IN MILLING | 340 | 340 | 0 |  | 100% | 2025-01-10 | SITE
REL-FMG-STS-1.90 | 2024-12-23 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-01-01 | SITE
REL-FMG-20.01 | 2024-12-23 |  |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2025-01-10 | SITE
REL-FMG-38.3 | 2024-12-23 |  |  | COMPLETE IN MILLING | 233 | 233 | 0 |  | 100% | 2025-01-10 | SITE
REL-FMG-1.92 | 2024-12-23 |  |  | COMPLETE IN MILLING | 379 | 379 | 0 |  | 100% | 2024-12-31 | SITE
REL-FMG-11.03 [19 Units] | 2025-01-03 | 19 |  | COMPLETE IN MILLING | 1026 | 1026 | 0 |  | 100% | 2025-01-24
REL-FMG-11.03-FINS | 2025-01-03 |  |  | COMPLETE IN MILLING | 501 | 501 | 0 |  | 100% | 2025-01-24
REL-FMG-11.04 [12 Units] | 2025-01-03 | 12 |  | COMPLETE IN MILLING | 805 | 805 | 0 |  | 100% | 2025-01-31 | MISSING 346 [24] FROM KM
REL-FMG-11.04-FINS | 2025-01-03 |  |  | COMPLETE IN MILLING | 413 | 413 | 0 |  | 100% | 2025-01-31
REL-FMG-11.05 [48 Units] | 2025-01-03 | 48 |  | COMPLETE IN MILLING | 2275 | 2275 | 0 |  | 100% | 2025-02-28 | MISSING 623 [48], 346 [96] FROM KM
REL-FMG-11.05-FINS | 2025-01-03 |  |  | COMPLETE IN MILLING | 1920 | 1920 | 0 |  | 100% | 2025-02-28
REL-FMG-8.01_1 | 2025-01-08 |  |  | COMPLETE IN MILLING | 639 | 639 | 0 |  | 100% | 2025-02-07 | SITE
REL-FMG-8.01_2 | 2025-01-29 |  |  | COMPLETE IN MILLING | 1329 | 1329 | 0 |  | 100% | 2025-02-28 | SITE MISSING 622 [654] FROM KM
REL-FMG-11.06-FINS | 2025-01-08 |  |  | COMPLETE IN MILLING | 790 | 790 | 0 |  | 100% | 2025-02-28
REL-FMG-11.07-FINS | 2025-01-08 |  |  | COMPLETE IN MILLING | 733 | 733 | 0 |  | 100% | 2025-02-07
REL-FMG-90.01 | 2025-01-10 |  |  | COMPLETE IN MILLING | 40 | 40 | 0 |  | 100% | 2025-01-24 | SITE
REL-FMG-99.01 | 2025-01-16 |  |  | WAITING ON POST PAINT | 24 | 36 | 12 | DEAN | 66.67% | 2025-03-07 | POST PAINTED FROM SPECTRUM/SITE | 12
REL-FMG-11.07 [17 Units] | 2025-01-20 | 17 |  | COMPLETE IN MILLING | 919 | 919 | 0 |  | 100% | 2025-02-07 | MISSING 346 [31] FROM KM
REL-FMG-11.06 [15 Units] | 2025-01-20 | 15 |  | COMPLETE IN MILLING | 739 | 739 | 0 |  | 100% | 2025-02-28 | MISSING 623 [21], 346 [30] FROM KM
REL-FMG-90.2 | 2025-01-22 |  |  | COMPLETE IN MILLING | 90 | 90 | 0 |  | 100% | 2025-01-23
REL-FMG-58.2 | 2025-01-24 |  |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2025-02-07
REL-FMG-13.01 [16 Units] | 2025-01-24 | 16 |  | COMPLETE IN MILLING | 518 | 518 | 0 |  | 100% | 2025-02-14 | MISSING 1480 [9], 1481 [9] FROM CORT
REL-FMG-STS-13.03-REVISION | 2025-01-30 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-07
REL-FMG-13.02 [20 Units] | 2025-01-30 | 20 |  | COMPLETE IN MILLING | 585 | 585 | 0 |  | 100% | 2025-03-21 | MISSING 1480 [11], 1481 [11] FROM CORT
REL-FMG-SITESHIMS | 2025-01-31 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-03-10 | SITE
REL-FMG-3.14 | 2025-01-31 | REVISED PARTS |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2025-02-07
REL-FMG-2.08 | 2025-02-05 |  |  | COMPLETE IN MILLING | 781 | 781 | 0 |  | 100% | 2025-02-21 | SITE
REL-FMG-STOREFRONT-2.99 | 2025-02-05 |  |  | COMPLETE IN MILLING | 374 | 374 | 0 |  | 100% | 2025-02-28 | SITE
REL-FMG-13.04 [16 Units] | 2025-02-05 | 16 |  | COMPLETE IN MILLING | 577 | 577 | 0 |  | 100% | 2025-02-21
REL-FMG-SST-4-SITE | 2025-02-06 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-10 | SITE
REL-FMG-ALU-4-SITE | 2025-02-06 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-02-10 | SITE
REL-FMG-STOREFRONT-2.11 | 2025-02-07 |  |  | COMPLETE IN MILLING | 374 | 374 | 0 |  | 100% | 2025-02-21 | SITE
REL-FMG-S1492-4-DEAN | 2025-02-11 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2025-02-12
REL-FMG-13.03 [26 Units] | 2025-02-11 | 26 |  | COMPLETE IN MILLING | 507 | 507 | 0 |  | 100% | 2025-02-28
3.04 STS-SST.S-REMAKE | 2025-02-17 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-17
REL-FMG-90.03-FIELDFIX | 2025-02-20 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-25 | SITE
REL-FMG-STOREFRONT-2.12-PRIORITY2 | 2025-02-20 |  |  | COMPLETE IN MILLING | 930 | 930 | 0 |  | 100% | 2025-03-21 | SITE
REL-FMG-STOREFRONT-2.13-PRIORITY1&2 | 2025-02-20 |  |  | COMPLETE IN MILLING | 1298 | 1298 | 0 |  | 100% | 2025-03-14 | SITE
REL-FMG-S1492-4-DEAN-AGAIN | 2025-03-03 |  |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2025-03-03
REL-FMG-13.03-REV | 2025-03-03 |  |  | COMPLETE IN MILLING | 46 | 46 | 0 |  | 100% | 2025-03-03
REL-FMG-TYLER-FIELDFIX | 2025-03-03 |  |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2025-03-04 | SITE
REL-FMG-2.12-PRIORITY-3&4 | 2025-03-03 |  |  | COMPLETE IN MILLING | 928 | 928 | 0 |  | 100% | 2025-03-21 | SITE
REL-FMG-2.13-PRIORITY-3&4 | 2025-03-03 |  |  | COMPLETE IN MILLING | 646 | 646 | 0 |  | 100% | 2025-03-21 | SITE
REL-FMG-MISSING-STL | 2025-03-07 |  |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2025-03-07 | SITE
REL-FMG-13.01-MISSING-GA-1302-28 | 2025-03-07 |  |  | COMPLETE IN MILLING | 15 | 15 | 0 |  | 100% | 2025-03-12
REL-FMG-30.01 | 2025-03-10 |  |  | COMPLETE IN MILLING | 1659 | 1659 | 0 |  | 100% | 2025-03-28
REL-FMG-30.11 | 2025-03-17 |  |  | COMPLETE IN MILLING | 78 | 78 | 0 |  | 100% | 2025-03-28 | RELEASED 3/17 -SHEET SIZE CONFLICT/TO MASTERCRAFT
REL-FMG-38.5 | 2025-03-17 |  |  | COMPLETE IN MILLING | 126 | 126 | 0 |  | 100% | 2025-03-21 | SITE
REL-FMG-30.02 | 2025-03-17 |  |  | COMPLETE IN MILLING | 1350 | 1350 | 0 |  | 100% | 2025-03-28 | MISSING 14GA ALU SHEETS
REL-FMG-21.11 | 2025-03-18 |  |  | COMPLETE IN MILLING | 265 | 265 | 0 |  | 100% | 2025-04-11 | MISSING 3X7X1/4 [93]
REL-FMG-21.01 | 2025-03-18 |  |  | WAITING ON POST PAINT | 937 | 1005 | 68 | DEAN | 93.23% | 2025-05-02 | NEEDS TO GO TO PAINT MISSING 3X7X1/4 [134]
REL-FMG-MATTS-SHIMS | 2025-03-18 |  |  | COMPLETE IN MILLING | 181 | 181 | 0 |  | 100% | 2025-03-21 | SITE
REL-FMG-30.12 | 2025-03-19 |  |  | COMPLETE IN MILLING | 64 | 64 | 0 |  | 100% | 2025-03-28 | NEEDS TO GO TO PAINT
REL-FMG-30.13 | 2025-03-19 |  |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2025-03-28 | NEEDS TO GO TO PAINT
REL-FMG-30.14 | 2025-03-19 |  |  | COMPLETE IN MILLING | 60 | 60 | 0 |  | 100% | 2025-03-28 | NEEDS TO GO TO PAINT
REL-FMG-STS11.05-REMAKES | 2025-03-19 |  |  | COMPLETE IN MILLING | 43 | 43 | 0 |  | 100% | 2025-03-21 | SITE
REL-FMG-38.6 | 2025-03-20 |  |  | COMPLETE IN MILLING | 26 | 26 | 0 |  | 100% | 2025-03-24 | SITE
REL-FMG-4.11 | 2025-03-20 |  |  | COMPLETE IN MILLING | 180 | 180 | 0 |  | 100% | 2025-04-04 | NEED REVISED INFO ON SHEET SIZE SITE
REL-FMG-40.90 | 2025-03-20 |  |  | COMPLETE IN MILLING | 200 | 200 | 0 |  | 100% | 2025-04-04 | SITE
REL-FMG-40.91 | 2025-03-20 |  |  | COMPLETE IN MILLING | 420 | 420 | 0 |  | 100% | 2025-04-04 | SITE
REL-FMG-40.92 | 2025-03-20 |  |  | COMPLETE IN MILLING | 480 | 480 | 0 |  | 100% | 2025-04-04 | SITE
REL-FMG-90.04 | 2025-03-21 |  |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2025-03-28 | SITE
REL-FMG-30.03 | 2025-03-31 |  |  | COMPLETE IN MILLING | 1227 | 1227 | 0 |  | 100% | 2025-04-11 | SITE
REL-FMG-30.04 | 2025-03-31 |  |  | COMPLETE IN MILLING | 1327 | 1327 | 0 |  | 100% | 2025-04-18 | SITE
REL-FMG-1.91 | 2025-03-31 |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2025-04-11 | SITE
REL-FMG-40.01 | 2025-03-31 |  |  | IN PROGRESS | 1766 | 1835 | 69 | DEAN | 96.24% | 2025-04-25 | NEED REVISED INFO MISSING ALU-S0224 [166] SITE
REL-FMG-21.02 | 2025-04-03 |  |  | WAITING ON POST PAINT | 357 | 393 | 36 | DEAN | 90.84% | 2025-05-16 | MISSING ALU-S0224 [10] SITE
REL-FMG-21.12 | 2025-04-03 |  |  | COMPLETE IN MILLING | 144 | 144 | 0 |  | 100% | 2025-05-02 | SITE
REL-FMG-12.12 | 2025-04-04 |  |  | IN PROGRESS | 1419 | 1444 | 25 | DEAN | 98.27% | 2025-05-02 | SITE
REL-FMG-12.11 | 2025-04-07 |  |  | IN PROGRESS | 931 | 961 | 30 | DEAN | 96.88% | 2025-05-09 | SITE
REL-FMG-40.02 | 2025-04-07 |  |  | IN PROGRESS | 925 | 1194 | 269 | ALL SHOPS | 77.47% | 2025-05-09 | MISSING 622 [148] FROM KM MISSING ALU-S0224 [114] SITE
REL-FMG-Q01 | 2025-04-07 |  |  | COMPLETE IN MILLING | 7 | 7 | 0 |  | 100% | 2025-04-16 | SITE
REL-FMG-4.11-REV | 2025-04-09 |  |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2025-04-18 | SITE
REL-FMG-20.01 | 2025-04-09 |  |  | IN PROGRESS | 1082 | 3714 | 2632 | ALL SHOPS | 29.13% | 2025-05-09 | SITE
REL-FMG-40.11 | 2025-04-14 |  |  | COMPLETE IN MILLING | 36 | 36 | 0 |  | 100% | 2025-05-02 | SITE
REL-FMG-40.12 | 2025-04-14 |  |  | COMPLETE IN MILLING | 26 | 26 | 0 |  | 100% | 2025-05-02 | SITE
REL-FMG-40.13 | 2025-04-14 |  |  | COMPLETE IN MILLING | 13 | 13 | 0 |  | 100% | 2025-05-02 | SITE
REL-FMG-40.14 | 2025-04-14 |  |  | COMPLETE IN MILLING | 34 | 34 | 0 |  | 100% | 2025-05-02 | SITE
REL-FMG-20.04 | 2025-04-14 |  |  | IN PROGRESS | 618 | 2604 | 1986 | ALL SHOPS | 23.73% | 2025-05-16 | SITE
REL-FMG-20.14 | 2025-04-14 |  |  | NOT IN PROGRESS | 0 | 547 | 547 | ALL SHOPS | 0% | 2025-05-16 | MISSING ALU-S0254 [68] SITE
FMG-SITESHIMS | 2025-04-14 |  |  | NOT IN PROGRESS | 0 | 500 | 500 | DEAN | 0% | 2025-05-18 | SITE
FMG-CHAIRSHIM-4SITE | 2025-04-15 |  |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2025-05-18 | SITE
12x12-MILL-ALU-SAMPLES4PAINT | 2025-04-16 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2025-05-25 | SITE
REL-FMG-HOT-SITE-EMBEDS | 2025-04-17 |  |  | COMPLETE IN MILLING | 104 | 104 | 0 |  | 100% | 2025-04-18 | SITE
REL-FMG-90.06 | 2025-04-18 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-04-21 | SITE
HOT-SSBRACKETS | 2025-04-18 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-04-18 | SITE
REL-FMG-40.03 | 2025-04-21 |  |  | IN PROGRESS | 73 | 1287 | 1214 | ALL SHOPS | 5.672% | 2025-05-23 | MISSING 622 [170] FROM KM SITE
REL-FMG-90.07 | 2025-04-21 |  |  | NOT IN PROGRESS | 0 | 17 | 17 | ALL SHOPS | 0% | 2025-05-23 | MISSING 622 [6] FROM KM SITE
REL-FMG-90.08 | 2025-04-21 |  |  | IN PROGRESS | 3 | 17 | 14 | DEAN | 17.65% | 2025-05-23 | SITE
REL-FMG-40.04 | 2025-04-23 |  |  | IN PROGRESS | 74 | 1432 | 1358 | ALL SHOPS | 5.168% | 2025-05-23 | SITE
REL-FMG-20.02 | 2025-04-24 |  |  | IN PROGRESS | 276 | 705 | 429 | ALL SHOPS | 39.15% | 2025-05-16 | SITE
171 |  | 619 | 0 |  | 98211 | 107417 | 9206 |  | 91.43%

## 660 (hidden)
660 LEFT TO FABRICATE FOR 707
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
LVL 11 TERRACE DOORS | 2024-03-15 |  |  | COMPLETE IN MILLING | 47 | 47 | 0 |  | 100% | POST PAINT 3/29/24 REMAINING REL. 4/19/24 | MISSING 1077 [3], 411 [1], 1076 [2] FROM KM
LVL 10 TERRACE DOORS | 2024-03-15 |  |  | COMPLETE IN MILLING | 340 | 340 | 0 |  | 100% | POST PAINT 3/29/24 REMAINING REL. 4/19/24
TERRACE DOORS THRESHOLDS | 2024-03-18 |  |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2024-04-19 | PART GOING TO LINO FOR FAB
REL-660TD-03 [MAG LOCK + MULLION COVERS] | 7/3/24 7/11/24 |  |  | COMPLETE IN MILLING | 142 | 142 | 0 |  | 100% | 2024-07-26 | 84 ADDED PARTS RELEASED 7/11/24
4 |  | 0 | 0 |  | 535 | 535 | 0 |  | 100%

## SOUTH STATION
SOUTH STATION LEFT TO FABRICATE
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
South Station Missing Parts for release 65 | 2024-04-24 | BPN |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-04-25
BSS-SHOP-REL065-01 | 2024-04-29 | MISSING PARTS |  | COMPLETE IN MILLING | 137 | 137 | 0 |  | 100% | 2024-05-10 | MISSING STRUTTED MATERIAL
BSS-SHOP-REL065-02 | 5/3/24 5/6/24 | SLEEVE BLOCKS FPN BPN |  | COMPLETE IN MILLING | 395 | 395 | 0 |  | 100% | 5/10/24 5/10/24 5/10/24 | SLEEVE BLOCKS COMPLETE FPN IN PROGRESS BPN WAITING ON INFO
BSS-SHOP-REL065-03 | 2024-05-07 | MISSING PARTS |  | COMPLETE IN MILLING | 451 | 451 | 0 |  | 100% | 2024-05-10 | MISSING STRUTTED MATERIAL
692-H6101-02 REMAKE | 2024-05-08 | REMAKE |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-05-10
BSS-SHOP-REL065-04 (Missing) | 2024-05-14 | MISSING PARTS |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-05-17
BSS-SHOP-REL065-05 | 2024-05-15 | MISSING PARTS |  | COMPLETE IN MILLING | 21 | 21 | 0 |  | 100% | 2024-05-17 | RELEASED PARTS 5/15/24 RELEASED PARTS 5/16/24 RELEASED PARTS 5/16/24
BSS-SHOP-REL065-06 | 5/21/24 5/21/24 5/28/24 | MISSING PARTS MISSING PARTS MISSING PARTS |  | COMPLETE IN MILLING | 51 | 51 | 0 |  | 100% | 2024-05-24 | MISSING STRUTTED MATERIAL
BSS-SHOP-REL065-07 | 2024-05-31 | MISSING PARTS |  | COMPLETE IN MILLING | 37 | 37 | 0 |  | 100% | 2024-05-31
REL- L35 CORNER ANCHORS | 2024-06-03 | ANCHORS |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-06-07 | SITE
REL-BSS-E080 | 2024-06-03 | BSH PARTS |  | COMPLETE IN MILLING | 400 | 400 | 0 |  | 100% | 2024-06-07 | SITE
REL-BSS-E170 (LVL 38-50) | 6/4/24 6/13/24 | ERECTION ANGLES ERECTION ANGLES LVL39 ERECTION ANGLES LVL 40 ERECTION ANGLES LVL 41 ERECTION ANGLES LVL 42 ERECTION ANGLES LVL 43 ERECTION ANGLES LVL 44 ERECTION ANGLES LVL 45 ERECTION ANGLES LVL 46 ERECTION ANGLES LVL 47 ERECTION ANGLES LVL 48 ERECTION ANGLES LVL 49 ERECTION ANGLES LVL 50 |  | COMPLETE IN MILLING | 5851 | 5851 | 0 |  | 100% | 6/14/24 7/12/24 7/19/24 7/26/24 8/2/24 8/9/24 8/16/24 8/23/24 8/30/24 9/6/24 9/13/24 9/20/24 9/27/24 | SITE
BSS-SHOP-REL070A-01 | 2024-06-04 | FPN REMAKE |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-06-07
REL-692-E265 - ALUM. SHIMS | 2024-06-10 | SHIMS |  | COMPLETE IN MILLING | 1200 | 1200 | 0 |  | 100% | 2024-06-14 | SITE
REL-BSS-E172 (STEEL ERECTION ANGLES) | 2024-06-17 | ERECTION ANGLES |  | COMPLETE IN MILLING | 600 | 600 | 0 |  | 100% | 2024-07-12 | SITE
REL-BSS-E340 (Release 40 Silver Dollar) | 2024-06-17 | SITE PARTS |  | COMPLETE IN MILLING | 407 | 407 | 0 |  | 100% | 2024-08-02 | 174 POST PAINT PARTS READY FOR VALLEY 7/8/24
REL-BSS-SHOP-REL070A-02 | 2024-06-19 | MISSING PARTS |  | COMPLETE IN MILLING | 884 | 884 | 0 |  | 100% | 2024-07-12 | CON'T TO ADD PARTS TO THIS RELEASE
REL-BSS-SHOP-REL070B | 2024-06-19 | 327 |  | COMPLETE IN MILLING | 3008 | 3008 | 0 |  | 100% | 2024-07-12
REL-BSS-SHOP-REL070B-1 | 2024-06-19 | 18 |  | COMPLETE IN MILLING | 126 | 126 | 0 |  | 100% | 2024-07-12
REL-BSS-E174 - STEEL ANCHORS TYPE E, 1A, 7 & 9 | 2024-06-24 | ANCHORS |  | COMPLETE IN MILLING | 1730 | 1730 | 0 |  | 100% | 2024-07-19 | SITE
REL-BSS- L36 STARTER SILL FIELD FIX | 2024-06-27 | STARTER |  | COMPLETE IN MILLING | 325 | 325 | 0 |  | 100% | 2024-07-05 | SITE
REL-BSS-E175 (Steel HS Shims) [To be HDG] - Shims for LVL 36-49 Wind wall and balconies | 2024-07-02 | SHIMS |  | COMPLETE IN MILLING | 3000 | 3000 | 0 |  | 100% | 2024-07-26 | REC'D MATERIAL 7/18/24/SITE
REL-BSS- E170-6 - L36 DOOR BRACKETS | 2024-07-02 | BRACKETS |  | COMPLETE IN MILLING | 308 | 308 | 0 |  | 100% | 2024-07-12 | SITE
REL-BSS-R070C [327 Units] | 2024-07-10 | 327 |  | COMPLETE IN MILLING | 3654 | 3654 | 0 |  | 100% | 2024-08-02
REL-BSS-L35 PANEL POST INSTALLED EMBED | 2024-07-11 | EMBEDS |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-08-09
REL-BSS-E301 - LIFTING HOLE COVER PLATE | 2024-07-11 | PLATES |  | COMPLETE IN MILLING | 8000 | 8000 | 0 |  | 100% | 2024-07-26
REL-BSS-692-E075-36-Terrace Curb Flashing | 2024-07-16 | FLASHING |  | COMPLETE IN MILLING | 57 | 57 | 0 |  | 100% | 2024-08-09 | SITE
REL-BSS-E001 | 2024-07-16 | ALU PARTS |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-08-09 | SITE
REL-BSS- 230 -L11 GALV FLASHING | 2024-07-17 | FLASHING |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2024-07-19 | SITE
REL-BSS-R070C-1 [18 Units] | 2024-07-22 | 18 |  | COMPLETE IN MILLING | 131 | 131 | 0 |  | 100% | 2024-08-02
REL-BSS- 320 - Coping R030 | 2024-07-30 | R030S |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-08-09
REL-BSS-L11 MISSING EMBED | 2024-07-30 | EMBEDS |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2024-08-09 | SITE
REL-BSS-H EMBED ERECTION ANGLES | 2024-07-30 | ANGLESS |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2024-08-09 | SITE
REL-BSS- E045 – WALKWAY | 2024-08-01 | WALKWAYS |  | COMPLETE IN MILLING | 3163 | 3163 | 0 |  | 100% | 2024-08-30 | SITE
REL-BSS-R070D [436 Units] | 2024-08-06 | 436 |  | COMPLETE IN MILLING | 8092 | 8092 | 0 |  | 100% | 2024-08-30
REL-BSS-R070D-1 [24 Units] | 2024-08-06 | 24 |  | COMPLETE IN MILLING | 252 | 252 | 0 |  | 100% | 2024-09-06
REL-BSS- E420 COPING SLEEVES | 2024-08-07 | SLEEVESS |  | COMPLETE IN MILLING | 15 | 15 | 0 |  | 100% | 2024-09-06
REL-BSS-E180 (Anchors 51+) | 2024-08-12 | ANCHORS |  | COMPLETE IN MILLING | 3233 | 3233 | 0 |  | 100% | 2024-10-04 | SITE
REL-BSS-R060 - Damaged panels [12 PNLS] | 2024-08-12 | 12 |  | COMPLETE IN MILLING | 143 | 143 | 0 |  | 100% | 2024-09-20
REL-BSS-R075A | 2024-08-12 | 13 |  | COMPLETE IN MILLING | 929 | 929 | 0 |  | 100% | 2024-09-20
REL-BSS-R075B | 2024-08-21 |  |  | COMPLETE IN MILLING | 1965 | 1965 | 0 |  | 100% | 2024-10-04 | SITE
REL -070C - LVL 45 | 2024-08-26 | LVL 450 |  | COMPLETE IN MILLING | 31 | 31 | 0 |  | 100% | 2024-08-30
REL-BSS-E350 - VOID PANEL | 2024-08-26 | PANELS |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-09-06
REL-BSS-E150-L11 DOOR BRACKET | 2024-08-27 | BRACKETS |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2024-09-27 | SITE
REL-BSS- FF1005 - ERECTION ANGLE | 2024-09-03 | ANGLES |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-09-06
REL-BSS-R010 [Shuttle lobby 19 Units] | 2024-09-06 | 19 |  | COMPLETE IN MILLING | 1641 | 1641 | 0 |  | 100% | 2024-09-27
REL-BSS-R080A [200 Units LVL 50 + 51] | 2024-09-06 | 200 |  | COMPLETE IN MILLING | 4144 | 4144 | 0 |  | 100% | 2024-09-27
REL-BSS-370 - ACOUSTIC GALV FLASHING LEVEL 37 - 49 | 2024-09-08 | FLASHING |  | COMPLETE IN MILLING | 3843 | 3843 | 0 |  | 100% | 2024-09-20 | SITE
REL- BSS - L50 STARTER SILLS & DOOR WIND LOAD BRACKETS | 2024-09-20 | STARTER |  | COMPLETE IN MILLING | 1763 | 1763 | 0 |  | 100% | 2024-09-27 | SITE
REL-692-E080-50-Terrace Curb Flashing | 2024-09-20 | Flashing |  | COMPLETE IN MILLING | 54 | 54 | 0 |  | 100% | 2024-09-27 | SITE
REL-BSS-R080B-52 [120 UNITS] | 2024-09-25 | 120 |  | COMPLETE IN MILLING | 593 | 593 | 0 |  | 100% | 2024-10-11
REL-BSS-R080B-53 [120 UNITS] | 2024-09-30 | 120 |  | COMPLETE IN MILLING | 552 | 552 | 0 |  | 100% | 2024-10-18
REL-BSS-R080B-54 [120 UNITS] | 2024-09-30 | 120 |  | COMPLETE IN MILLING | 866 | 866 | 0 |  | 100% | 2024-10-25
REL-075-L36 WINDWALL SHOES EXCLUDING HOIST BAY | 2024-10-01 | SHOES |  | COMPLETE IN MILLING | 784 | 784 | 0 |  | 100% |  | SITE
REL-095A-L36 AIRWAY SHOES | 2024-10-03 | SHOES |  | COMPLETE IN MILLING | 176 | 176 | 0 |  | 100% |  | SITE
REL-075-L36 WINDWALL SHOES HOIST BAY | 2024-10-03 | SHOES |  | COMPLETE IN MILLING | 86 | 86 | 0 |  | 100% |  | SITE
REL-L37 SILL & SLAB TRIM MOCKUP | 2024-10-03 | TRIMS |  | COMPLETE IN MILLING | 45 | 45 | 0 |  | 100% | 2024-10-11 | SITE
REL-L36 WW SHOE TEMPLATE | 2024-10-03 | SHOES |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2024-10-04 | SITE
REL-085-L50 WINDWALL SHOES | 2024-10-03 | SHOES |  | COMPLETE IN MILLING | 1054 | 1054 | 0 |  | 100% |  | SITE
REL-SOUTH BALCONY CORNER FF | 2024-10-04 | TRIMS |  | COMPLETE IN MILLING | 106 | 106 | 0 |  | 100% | 2024-10-18 | SITE
REL-L37 TO 39 SILL & SLAB TRIMS | 2024-10-10 | TRIMS |  | COMPLETE IN MILLING | 1985 | 1985 | 0 |  | 100% | 2024-11-01 | LVL 39 BSH PARTS [301] SCRAPPED
REL-BSS-L50.1 STARTER SILL ADDITIONAL ACCESARIES | 2024-10-17 | STARTER |  | COMPLETE IN MILLING | 119 | 119 | 0 |  | 100% | 2024-11-01
REL-BSS-50 STICK BUILT PANELS | 2024-10-21 | STICK BUILT |  | COMPLETE IN MILLING | 449 | 449 | 0 |  | 100% | 2024-11-15 | NEED MATERIAL 4X8X1/4 [3]
REL-BSS-35 PANELS, STARTER SILL & Accessories | 2024-10-21 | STARTER |  | COMPLETE IN MILLING | 320 | 320 | 0 |  | 100% | 2024-11-15
REL-BSS-080-L52 PHERIPHERY FLASHING | 10/22/2024 1/7/2025 | FLASHING MORE FLASHING |  | COMPLETE IN MILLING | 254 | 254 | 0 |  | 100% | 11/8/2024 1/14/2025 | SITE
REL-BSS-050-WW SHOE TEMPLATES | 2024-10-22 | SHOES |  | COMPLETE IN MILLING | 94 | 94 | 0 |  | 100% | 2024-11-08 | SITE
REL-BSS-L36 & 50 STEEL SHOE LIFTING PLATE | 2024-10-22 | SHOES |  | COMPLETE IN MILLING | 430 | 430 | 0 |  | 100% | 2024-11-08 | SITE
REL-BSS-L35 GALV BACKPANS | 2024-10-23 | BPN |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-10-25
REL-BSS-090 [36 Units] | 2024-10-24 | 39 |  | COMPLETE IN MILLING | 2359 | 2359 | 0 |  | 100% | 2024-11-08
REL- BSS -080D-L50STARTER SILL SHIMS | 2024-10-28 | SHIMS |  | COMPLETE IN MILLING | 1100 | 1100 | 0 |  | 100% | 1931-11-01 | SITE
REL-080-L50 & 51 ACOUSTIC FLASHING | 2024-10-28 | FLASHING |  | COMPLETE IN MILLING | 217 | 217 | 0 |  | 100% | 2024-11-08 | SITE
REL-BSS-WIND WALL SHOES SHIMS | 2024-10-29 | SHIMS |  | COMPLETE IN MILLING | 4130 | 4130 | 0 |  | 100% | 2024-11-08 | NEED MATERIAL SHEETS
REL- Bulletin 131 PICTURE FRAME | 2024-10-29 |  |  | COMPLETE IN MILLING | 26 | 26 | 0 |  | 100% | 2024-11-15
REL-035C-WINDLOAD BRACKETS | 2024-10-29 | BRACKETS |  | COMPLETE IN MILLING | 78 | 78 | 0 |  | 100% | 2024-11-15 | SITE
REL-BSS-080-L52-54 SHIMS | 2024-10-29 | SHIMS |  | COMPLETE IN MILLING | 105 | 105 | 0 |  | 100% | 2024-11-15 | SITE
BSS-SHOP-REL070A | 6/5/24 10/31/24 | MISSING PARTS |  | COMPLETE IN MILLING | 1137 | 1137 | 0 |  | 100% | 6/14/24 11/15/24 | 548PCS COMPLETED ADDED INFO RELEASED 10/31/24
REL-BSS-R075C | 2024-10-31 |  |  | COMPLETE IN MILLING | 954 | 954 | 0 |  | 100% | 2024-11-29 | SITE
REL-BSS-R075C-02 | 2024-10-31 |  |  | COMPLETE IN MILLING | 174 | 174 | 0 |  | 100% | 2024-11-29 | SITE
REL-BSS-R075A-02 | 2024-10-31 |  |  | COMPLETE IN MILLING | 234 | 234 | 0 |  | 100% | 2024-11-15 | SITE
REL-BSS-080-L52-54 SHIMS | 2024-11-01 | SHIMS |  | COMPLETE IN MILLING | 105 | 105 | 0 |  | 100% | 2024-11-15 | SITE
REL-BSS- L39 TO 49 SILL & SLAB TRIMS | 2024-11-01 | TRIMS |  | COMPLETE IN MILLING | 8030 | 8030 | 0 |  | 100% | 2025-01-17
REL-BSS-R20-TRIMS | 2024-11-04 | TRIMS |  | COMPLETE IN MILLING | 72 | 72 | 0 |  | 100% | 2024-11-15
REL-BSS-L26 SILL AND SLAB TRIMS | 2024-11-06 | TRIMS |  | COMPLETE IN MILLING | 755 | 755 | 0 |  | 100% | 2024-11-15
REL-BSS-R090-BRACKETS | 2024-11-06 | BRACKETS |  | COMPLETE IN MILLING | 1620 | 1620 | 0 |  | 100% | 2024-11-15 | SITE
REL-BSS-L13-35 SILL AND SLAB TRIMS EXCLUDING L26 | 2024-11-11 | TRIMS |  | COMPLETE IN MILLING | 10729 | 10729 | 0 |  | 100% | 2024-01-17 | MISSING 11766 [133] FROM METRA
REL-BSS-L12 SILL & SLAB TRIMS | 2024-11-13 | TRIMS |  | COMPLETE IN MILLING | 304 | 304 | 0 |  | 100% | 2024-11-29 | SITE
REL-BSS-90H [10 Units] | 2024-11-18 | 10 |  | COMPLETE IN MILLING | 250 | 250 | 0 |  | 100% | 2024-12-06
REL-BSS-R080C PANELS, STRUCTURE AND ACCESSORIES | 2024-11-18 | 4 |  | COMPLETE IN MILLING | 271 | 271 | 0 |  | 100% | 2024-12-06
REL-BSS-L37-49 IN-CORNERS SLEEVES | 2024-11-19 | SLEEVESS |  | COMPLETE IN MILLING | 152 | 152 | 0 |  | 100% | 2024-11-29 | SITE
REL-BSS-095B-EXTERIOR SKIRT PANEL | 2024-11-19 | TRIMS |  | COMPLETE IN MILLING | 78 | 78 | 0 |  | 100% | 2024-12-20 | SITE
REL-BSS-095B-INTERIOR SKIRT PANEL | 2024-11-19 | TRIMS |  | COMPLETE IN MILLING | 78 | 78 | 0 |  | 100% | 2024-12-20 | SITE
REL-BSS-R050 JAMB FORMING | 2024-11-19 |  |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2024-12-20 | SITE
REL-BSS-L50 SILL & SLAB TRIMS | 2024-11-19 | TRIMS |  | COMPLETE IN MILLING | 336 | 336 | 0 |  | 100% | 2024-12-13 | SITE
REL-BSS-L35 ANGLE & ACC AT FAKE STACK JOINT | 2024-11-21 |  |  | COMPLETE IN MILLING | 40 | 40 | 0 |  | 100% | 2024-12-20 | SITE
REL-BSS-L51 SILL & SLAB TRIMS | 2024-11-21 | TRIMS |  | COMPLETE IN MILLING | 299 | 299 | 0 |  | 100% | 2024-12-13 | SITE
REL-BSS-R085A-EXTERIOR COPING | 2024-11-21 | COPING |  | COMPLETE IN MILLING | 226 | 226 | 0 |  | 100% | 2024-12-13 | SITE
REL-BSS-R09-SILL TRIMS PARTIAL | 2024-11-21 | TRIMS |  | COMPLETE IN MILLING | 103 | 103 | 0 |  | 100% | 2024-12-13 | SITE
REL-BSS-R085B-INTERIOR SKIRT PANEL | 2024-11-21 | SKIRT |  | COMPLETE IN MILLING | 171 | 171 | 0 |  | 100% | 2024-12-20 | SITE
REL-BSS-L36 MISSING SUNSHADES | 2024-11-26 |  |  | COMPLETE IN MILLING | 145 | 145 | 0 |  | 100% | 2024-12-06 | SITE
REL-BSS-R09-SILL TRIMS PARTIAL 2 | 2024-12-10 |  |  | COMPLETE IN MILLING | 294 | 294 | 0 |  | 100% | 2024-12-20 | MISSING 11766 [60] FROM METRA
REL-BSS-L52 SILL & SLAB TRIMS | 2024-12-10 |  |  | COMPLETE IN MILLING | 480 | 480 | 0 |  | 100% | 2024-01-03 | MISSING 11766 [120] FROM METRA
REL-BSS-R090B SKIRT PANELS | 2024-12-10 |  |  | COMPLETE IN MILLING | 1557 | 1557 | 0 |  | 100% | 2024-12-27 | PARTS TO PAINT 12/27/24
REL-BSS-R010H-FORMED ALUM. PANEL | 2024-12-10 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-12-27
REL-BSS-R080D BALCONY SITE MATERIALS | 2024-12-10 |  |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2024-12-27 | PARTS TO PAINT 12/27/24
REL-BSS-70E - SHOP [Hoist] | 2024-12-11 | 30 |  | COMPLETE IN MILLING | 135 | 135 | 0 |  | 100% | 2024-12-20
REL-BSS-R090-WINDLOAD BRACKET SHIM | 2024-12-11 |  |  | COMPLETE IN MILLING | 400 | 400 | 0 |  | 100% | 2024-12-13
REL-BSS-R30 TRIM | 2024-12-11 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-12-20
REL-BSS-010A-RESEDENTIAL ENATRANCE SITE INSTALLED TUBES | 2024-12-11 |  |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2024-12-20
REL-BSS-Site-01 - 75A Site Material | 2024-12-16 |  |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-12-18
REL-BSS-R090-DEADLOAD BRACKET SHIM | 2024-12-17 |  |  | COMPLETE IN MILLING | 204 | 204 | 0 |  | 100% | 2024-12-27
REL-BSS-R075B-02: L36-50 HANDRAIL FLASHING | 2024-12-17 |  |  | COMPLETE IN MILLING | 112 | 112 | 0 |  | 100% | 2024-12-27
REL-BSS-R030 END CLOSURE | 2024-12-18 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-12-27
REL-BSS-R030 COPING | 2024-12-18 |  |  | COMPLETE IN MILLING | 41 | 41 | 0 |  | 100% | 2024-01-10 | PARTS TO PAINT 12/27/24
REL-BSS-L36 DIVIDERS | 2024-12-19 |  |  | COMPLETE IN MILLING | 2854 | 2854 | 0 |  | 100% | 2025-01-17 | MISSING 0161 [1135] FROM VALLEY PARTS TO PAINT 12/27/24
REL-BSS- ADDITIONAL WIND WALL SHOES SHIMS | 2024-12-19 |  |  | COMPLETE IN MILLING | 2750 | 2750 | 0 |  | 100% | 2025-01-10
REL-BSS-R040-3401 COPING SUB ASSEMBLY | 2024-12-19 |  |  | ASSEMBLY IN 393 | 3 | 3 | 0 |  | 100% | 2025-01-24 | PARTS TO PAINT 12/27/24
REL-BSS-L50 DIVIDERS EAST WITH OUT STEEL | 2024-12-20 |  |  | COMPLETE IN MILLING | 742 | 742 | 0 |  | 100% | 2025-01-17 | PARTS TO PAINT 12/27/24 MISSING 0161 TUBES [378] FROM VALLEY
REL-BSS-L50 DIVIDERS WEST WITH OUT STEEL | 2025-01-02 |  |  | COMPLETE IN MILLING | 497 | 497 | 0 |  | 100% | 2025-01-17 | MISSING 0161 [252] FROM VALLEY PARTS TO PAINT 12/27/24
REL-BSS- L27 & ALL RESIDENTIAL FLOORS REGALZING MATERIAL | 2025-01-02 |  |  | COMPLETE IN MILLING | 518 | 518 | 0 |  | 100% | 2025-01-10
REL-BSS-FIELD-01 | 2025-01-02 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-01-17
REL-BSS-L11 SILL & SLAB TRIMS | 2025-01-02 |  |  | COMPLETE IN MILLING | 329 | 329 | 0 |  | 100% | 2025-01-17 | MISSING 11766 [67] FROM METRA
REL-BSS-L36 SILL & SLAB TRIMS | 2025-01-02 |  |  | COMPLETE IN MILLING | 409 | 409 | 0 |  | 100% | 2025-01-17 | MISSING 11766 [107] FROM METRA
REL-BSS-L12 CORNER SILL & SLAB TRIMS | 2025-01-07 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-01-17 | POST PAINT
REL-BSS-R010 BOTTOM FLASHING | 2025-01-07 |  |  | COMPLETE IN MILLING | 15 | 15 | 0 |  | 100% | 2025-01-24
REL-BSS-L09 SHADOW BOX | 2025-01-07 |  |  | COMPLETE IN MILLING | 114 | 114 | 0 |  | 100% | 2025-01-31
REL-BSS-L50 SHADOW BOX | 2025-01-08 |  |  | COMPLETE IN MILLING | 38 | 38 | 0 |  | 100% | 2025-01-15
REL-131 - DOUBLE DOOR WINDLOAD BRACKETS(CLIPS) | 2025-01-15 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-01-17
REL-060E- MISSING PANELS | 2025-01-21 | 4 |  | COMPLETE IN MILLING | 68 | 68 | 0 |  | 100% | 2025-01-24
REL-BSS-L36 STEEL DIVIDERS | 2025-01-24 |  |  | COMPLETE IN MILLING | 1038 | 1038 | 0 |  | 100% | 2025-02-07
REL-BSS-L50 EAST & WEST SLIDING DOOR FLASHING | 2025-01-28 |  |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2025-02-14
REL-BSS-L10 SILL & SLAB TRIMS | 2025-01-28 |  |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2025-02-14 | MISSING 11766 [40] FROM VALLEY MISSING TUBES [10]FROM YARDE [NEEDS POST PAINT]
REL-BSS-L50 STEEL DIVIDERS | 2025-01-28 |  |  | COMPLETE IN MILLING | 319 | 319 | 0 |  | 100% | 2025-02-14
REL-BSS-L37-50 SOUTH BALCONY GLASS RAIL WASHERS | 2025-01-29 |  |  | COMPLETE IN MILLING | 230 | 230 | 0 |  | 100% | 2025-02-14
REL-BSS-R060 - 2 HOIST PANELS | 2025-01-31 | 2 |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2025-02-07
REL-BSS-MISSING-POST-PAINT | 2025-02-05 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-02-10
REL-BSS-L37-50 SOUTH BALCONY RAILING SHOE SHIMS | 2025-02-06 |  |  | COMPLETE IN MILLING | 930 | 930 | 0 |  | 100% | 2025-02-14
REL-BSS-TOH-ESCUTCHEON PLATES | 2025-02-10 |  |  | COMPLETE IN MILLING | 96 | 96 | 0 |  | 100% | 2025-02-14
REL-BSS-R010 ACCESSORIES & CLADDING | 2025-02-10 |  |  | WAITING ON MATERIAL | 244 | 246 | 2 | JON | 99.19% | 2025-02-21 | MISSING CHANNEL
REL-BSS- COMMERCIAL FLOORS REGALZING MATERIAL | 2025-02-10 |  |  | COMPLETE IN MILLING | 1000 | 1000 | 0 |  | 100% | 2025-02-21
REL-BSS-L13-35 ADDITIONAL STOOL TRIMS | 2025-03-03 |  |  | WAITING ON MATERIAL | 150 | 296 | 146 | SEAN | 50.68% | 2025-03-14 | MISSING 11766 [146] FROM VALLEY
REL-BSS-R035 SILL TRIMS | 3/3/25 4/30/25 ADD ON |  |  | WAITING ON MATERIAL | 86 | 108 | 22 | ALL SHOPS | 79.63% | 2025-05-02 | MISSING 11766 [10] FROM VALLEY
REL-BSS-R090 REMAKE COPING | 2025-03-18 |  |  | POST PAINT | 82 | 98 | 16 | DEAN | 83.67% | 2025-04-25 | NEEDS TO GO TO PAINT
REL-BSS-L52 SILL TRIM REFABRICATED | 2025-03-19 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-03-28 | NEEDS TO GO TO PAINT
REL-BSS-L36 STOOL ANGLES ADD | 2025-03-19 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-03-28 | NEEDS TO GO TO PAINT
Site Request - A9800 | 2025-03-20 |  |  | COMPLETE IN MILLING | 15 | 15 | 0 |  | 100% | 2025-03-25 | SITE
REL-BSS-L36 SKIRT PANELS | 2025-03-27 |  |  | COMPLETE IN MILLING | 135 | 135 | 0 |  | 100% | 2025-04-11 | NEEDS TO GO TO PAINT
REL-BSS-FIRE DAMAGE PANELS UPDATED | 3/28/25 4/14/25 |  |  | WAITING ON MATERIAL | 502 | 512 | 10 | ALL SHOPS | 98.05% | 2025-04-25 | ADDED PARTS [35] AP MISSING 12274 [9], 12268 [1] FROM VALLEY
LVL36 Divider Close out | 2025-03-28 |  |  | COMPLETE IN MILLING | 86 | 86 | 0 |  | 100% | 2025-04-04 | NEED CHANNEL
REL-BSS-R75B MISSING PARTS | 2025-04-03 |  |  | COMPLETE IN MILLING | 25 | 25 | 0 |  | 100% | 2025-04-18 | NEEDS TO GO TO PAINT
BSS - Door Clips | 2025-04-15 |  |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2025-04-18
L36 & L50 - WW Galvy | 2025-04-15 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-18
REL-BSS-L13 VENT GLASS SETTING SHOES | 4/17/25 4/23/25 |  |  | COMPLETE IN MILLING | 52 | 52 | 0 |  | 100% | 2025-05-02 | ADDED PARTS [24] 4/23/25
REL-BSS-L12 SOFFIT BEND SHAPES | 2025-04-17 |  |  | COMPLETE IN MILLING | 20 | 20 | 0 |  | 100% | 2025-04-25
REL-BSS-L11 RIDER MULLION F5042 | 2025-04-17 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-04-25
REL-CRANE TIE | 2025-04-17 |  |  | COMPLETE IN MILLING | 39 | 39 | 0 |  | 100% | 2025-04-25
0
0
0
155 |  | 1843 | 0 |  | 119291 | 119487 | 196 |  | 99.84%

## FNB
FNB SITE MATERIAL
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
REL-FNB-SW-VESTIBULE-ANC | 2024-05-09 |  |  |  | 0 | 0 | 0 |  | #DIV/0! | 2024-05-31 | NOT NEEDED 6/17/24
REL-FNB-SE-VESTIBULE-ANC | 2024-05-09 |  |  |  | 0 | 0 | 0 |  | #DIV/0! | 2024-05-31 | NOT NEEDED 6/17/24
REL-FNB-NW-AIRSEAL | 2024-05-09 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-05-24 | SITE
REL-FNB-ADDL-PODIUM-ANC | 2024-05-28 | ANCHOR |  | COMPLETE IN MILLING | 5 | 5 | 0 |  | 100% | 2024-05-31 | SITE
REL-FNB-NE-SOFFIT-LOOSE-MATERIAL | 2024-05-28 |  |  |  | 0 | 0 | 0 |  | #DIV/0! | 2024-06-28 | NOT NEEDED 6/17/24
REL-FNB-NW-SOFFIT-LOOSE-MATERIAL | 2024-05-28 |  |  |  | 0 | 0 | 0 |  | #DIV/0! | 2024-06-28 | NOT NEEDED 6/17/24
REL-FNB-SE-SOFFIT-LOOSE-MATERIAL | 2024-05-28 |  |  |  | 0 | 0 | 0 |  | #DIV/0! | 2024-06-28 | NOT NEEDED 6/17/24
REL-FNB-SW-SOFFIT-LOOSE-MATERIAL | 2024-05-28 |  |  |  | 0 | 0 | 0 |  | #DIV/0! | 2024-06-28 | SITE
REL-FNB-NE-LVL3-GALV-AIRSEAL | 2024-06-06 |  |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100% | 2024-06-14 | SITE
REL-FNB-VESTIBULE-BASE-ANC | 2024-06-06 |  |  | COMPLETE IN MILLING | 40 | 40 | 0 |  | 100% | 2024-06-14 | SITE
REL-FNB-GLAZING-SADDLES | 2024-06-06 |  |  | COMPLETE IN MILLING | 600 | 600 | 0 |  | 100% | 2024-07-12 | SITE
REL-FNB-VESTIVULE-GALV | 2024-07-09 |  |  | COMPLETE IN MILLING | 27 | 27 | 0 |  | 100% | 2024-07-19 | SITE
REL-FNB-STICKBUILT-INTERIORWALL | 8/12/24 8/23/24 | PARTIALLY RELEASED REMAINING RELEASED |  | COMPLETE IN MILLING | 63 | 63 | 0 |  | 100% | 2024-08-27 | SITE
REL-FNB-FIRESTOPPING-PRESSWORK | 2024-09-03 |  |  | COMPLETE IN MILLING | 18 | 18 | 0 |  | 100% | 2024-09-13 | SITE
REL-FNB-CORNER-ANC-FIX | 2024-09-08 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2024-09-20 | SITE
REL-FNB-COPING-STRIPS | 2024-09-18 |  |  | COMPLETE IN MILLING | 190 | 190 | 0 |  | 100% | 2024-09-18 | SITE
REL-FNB-FLAT-ANCHOR-FIELDFIX | 2024-10-28 |  |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-11-15 | SITE
REL-FNB-LARSON-FIELD-FIXES2 | 2024-12-09 |  |  | COMPLETE IN MILLING | 11 | 11 | 0 |  | 100% | 2024-12-13 | SITE
REL-FNB-LARSON-FIELD-FIXES3 | 2024-12-20 |  |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 1/10//25 | SITE
REL-FNB-LARSON-FIELD-FIXES4 | 2024-12-20 |  |  | COMPLETE IN MILLING | 44 | 44 | 0 |  | 100% | 2025-01-10 | SITE
REL-FNB-LARSON-FIELD-FIXES6 | 2025-01-30 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-14 | SITE
REL-FNB-LARSON-FIELD-FIXES7 | 2025-02-03 |  |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2025-02-14 | SITE
REL-FNB-LARSON-FIELD-FIXES5 | 2025-02-21 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2025-03-07 | SITE
REL-FNB-08-POD-MULL-RECLAD | 2025-04-04 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-11 | SITE
24 |  |  |  |  | 1109 | 1109 | 0 |  | 100%

## PENN
PENN MED LEFT TO FABRICATE
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
BMU - FPN (401) [To Spectrum] | 2024-06-28 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-07-12 | POST PAINTED PARTS READY 7/11/24 SPECTRUM
REL-PMC-BMU | 2024-08-06 |  |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2024-08-23
REL-PMC-BMU_Addtional FPN Anchor | 2024-08-23 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-08-26
REL-PMG-GARAGE STEEL PARTS | 2024-09-23 |  |  | COMPLETE IN MILLING | 378 | 378 | 0 |  | 100% | 2024-10-11
REL-PMG-Post Paint BSH BULK | 2024-10-03 |  |  | COMPLETE IN MILLING | 603 | 603 | 0 |  | 100% | 2024-11-15
REL-PMG-Garage Additional Release | 2024-10-24 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2024-11-01
REL-PMG- samples | 2024-10-24 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-11-01
REL-PMG-Garage Misc Parts Release | 10/28/2024 1/10/2025 |  |  | COMPLETE IN MILLING | 479 | 479 | 0 |  | 100% | 11/15/2024 1/17/2025 | ADDITIONAL 50 TUBES RELEASED
REL-PMG-MIA-GARAGE-PARTS | 2024-12-09 |  |  | COMPLETE IN MILLING | 237 | 237 | 0 |  | 100%
REL-PMG-Shim Batch #1 (401) TO SITE | 2025-01-02 |  |  | COMPLETE IN MILLING | 200 | 200 | 0 |  | 100% | 2025-01-06
REL-PMG-Shim Batch #2 | 2025-01-02 |  |  | COMPLETE IN MILLING | 310 | 310 | 0 |  | 100% | 2025-01-06
REL-NEO-PMG-Additional Field Bracket | 2025-01-07 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-01-17
REL-PMG-Additional Site Shim Batch #3.4.5 | 2025-01-10 |  |  | COMPLETE IN MILLING | 1175 | 1175 | 0 |  | 100% | 2025-01-31
REL-PMG-Cancer Center ¦ PMC ¦ Curver Metal Pan Sample Fab Release | 2025-01-10 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-01-22
REL-PMC ¦ PMU ¦ TEST_PNL_ASSEMBLY | 2025-02-12 |  |  | COMPLETE IN MILLING | 79 | 79 | 0 |  | 100% | 2025-03-07
REL-PMC ¦ PMU ¦ Post-Paint Metal PAN Fab Release | 2025-02-17 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-02-28 | POST PAINTED PARTS READY 2/20/25 SPECTRUM
REL-PMC-Curved Metal Pan 2nd test with More Tabs | 2025-02-27 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-03-07
REL-PMG-Garage - Spectrum missing and damaged materials list | 2025-03-05 |  |  | COMPLETE IN MILLING | 13 | 13 | 0 |  | 100% | 2025-03-14
REL-PMC-PMU CW Fab Release | 2025-03-25 |  |  | COMPLETE IN MILLING | 719 | 719 | 0 |  | 100% | 2025-04-11
REL-PMC-PMG ¦ Mullion Cover Sample | 2025-03-25 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-04-04
REL-PMC-TST PANEL REMAKES | 2025-03-28 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-04-04
REL-PCC-P9.01 PMU Spiderclip Release | 2025-04-04 |  |  | COMPLETE IN MILLING | 286 | 286 | 0 |  | 100% | 2025-04-11 | GOING TO DKI
REL-PMC-CURVED METAL PAN SAMPLE | 2025-04-09 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-04-18
REL-PMC-Alum w/ Macropoxy Dowsil Testing - SP TO PS TO OFFICE | 2025-04-15 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-05-02
REL-PMC-PMU- ADDITIONAL PARTS | 2025-04-17 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2025-04-25
REL-PMC-1.1 Softstart | 2025-04-21 | 12 | 12 | IN PROGRESS | 79 | 1144 | 1065 | ALL SHOPS | 6.906% | 2025-05-30 | MISSING 651 [13], 652 [13], 667 [23], 1541 [13] 1626 [12] FROM KM
REL-PennMed-PMU Starter Sill Fab Release | 2025-04-22 |  |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2025-05-02
REL-PMU_Embed | 2025-04-22 |  |  | COMPLETE IN MILLING | 52 | 52 | 0 |  | 100% | 2025-05-01
REL-PMC-REMAKES-S1558-9003-02 | 2025-04-28 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-29
REL-PMC- Post Paint ¦ Fin Cap Bulk Fab Release | 2025-04-29 |  |  | IN PROGRESS | 0 | 120 | 120 | TIM | 0% | 2025-05-09 | NEEDS POST PAINT
REL-PMC- 1.1 ¦ New BOM added for 1.1 (Exclude the softstart PNL) | NOT RELEASED |  |  | NOT IN PROGRESS
REL-NEO-PMC-2.1 FAB RELEASE | NOT RELEASED |  |  | NOT IN PROGRESS
32 |  | 12 | 12 |  | 4811 | 5996 | 1185 |  | 80.24%
June material delivery.

## STRIDER
STRIDER BLDG.
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
REL-SDH-BMU ACCESSORIES | 2024-10-31 | BMU |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-11-08
Spectrum Samples | 2025-01-08 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-01-10
REL-SDH-VMU STARTER SILL | 1/16/25 2/25/25 | VMU STARTER |  | COMPLETE IN MILLING | 103 | 103 | 0 |  | 100% | 2/14/25 COMPLETE 3/7/25
REL-SDH-VMU PANELS [4 Units] | 2025-01-16 | VMU UNITS |  | COMPLETE IN MILLING | 492 | 492 | 0 |  | 100% | 2025-02-21 | MISSING 582 [21] FROM KM
REL-SDH-VMU STEEL STRUCTURE | 1/28/25 2/24/25 | VMU STEEL |  | COMPLETE IN MILLING | 52 | 52 | 0 |  | 100% | 2025-02-28
REL-SDH-PMU STARTERSILL | 2025-03-10 | PMU STARTER SILL |  | WAITING ON MATERIAL | 169 | 194 | 25 | SEAN | 87.11% | 2025-05-09 | MISSING 372 [3] FROM KM
REL-SDH-PMU PANELS [6 Units] | 3/10/25 3/31/25 | PMU 6 UNITS |  | WAITING ON MATERIAL | 593 | 705 | 112 | ALL SHOPS | 84.11% | 2025-05-09 | MISSING 365 [20], 366 [8], 370 [4], 371 [4] FROM KM
REL-SDH-SAMPLE WELDED COPING | 2025-03-13 | SAMPLE |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-03-17
BULK RELEASE - TYP EMBED FA-5001 | 2025-04-02 | EMBEDS |  | COMPLETE IN MILLING | 5200 | 5200 | 0 |  | 100% | 2025-04-25 | SITE
REL-SDH-SAMPLE ROLLED SCALLOP | 2025-04-07 | SAMPLE |  | WAITING ON TOOLING | 0 | 3 | 3 | ALL SHOPS | 0% | 2025-04-25 | WAITING ON TOOLING
BULK RELEASE - BACKPAN | 2025-04-08 | BULK BPN |  | IN PROGRESS | 3722 | 4340 | 618 | TIM | 85.76% | 2025-05-09
REL-SDH-PMU 2.0 PANEL [1 Unit] | 2025-04-14 | PMU |  | IN PROGRESS | 64 | 85 | 21 | ALL SHOPS | 75.29% | 2025-05-02 | MISSING 365 [1], 366 [1], 663 [2] FROM KM
BULK RELEASE - CROSS BAR | 2025-04-14 | BARS |  | IN PROGRESS | 0 | 1147 | 1147 | BRIAN | 0% | 2025-05-16 | MISSING S03922 [1124]
REL-SDH-PMU 2.0 SITE MATERIAL | 2025-04-15 | PMU |  | WAITING ON MATERIAL | 40 | 41 | 1 | SEAN | 97.56% | 2025-05-02 | MISSING 372 [1] FROM KM | HOT
BULK RELEASE - SS PLATES & KOROLATH SHIMS | 2025-04-16 | PLATES AND SHIMS |  | IN PROGRESS | 826 | 10476 | 9650 | ALL SHOPS | 7.885% | 2025-05-30 | MISSING 1/4" PLATE
BULK RELEASE - PAINTED ALU PLATES | 2025-04-16 | PLATES |  | WAITING ON MATERIAL | 0 | 462 | 462 | TIM | 0% | 5/2/25 - 7/2/25 [IF REC'D BY 6/11/25] | MISSING 1/4" PLATE 136,135,137 [350] ORDER NOT RELEASE [7 WEEK LEADTIME] NEEDS TO GO TO PAINT
BULK RELEASE - SLIDERS & HOOKS | 2025-04-16 | SLIDERS AND HOOKS |  | NOT IN PROGRESS | 0 | 2259 | 2259 | BRIAN | 0% | 2025-05-23
REL-SDH-SAMPLE ROLLED SCALOOP 2.0 | 2025-04-21 | SAMPLE |  | NOT IN PROGRESS | 0 | 3 | 3 | ALL SHOPS | 0% | 2025-05-02
[7 empty] | 0 |  | #DIV/0!
[7 empty] | 0 |  | #DIV/0!
[7 empty] | 0 |  | #DIV/0!
[7 empty] | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
18 |  | 0 | 0 |  | 11286 | 25587 | 14301 |  | 44.11%

## REGENERON
REGENERON
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
REL-REG-SOFF-COP-TEST | 12/20/24 2/18/25 | TEST |  | COMPLETE IN MILLING | 41 | 41 | 0 |  | 100% | 2025-02-28
REG-DOW-SAMPLES-SILVERGREY | 2025-03-19 | SAMPLES |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-03-28
REG-DOW-SAMPLES-BISTROBRONZE | 2025-03-19 | SAMPLES |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-03-28
REL-REG-ACC-POST-PAINTED-B29 | 2025-03-31 |  |  | COMPLETE IN MILLING | 125 | 125 | 0 |  | 100% | 2025-04-11
REL-REG-29.01-COP | 2025-04-21 | COPING |  | NOT IN PROGRESS | 0 | 427 | 427 | ALL SHOPS | 0% | 2025-06-13 | NO MATERIAL
REL-REG-29.01-SFAS | 2025-04-21 | SOFFIT |  | NOT IN PROGRESS | 0 | 142 | 142 | TIM | 0% | 2025-06-13 | NO MATERIAL
REL-REG-29.01A [10 Units] | 2025-04-21 | 10 | 10 | NOT IN PROGRESS | 0 | 1500 | 1500 | ALL SHOPS | 0% | 2025-06-13 | NO MATERIAL
REL-REG-29.01B [132 Units] | 2025-04-21 | 132 | 132 | IN PROGRESS | 264 | 15137 | 14873 | ALL SHOPS | 1.744% | 2025-06-13 | NO MATERIAL
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
8 |  | 142 | 142 |  | 446 | 17388 | 16942 |  | 2.565%
MILLING JULY

## JEFFERSON
JEFFERSON
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
Perforated Sheet Pattern - Test | 2025-01-22 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-01-29
REL-JEF-SAM-001 | 2025-01-28 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-07
Perforated Sheet Pattern - Test 2 | 2025-01-30 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-01-30
REL-JEF-SAM-002 | 2025-01-30 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-01-30
REL-JEF-SAM-003 | 2025-02-12 |  |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2025-02-21
Sample Release 004 Non-Perforated Sheet and Angles | 3/3/25 3/5/25 |  |  | COMPLETE IN MILLING | 19 | 19 | 0 |  | 100% | 3/3/25 3/7/25
VMU [3 UNITS] | 3/19/25 4/4/25 REVISED 4/28/25 ADD ON 4/30/25 ADD ON |  |  | IN PROGRESS | 457 | 461 | 4 | TIM | 99.13% | 4/8/25 5/2/25 5/2/25 | NEED REVISED INFO NEEDS TO GO TO PAINT
REL-JEF-SAMPLES | 3/21/25 3/28/25 ADD ON |  |  | COMPLETE IN MILLING | 130 | 130 | 0 |  | 100% | 2025-04-11
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
8 |  | 0 | 0 |  | 616 | 620 | 4 |  | 99.35%

## NYPCC
NYPCC
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
WT-03 Steel Test | 2024-12-23 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-01-03
GFRC Spider Anchor | 2025-02-12 |  |  | COMPLETE IN MILLING | 400 | 400 | 0 |  | 100% | 2025-03-07 | WAITING ON 12GA 304 SS MATERIAL
REL-PCC-9.02 | 2025-02-18 |  |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2025-02-21 | WAITING ON 5052 ALU MATERIAL
Curved Plate Template | 2025-02-21 |  |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2025-02-28
REL-PCC ¦ REL-PCC-PMU_T1 Internal Impact Test Release | 2025-03-05 |  |  | COMPLETE IN MILLING | 24 | 24 | 0 |  | 100% | 2025-03-14
REL-PCC-VMU1 | 2025-03-07 |  |  | COMPLETE IN MILLING | 517 | 517 | 0 |  | 100% | 2025-04-11 | NEEDS TO GO TO PAINT MISSING T0145 [14] TUBE GOT UPDATED INFO 4/24/25
REL-PCC-VMU2 | 2025-03-18 |  |  | COMPLETE IN MILLING | 778 | 778 | 0 |  | 100% | 2025-04-18 | NEEDS TO GO TO PAINT
REL-PCC-9.03 WT02 INTERNAL TRIM SAMPLE | 2025-03-31 |  |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2025-04-11
REL-PCC-PMU_T2 Internal Impact Test Alum. Tubes | 2025-04-07 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2025-04-18
REL-PCC ¦ VMU1 Revisions - WT3 BSA | 2025-04-10 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-11 | NEEDS TO GO TO PAINT
REL-NYPCC-CT_SAMPLE (AP) TO OFFICE | 2025-04-16 |  |  | COMPLETE IN MILLING | 2 | 2 | 0 |  | 100% | 2025-04-25
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
11 |  | 0 | 0 |  | 1755 | 1755 | 0 |  | 100%

## MET TANG (hidden)
MET TANG
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
Mock Up | 2/6/25 2/19/25 |  |  | COMPLETE IN MILLING | 9 | 9 | 0 |  | 100% | 2025-02-21
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
1 |  | 0 | 0 |  | 9 | 9 | 0 |  | 100%

## OBH
ONE BEVERLY HILLS
RELEASE | RELEASE DATES | PANEL COUNT | UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
OBH ¦ V-GROOVED FPN SAMPLE FAB RELEASE | 2025-03-07 |  |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2025-03-12
POST-PAINT RAILING TRIM FAB RELEASE | 2025-03-13 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2025-03-14
PNL-OBH-9001-01 | 2025-03-13 |  |  | COMPLETE IN MILLING | 12 | 12 | 0 |  | 100% | 2025-03-17
PNL-OBH-9002-01 | 3/17/25 3/20/25 |  |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2025-03-21
OBH_RAILING | 2025-03-18 |  |  | COMPLETE IN MILLING | 3 | 3 | 0 |  | 100% | 2025-03-21
Mock Up Support Frame | 2025-04-29 |  |  | IN PROGRESS | 0 | 1 | 1 | JON | 0% | 2025-05-02
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
[5 empty] | 0 | 0 | 0 |  | #DIV/0!
6 |  | 0 | 0 |  | 50 | 51 | 1 |  | 98.04%