## Sheet1
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL PARTS | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
REL-FMG-1.02 [42 Units] | 2024-06-27 | 42 | 3384 |  | COMPLETE IN MILLING | 3384 | 3384 | 0 |  | 100% | 2024-07-19 | MISSING 1473 [2], 1474 [2] FROM KM BPN [113] ON HOLD
REL-FMG-1.02-FINS | 2024-06-27 | FINS | 2552 |  | COMPLETE IN MILLING | 2552 | 2552 | 0 |  | 100% | 2024-07-19 | MISSING 631 [45] FROM KM
REL-FMG-BULK-FINCAPS | 2024-07-01 | CAPS | 2340 |  | COMPLETE IN MILLING | 2340 | 2340 | 0 |  | 100% | 2024-07-19 | CAPS READY FOR POST PAINT 7/23/24
REL-FMG-EMB-BAR2-LVL3 | 2024-07-18 | EMBEDS | 208 |  | COMPLETE IN MILLING | 208 | 208 | 0 |  | 100% | 2024-08-16 | SITE
REL-FMG-SB-EWA-3 | 2024-07-18 | SHADOW BOXES | 493 |  | COMPLETE IN MILLING | 493 | 493 | 0 |  | 100% | 2024-11-29 | 707 TO ASSEMBLE
REL-FMG-1.03 [24 Units] | 2024-07-18 | 24 | 1902 |  | COMPLETE IN MILLING | 1902 | 1902 | 0 |  | 100% | 2024-09-20
REL-FMG-1.03-FINS | 2024-07-18 | FINS | 1295 |  | COMPLETE IN MILLING | 1295 | 1295 | 0 |  | 100% | 2024-09-20 | WAITING ON SNOW BUTTONS
REL-FMG-1.04 (42 Units) | 2024-07-22 | 42 | 3286 |  | COMPLETE IN MILLING | 3286 | 3286 | 0 |  | 100% | 2024-10-11 | MISSING 1473 [2] FROM KM
REL-FMG-1.04-FINS | 2024-07-22 | FINS | 3297 |  | COMPLETE IN MILLING | 3297 | 3297 | 0 |  | 100% | 2024-10-11
REL-FMG-1.02-FOAM | 2024-07-25 | FOAM | 616 |  | COMPLETE IN MILLING | 616 | 616 | 0 |  | 100% | 2024-08-02
REL-FMG-RIMU6 | 2024-07-26 | MOCKUP | 55 |  | COMPLETE IN MILLING | 55 | 55 | 0 |  | 100% | 2024-07-29
REL-FMG-RIMU7 | 2024-07-26 | MOCKUP | 89 |  | COMPLETE IN MILLING | 89 | 89 | 0 |  | 100% | 2024-07-29
REL-FMG-RIMU8 | 2024-08-05 | MOCKUP | 38 |  | COMPLETE IN MILLING | 38 | 38 | 0 |  | 100% | 2024-08-09
REL-FMG-RIMU9 | 2024-08-06 | MOCKUP | 17 |  | COMPLETE IN MILLING | 17 | 17 | 0 |  | 100% | 2024-08-09
REL-FMG-RIMU7.2 | 2024-08-12 | MOCKUP | 94 |  | COMPLETE IN MILLING | 94 | 94 | 0 |  | 100% | 2024-08-14
REL-FMG-POSTPAINT-BULKBATCH1 | 2024-08-12 | BULK | 142 |  | COMPLETE IN MILLING | 142 | 142 | 0 |  | 100% | 2024-09-06
REL-FMG-1.01 [22 Units] | 2024-08-12 | 22 | 1237 |  | COMPLETE IN MILLING | 1237 | 1237 | 0 |  | 100% | 2024-10-11
REL-FMG-1.01 FINS | 2024-08-12 | FINS | 845 |  | COMPLETE IN MILLING | 845 | 845 | 0 |  | 100% | 2024-10-11
REL-FMG-BAR2-PHROOF | 2024-08-12 | EMBEDS | 424 |  | COMPLETE IN MILLING | 424 | 424 | 0 |  | 100% | 2024-08-30 | SITE
REL-FMG-1.05 | 2024-08-12 | 21 | 1606 |  | COMPLETE IN MILLING | 1606 | 1606 | 0 |  | 100% | 2024-11-29
REL-FMG-1.05 FINS | 2024-08-12 | FINS | 764 |  | COMPLETE IN MILLING | 764 | 764 | 0 |  | 100% | 2024-11-29
REL-FMG-BAR2-PENTHOUSE | 2024-08-12 | EMBEDS | 107 |  | COMPLETE IN MILLING | 107 | 107 | 0 |  | 100% | 2024-08-30 | SITE
REL-FMG-BAR2-LVL4 | 2024-08-12 | EMBEDS | 154 |  | COMPLETE IN MILLING | 154 | 154 | 0 |  | 100% | 2024-08-23 | SITE
REL-FMG-BAR1-LVL4 | 2024-08-12 | EMBEDS | 437 |  | COMPLETE IN MILLING | 437 | 437 | 0 |  | 100% | 2024-08-23 | SITE
REL-FMG-JIG-TEST | 2024-08-13 | JIG | 4 |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-08-16
REL-FMG-FOAM-BULK-BATCH2 | 2024-09-10 | BULK | 3086 |  | COMPLETE IN MILLING | 3086 | 3086 | 0 |  | 100% | 2024-10-11
REL-FMG-STS-1.01 | 2024-09-10 | STARTER SILL | 290 |  | COMPLETE IN MILLING | 290 | 290 | 0 |  | 100% | 2024-11-22 | MISSING 1607 [25] FROM KM
REL-FMG-STS-1.07 | 2024-09-10 | STARTER SILL | 157 |  | COMPLETE IN MILLING | 157 | 157 | 0 |  | 100% | 2024-11-22 | MISSING 1607 [13] FROM KM
REL-FMG-EMB-BAR3-LVL2 | 2024-09-10 | EMBEDS | 142 |  | COMPLETE IN MILLING | 142 | 142 | 0 |  | 100% | 2024-10-25 | SITE
REL-FMG-EMB-BAR3-LVL3 | 2024-09-10 | EMBEDS | 132 |  | COMPLETE IN MILLING | 132 | 132 | 0 |  | 100% | 2024-11-01 | SITE
REL-FMG-EMB-BAR4-LVL1 | 2024-09-10 | EMBEDS | 134 |  | COMPLETE IN MILLING | 134 | 134 | 0 |  | 100% | 2024-10-25 | SITE
REL-FMG-EMB-BAR4-LVL2 | 2024-09-10 | EMBEDS | 382 |  | COMPLETE IN MILLING | 382 | 382 | 0 |  | 100% | 2024-10-25 | SITE
REL-FMG-EMB-BAR3-LVL4 | 2024-09-10 | EMBEDS | 148 |  | COMPLETE IN MILLING | 148 | 148 | 0 |  | 100% | 2024-11-01 | SITE
REL-FMG-EMB-BAR4-LVL3 | 2024-09-10 | EMBEDS | 308 |  | COMPLETE IN MILLING | 308 | 308 | 0 |  | 100% | 2024-11-01 | SITE
REL-FMG-EMB-BAR4-LVL4 | 2024-09-10 | EMBEDS | 418 |  | COMPLETE IN MILLING | 418 | 418 | 0 |  | 100% | 2024-11-01 | SITE
REL-FMG-MP-FIELDFIX | 2024-09-17 | FIX | 50 |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-09-30 | SITE
REL-FMG-STS-11.03 | 2024-09-30 | STARTER SILL | 44 |  | COMPLETE IN MILLING | 44 | 44 | 0 |  | 100% | 2024-12-27
REL-FMG-STS-11.01 | 2024-09-30 | STARTER SILL | 259 |  | COMPLETE IN MILLING | 259 | 259 | 0 |  | 100% | 2024-12-27
REL-FMG-STS-11.05 | 2024-09-30 | STARTER SILL | 165 |  | COMPLETE IN MILLING | 165 | 165 | 0 |  | 100% | 2024-12-27
REL-EMBED-STEEL-BAR1-LVL2 | 2024-09-30 | EMBEDS | 48 |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR2-PENTHOUSE | 2024-09-30 | EMBEDS | 33 |  | COMPLETE IN MILLING | 33 | 33 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR1-LVL4 | 2024-09-30 | EMBEDS | 22 |  | COMPLETE IN MILLING | 22 | 22 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR1-LVL3 | 2024-09-30 | EMBEDS | 57 |  | COMPLETE IN MILLING | 57 | 57 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR2-LVL2 | 2024-09-30 | EMBEDS | 47 |  | COMPLETE IN MILLING | 47 | 47 | 0 |  | 100% | 2024-10-18 | SITE
REL-EMBED-STEEL-BAR2-MECH PLATFORM | 2024-09-30 | EMBEDS | 377 |  | COMPLETE IN MILLING | 377 | 377 | 0 |  | 100% | 2024-10-18 | SITE
REL-FMG-1.06 [44 Units] | 2024-09-10 | 44 | 3246 |  | COMPLETE IN MILLING | 3246 | 3246 | 0 |  | 100% | 2024-11-22
REL-FMG-1.06 FINS | 2024-10-01 | FINS | 4635 |  | COMPLETE IN MILLING | 4635 | 4635 | 0 |  | 100% | 2024-11-22
REL-FMG-1.07 [19 UNITS] | 2024-10-01 | 19 | 1349 |  | COMPLETE IN MILLING | 1349 | 1349 | 0 |  | 100% | 2024-11-22
REL-FMG-1.07_FIN | 2024-10-01 | FINS | 1082 |  | COMPLETE IN MILLING | 1082 | 1082 | 0 |  | 100% | 2024-11-22
REL-FMG-1.08 [36 UNITS] | 2024-10-01 | 36 | 2029 |  | COMPLETE IN MILLING | 2029 | 2029 | 0 |  | 100% | 2024-12-06
REL-FMG-1.08-FINS | 2024-10-01 | FINS | 1449 |  | COMPLETE IN MILLING | 1449 | 1449 | 0 |  | 100% | 2024-12-06