## Sheet1
RELEASE | RELEASE DATES | TOTAL UNIT COUNT | TOTAL UNITS LEFT | STATUS | PARTS FABRICATED | TOTAL PARTS | DELTA | SHOP | % OF COMPLETION | EST. COMPLETION DATES | NOTES
Release ¦ VMU | 2023-09-18 | VMU |  | COMPLETE IN MILLING | 302 | 302 | 0 |  | 100%
Release ¦ VMU - SITE MATERIAL | 2023-10-10 | VMU |  | COMPLETE IN MILLING | 93 | 93 | 0 |  | 100% | 2023-10-17
Release ¦ STEEL BRACKETS LVL6 - WELDED ON SITE | 2024-01-05 | BRACKETS |  | COMPLETE IN MILLING | 84 | 84 | 0 |  | 100% | 2024-01-12
Release ¦ PMU | 2024-01-31 | PMU |  | COMPLETE IN MILLING | 165 | 165 | 0 |  | 100% | 2024-02-09
Release ¦ LEVEL 02 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 1808 | 1808 | 0 |  | 100% | 2024-04-19 | 2024-05-01
Release ¦ LEVEL 03 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 3036 | 3036 | 0 |  | 100% | 2024-05-10
Release ¦ LEVEL 04 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 2832 | 2832 | 0 |  | 100% | 2024-05-17 | 2024-05-20
Release ¦ LEVEL 05 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 2878 | 2878 | 0 |  | 100% | 2024-05-24
Release ¦ LEVEL 06 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 1135 | 1135 | 0 |  | 100% | 2024-06-07
Release ¦ LEVEL 07 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 1564 | 1564 | 0 |  | 100% | 2024-06-21
Release ¦ LEVEL 08 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 1796 | 1796 | 0 |  | 100% | 2024-06-28
Release ¦ LEVEL 09 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 3177 | 3177 | 0 |  | 100% | 2024-07-12
Release ¦ LEVEL 10 TYPICAL EMBED ORDER | 2024-02-26 | EMBEDS |  | COMPLETE IN MILLING | 2769 | 2769 | 0 |  | 100% | 2024-07-26
Release ¦ EMB-001 | 2024-03-08 | EMBEDS |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100%
Release ¦ LEVEL 02 UNTYPICAL EMBED ORDER | 2024-04-29 | EMBEDS |  | COMPLETE IN MILLING | 567 | 567 | 0 |  | 100% | 2024-05-03
Release ¦ LEVEL 03 UNTYPICAL EMBED ORDER | 2024-04-29 | EMBEDS |  | COMPLETE IN MILLING | 562 | 562 | 0 |  | 100% | 2024-05-10
Release ¦ LEVEL 04 UNTYPICAL EMBED ORDER | 2024-04-29 | EMBEDS |  | COMPLETE IN MILLING | 205 | 205 | 0 |  | 100% | 2024-05-17 | 2024-05-20
Release ¦ LEVEL 05 UNTYPICAL EMBED ORDER | 2024-04-29 | EMBEDS |  | COMPLETE IN MILLING | 168 | 168 | 0 |  | 100% | 2024-05-24
Release ¦ LEVEL 06 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 158 | 158 | 0 |  | 100% | 2024-06-07
Release ¦ LEVEL 07 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 228 | 228 | 0 |  | 100% | 2024-06-21
Release ¦ LEVEL 08 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 186 | 186 | 0 |  | 100% | 2024-06-28
Release ¦ LEVEL 09 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 76 | 76 | 0 |  | 100% | 2024-07-12
Release ¦ LEVEL 10 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 76 | 76 | 0 |  | 100% | 2024-07-26
Release ¦ LEVEL 11 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 2721 | 2721 | 0 |  | 100% | 2024-08-02
Release ¦ LEVEL 12 UNTYPICAL EMBED ORDER | 2024-05-13 | EMBEDS |  | COMPLETE IN MILLING | 2046 | 2046 | 0 |  | 100% | 2024-08-09
Release ¦ LEVEL 02-04 EMBED EAR EXTENSION RELEASE | 2024-05-28 | EMBEDS |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2024-06-14
REL-RUT-4.1_1CW | 6/10/24 7/8/24 | 51 SHM |  | COMPLETE IN MILLING | 4473 | 4473 | 0 |  | 100% | 2024-07-05
REL-RUT-1.01 A [55 UNITS] | 2024-06-25 | 55 |  | COMPLETE IN MILLING | 4798 | 4798 | 0 |  | 100% | 2024-08-02 | MISSING 592 [58] FROM KM
REL-RUT-4.1_2CW [242 UNITS] | 2024-06-25 | 242 |  | COMPLETE IN MILLING | 13439 | 13439 | 0 |  | 100% | 2024-08-16 | MISSING 592 [10] FROM KM
REL-RUT-4.1ACW [4 UNITS] | 2024-06-25 | 4 |  | COMPLETE IN MILLING | 195 | 195 | 0 |  | 100% | 2024-08-30 | MISSING 592 [6] FROM KM
REL-RUT-BULK ORDER 5.2 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 2272 | 2272 | 0 |  | 100% | 2024-09-06
REL-RUT-BULK ORDER 5.1 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 9885 | 9885 | 0 |  | 100% | 2024-09-13
REL-RUT-BULK ORDER 4.2 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 2004 | 2004 | 0 |  | 100% | 2024-09-27
REL-RUT-BULK ORDER 4.3 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 6030 | 6030 | 0 |  | 100% | 2024-11-22
REL-RUT-BULK ORDER 4.4 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 10929 | 10929 | 0 |  | 100% | 2024-11-29 | TO 393
REL-RUT-BULK ORDER 4.6 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 1426 | 1426 | 0 |  | 100% | 2024-12-27 | TO 393
REL-RUT-BULK ORDER 5.3 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 603 | 603 | 0 |  | 100% | 2024-11-15
REL-RUT-BULK ORDER 7.1 | 2024-06-25 | BULK |  | COMPLETE IN MILLING | 2103 | 2103 | 0 |  | 100% | 2024-11-15
REL-RUT-EMB-903 | 2024-07-08 | EMBEDS |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-07-12
REL-RUT-4.1_3 CW [4 UNITS] | 2024-07-09 | 4 |  | COMPLETE IN MILLING | 267 | 267 | 0 |  | 100% | 2024-08-02
REL-RUT-FIN END CAPS | 2024-07-10 | CAPS |  | COMPLETE IN MILLING | 2290 | 2290 | 0 |  | 100% | 2024-07-19 | CAPS READY FOR PAINT 7/17/24
REL-RUT-EMB-005 LVL 02 | 2024-07-11 | EMBEDS |  | COMPLETE IN MILLING | 766 | 766 | 0 |  | 100% | 2024-08-16 | SITE
REL-RUT-EMB-005 LVL 03 | 2024-07-11 | EMBEDS |  | COMPLETE IN MILLING | 594 | 594 | 0 |  | 100% | 2024-08-16 | SITE
REL-RUT-BULK ORDER 11.2 | 2024-07-11 | BULK |  | COMPLETE IN MILLING | 442 | 442 | 0 |  | 100% | 2024-03-21
REL-RUT-SILL-001 | 2024-07-15 | STARTER |  | COMPLETE IN MILLING | 2292 | 2292 | 0 |  | 100% | 2024-08-16 | SITE
REL-RUT-EMB-904 | 2024-07-16 | EMBEDS |  | COMPLETE IN MILLING | 100 | 100 | 0 |  | 100% | 2024-07-16 | SITE
RUT BPN PARTS | 2024-07-16 | BPN |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-07-16
RUT WOOD BUNK PARTS | 2024-07-17 | BUNK PARTS |  | COMPLETE IN MILLING | 4800 | 4800 | 0 |  | 100% | 2024-07-26
REL-RUT-2.1A CW [43 UNITS] | 2024-07-26 | 43 |  | COMPLETE IN MILLING | 8147 | 8147 | 0 |  | 100% | 2024-08-23 | MISSING 592 [397] FROM KM MISSING COUPLER NUTS [156] FROM VENDOR
REL-RUT-2.2A CW [16 UNITS] | 2024-07-26 | 16 |  | COMPLETE IN MILLING | 4785 | 4785 | 0 |  | 100% | 2024-08-09 | MISSING 592 [160] FROM KM
REL-RUT-2.1 CW [40 UNITS] | 2024-07-26 | 40 |  | COMPLETE IN MILLING | 5988 | 5988 | 0 |  | 100% | 2025-01-10 |  | 393
REL-RUT-2.2A STEEL FRAMES | 2024-07-31 | FRAMES |  | COMPLETE IN MILLING | 288 | 288 | 0 |  | 100% | 2024-08-23 | 4 PRIORITY FRAMES READY FOR HDG 8/28/24
REL-RUT-2.2B STEEL FRAMES | 2024-07-31 | FRAMES |  | COMPLETE IN MILLING | 56 | 56 | 0 |  | 100% | 2024-08-23 | HDG
REL-RUT-SILL-002 | 2024-08-05 | STARTER |  | COMPLETE IN MILLING | 523 | 523 | 0 |  | 100% | 2024-08-09
REL-RUT-8.1A CW [12 UNITS] | 2024-08-19 | 12 |  | COMPLETE IN MILLING | 2130 | 2130 | 0 |  | 100% | 2024-09-06 | MISSING 592 [24] FROM KM
REL-RUT-SILL-003 | 2024-08-19 | STARTER |  | COMPLETE IN MILLING | 364 | 364 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-SILL-004 | 2024-08-19 | STARTER |  | COMPLETE IN MILLING | 48 | 48 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-4.2 CW [28 UNITS] | 2024-08-19 | 28 |  | COMPLETE IN MILLING | 2903 | 2903 | 0 |  | 100% | 2024-10-11 | WAITING ON STL 1/8 and 1/4
REL-RUT-5.1 CW [268 UNITS] | 2024-08-21 | 268 |  | COMPLETE IN MILLING | 2808 | 2808 | 0 |  | 100% | 2024-09-20
REL-RUT-4.3 CW [226 UNITS] | 2024-08-21 | 226 |  | COMPLETE IN MILLING | 1844 | 1844 | 0 |  | 100% | 2024-11-22
REL-RUT-8.1 CW [13 UNITS] | 2024-08-23 | 13 |  | COMPLETE IN MILLING | 2066 | 2066 | 0 |  | 100% | 2024-10-18
REL-RUT-INFILL PANELS BULK ORDER | 2024-08-26 | BULK |  | COMPLETE IN MILLING | 304 | 304 | 0 |  | 100% | 2024-10-25
REL-RUT-LEVEL PH1 EMBED ORDER | 2024-08-26 | EMBEDS |  | COMPLETE IN MILLING | 2324 | 2324 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-LEVEL PH2 EMBED ORDER | 2024-08-26 | EMBEDS |  | COMPLETE IN MILLING | 2380 | 2380 | 0 |  | 100% | 2024-09-27 | SITE
REL-RUT-BULK ORDER 1.2 | 2024-08-26 | BULK |  | COMPLETE IN MILLING | 30 | 30 | 0 |  | 100% | 2024-10-25
REL-RUT-BULK ORDER 1.1 | 2024-08-26 | BULK |  | COMPLETE IN MILLING | 54 | 54 | 0 |  | 100% | 2024-10-18
REL-RUT-LEVEL PH2 ROOF EMBED ORDER | 2024-08-26 | EMBEDS |  | COMPLETE IN MILLING | 1539 | 1539 | 0 |  | 100% | 2024-09-27 | SITE
REL-RUT-MISC-003 - SPREADER BAR | 2024-09-05 | MISC |  | COMPLETE IN MILLING | 10 | 10 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-5.2 CW [42 UNITS] | 2024-09-10 | 42 |  | COMPLETE IN MILLING | 4626 | 4626 | 0 |  | 100% | 2024-11-15 | WAITING ON STL 1/8 and 1/4
REL-RUT-MISC-004 | 2024-09-13 | MISC |  | COMPLETE IN MILLING | 3160 | 3160 | 0 |  | 100% | 2024-09-16 | SITE
ALU-RUT-S1520-5012-01 | 2024-09-13 | MISC |  | COMPLETE IN MILLING | 45 | 45 | 0 |  | 100% | 2024-09-16
REL-RUT-EMB-905 | 2024-09-20 | EMBEDS |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-09-27 | SITE
REL-RUT-MISC-006 | 2024-09-20 | MISC |  | COMPLETE IN MILLING | 120 | 120 | 0 |  | 100% | 2024-09-20 | SITE
REL-RUT-MISC-002 | 2024-09-20 | MISC |  | COMPLETE IN MILLING | 430 | 430 | 0 |  | 100% | 2024-09-27 | SITE
RUT - CW7 CORNER SLIDERS | 2024-09-20 | SLIDERS |  | COMPLETE IN MILLING | 16 | 16 | 0 |  | 100% | 2024-10-04 | READY FOR TO CARNEY
REL-RUT-SILL-005 | 2024-09-20 | STARTER |  | COMPLETE IN MILLING | 473 | 473 | 0 |  | 100% | 2024-10-11 | SITE
REL-RUT-5.3 [28 Units] | 2024-09-20 | 28 |  | COMPLETE IN MILLING | 237 | 237 | 0 |  | 100% | 2024-10-25
REL-RUT-10.1 [62 Units] | 2024-09-20 | 62 |  | COMPLETE IN MILLING | 8327 | 8327 | 0 |  | 100% | 2024-11-29
REL-RUT-10.3 [31 Units] | 2024-09-20 | 31 |  | COMPLETE IN MILLING | 3407 | 3407 | 0 |  | 100% | 2024-11-29
REL-RUT-2.2B [18 Units] | 2024-09-20 | 18 |  | COMPLETE IN MILLING | 3021 | 3021 | 0 |  | 100% | 2025-01-10 |  | 393
REL-RUT-MISC-005 | 2024-09-20 | MISC |  | COMPLETE IN MILLING | 50 | 50 | 0 |  | 100% | 2024-10-04 | SITE
REL-RUT-EMB-008 | 2024-09-23 | EMBEDS |  | COMPLETE IN MILLING | 27 | 27 | 0 |  | 100% | 2024-09-27 | SITE
REL-RUT-EMB-007 | 2024-09-26 | EMBEDS |  | COMPLETE IN MILLING | 649 | 649 | 0 |  | 100% | 2024-11-01
REL-RUT-SILL-001.1 | 2024-09-26 | STARTER |  | COMPLETE IN MILLING | 8 | 8 | 0 |  | 100% | 2024-09-30 | SITE
REL-RUT-1.1 CW [48 UNITS] | 2024-10-04 | 48 |  | COMPLETE IN MILLING | 4101 | 4101 | 0 |  | 100% | 2024-10-18
REL - MISSING FIELD PARTS | 2024-10-10 | MISSING PARTS |  | COMPLETE IN MILLING | 4 | 4 | 0 |  | 100% | 2024-10-15 | SITE
REL-RUT-10.2 CW [17 Units] | 2024-10-16 | 17 |  | COMPLETE IN MILLING | 3359 | 3359 | 0 |  | 100% | 2024-11-29
REL-RUT-4.4 CW [360 Units] | 2024-10-16 | 360 |  | COMPLETE IN MILLING | 3740 | 3740 | 0 |  | 100% | 2024-11-29 | MISSING 580 [22] FROM KM | 393
REL-RUT-SILL-006 | 2024-10-16 | STARTER |  | COMPLETE IN MILLING | 411 | 411 | 0 |  | 100% | 2024-11-15 | SITE
REL-RUT-EMB-009 | 2024-10-17 | EMBEDS |  | COMPLETE IN MILLING | 6 | 6 | 0 |  | 100% | 2024-10-18 | SITE
REL-RUT-4.5 CW [407 UNITS] | 2024-10-21 | 407 |  | COMPLETE IN MILLING | 15568 | 15568 | 0 |  | 100% | 2024-12-27 |  | 350
REL-RUT-7.1 CW [124 UNITS] | 2024-10-21 | 124 |  | COMPLETE IN MILLING | 913 | 913 | 0 |  | 100% | 2024-11-15 |  | 393
REL-RUT-EMB-010 | 2024-10-24 | EMBEDS |  | COMPLETE IN MILLING | 26 | 26 | 0 |  | 100% | 2024-11-01 | SITE
REL-RUT-FLA-002 | 2024-10-31 | FLASHING |  | COMPLETE IN MILLING | 14 | 14 | 0 |  | 100% | 2024-11-15 | SITE
REL-RUT-MFP-002 | 2024-11-01 | MISC |  | COMPLETE IN MILLING | 128 | 128 | 0 |  | 100% | 2024-11-15 | SITE
REL-RUT-EMB-906 | 2024-11-01 | EMBEDS |  | COMPLETE IN MILLING | 1 | 1 | 0 |  | 100% | 2024-11-08 | SITE
REL-RUT-BULK ORDER 11.1 | 2024-11-01 | BULK |  | COMPLETE IN MILLING | 412 | 412 | 0 |  | 100% | 2024-11-29
REL-RUT-BULK ORDER 7.2 | 2024-11-01 | BULK |  | COMPLETE IN MILLING | 142 | 142 | 0 |  | 100% | 2024-12-06